# STANDARD BID DOCUMENT

# I  N  D  E  X

| No | Details | Page No. |
| --- | --- | --- |
| 1 | INDEX | 1 |
| 2. | TITLE | 2 & 3 |
| 3 | notice inviting tender (nit) Quality Control Lab (Page-8) | 4 to 11 |
| 4. | instructions to bidders | 11 to 21 |
|  | - General |  |
|  | - Bid Document | 22 |
|  | - Preparation of Bids | 22 to 29 |
|  | - Submission of Bids | 29 to 31 |
|  | - Bid Opening and Evaluation | 32 to 34 |
|  | - Award of Contract | 34 to 36 |
| 5. | ## Forms of Bid Qualification Information | ## 37 |
|  | ## Checklist to accompany the Bid | ## 38 to 40 |
|  | ## Statements (I to VII) | ## 40 to 45 |
|  | ## Under taking of bidder (Names of Technical Agents & Declaration of bidder etc., ) | ## 46 to 50 |
| 6. | ## Conditions of Contract |  |
|  | ## A) General | ## 51 to 61 |
|  | ## B) Time for completion | ## 61 to 66 |
|  | ## C) Quality Control Calibrated equipment list | ## 66 to 70 |
|  | ## D) Cost Control (Payments, Price Adjustments & Liquidated Damages) | ## 71 to 80 |
|  | ## E) Finishing the Contract | ## 81 to 83 |
|  | ## F) Special conditions (Indemnity Bond) | ## 83 to 106 |
| 7. | ## TECHNICAL SPECIFICATIONS | ## 107 to 238 |
| 8. | ## DRAWINGS | ## 239 to 241 |
| 9. | ## BILL OF QUANTITIES & PRICE BID | ## 242 to 253 |
| 10. | ## FORMATS OF SECURITIES | ## 254 to 259 |
| 11 | ## MOU (Enclosed – 12 pages) |  |
| 12 | ## Bar chart – (1 Page) |  |
| 13 | ## Technical Agents (As per Terms & Conditions) |  |
| 14 | ## Electrical & Public Health Registrations (As per Terms & Conditions) |  |

# GOVERNMENT OF ANDHRA PRADESH

# A.P EDUCATION & WELFARE INFRASTRUCTURE DEVELOPOMENT CORPORATION

# BID DOCUMENT

# Name of the work:	Construction of 208 Houses along with infrastructure and amenities at R.Ganapavaram Village (Colony), Buttaigudem Mandal, Eluru District for Rehabilitaton of the PDFs of Chinturu ITDA.

# Name of Circle	:	Guntur

# Name of Divisions : 	Eluru

# GOVERNMENT OF ANDHRA PRADESH

# A.P EDUCATION & WELFARE INFRASTRUCTURE DEVELOPOMENT CORPORATION

# BID DOCUMENT

# NIT No: 49/MD/APEWIDC/VJA/2026-27, Dated: 12.10.2026.

# VOLUME - I

# Name of the work:	Construction of 208 Houses along with infrastructure and amenities at R.Ganapavaram Village (Colony), Buttaigudem Mandal, Eluru District for Rehabilitaton of the PDFs of Chinturu ITDA.

# Name and address of	:	________________________________

# the bidder who down		________________________________

# loaded the bid documents

# GOVERNMENT OF ANDHRA PRADESH

# A.P EDUCATION & WELFARE INFRASTRUCTURE DEVELOPOMENT CORPORATION

*******

# NIT No: 49/MD/APEWIDC/VJA/2026-27, Dated: 12.10.2026.

# Name of the work:	Construction of 208 Houses along with infrastructure and amenities at R.Ganapavaram Village (Colony), Buttaigudem Mandal, Eluru District for Rehabilitaton of the PDFs of Chinturu ITDA.

# Officer inviting bids:	The Managing Director, APEWIDC, Door No. 9-76, Sai Fortune Heights, Block – A, Vaddeswaram (V), Tadepally (M), Guntur District, Amaravathi

- Bids are invited on the e-procurement platform for the above mentioned work from the Contractors/Contracting firms registered with Government of Andhra Pradesh. The details of bid conditions and terms can be downloaded from the electronic procurement platform of Government of Andhra Pradesh i.e. www.apeprocurement.gov.in

- Approximate Estimate Contract value of work:  Rs. 17,95,41,544/-

- Contractors would be required to register on the e-Procurement market place www.apeprocurement.gov.in and submit their bids online. The department will not accept any bid submitted in any other form including the paper form.

- Non refundable Processing fee of Rs. 1,18,000/- (including GST @ 18%) to be paid by way of online payment only through e-procurement platform and to upload the copy of Receipt slip.  Failure to pay the Processing fee in the aforesaid manner will entitle for rejection of the bid and debarred not to participate in APEWIDC tenders for a period of 3 Years.

- The bid Security of 1% on the ECV in the form of either Online / BG in favour of Managing Director, APEWIDC, Vijayawada. As per GO MS No.8, Dt.08.05.2016 in the standard format as shown in the bid document issued by any Nationalised/Schedule commercial Bank to be valid for 6 (Six) months from the date of NIT

- Period of completion of work		:  12 Months from the date of agreement

- The bidders can view/ down load the bid documents from the AP e-procurement platform

- Form of contract – Lump sum contract

- Class of Contractors eligible is  as given below:

- As per G.O Ms No. 94, I&CAD (PW.COD) Dept. Dated: 1/07/2003: Special Class (Civil)

- As per G.O Ms No. 63, Water Resources (Reforms) Department.

Dated: 13.11.2025: Class-I (Civil) (New/ Renewal)

- Downloading of bid documents: From   23.10.2026 to 06.11.2026

- Date and time for receipt of bids: From 23.10.2026 to 06.11.2026

- Time and date of opening of bids:

- PQ Stage				:  06.11.2026

- Commercial Stage		:  07.11.2026

Note:	The dates stipulated above are firm and under no circumstances they will be relaxed unless otherwise extended by an official notification or happens to be public holidays (in case holiday, the next day will be reconed for that purpose).

- Procedure for submission of bids:

- Bidders may contact the Office of The Managing Director, APEWIDC, Door No. 9-76, Sai Fortune Heights, Block–A, Vaddeswaram (V), Tadepally (M), Guntur District, Amaravathi for any information on e-Procurement.

- Bidders need to register on the electronic procurement market place of Government of Andhra Pradesh i.e., “http://www.eprocurement.gov.in”. On registration on the e-Procurement market place, the bidders they will be provided with a user Id and password by the system using which they can submit their bids online.

- While registering on the e-procurement market place, bidders need to scan and upload the required attested documents as per the bid requirements onto their profile. Such uploaded documents pertaining to technical bid need to be attached to the tender while submitting the tender online.

- As per G.O Ms No.174, I&CAD (PW-REFORMS) Department Dt.01/09/2008, the following modifications are made:

- All the bidders shall invariably upload the scanned copies of Online/ Bank Guarantee details in e-procurement system and this will be primary requirement to consider the bid as responsive.

- The Department shall carry out the Technical Bid Evaluation solely based on the uploaded certificates/documents, bank slips/BG Details of online payment towards Bid security in the e-procurement system and open the price bids of responsive bidders.

- The Department will notify the successful bidder for submission of original hard copies of all uploaded documents, /Details of online payment / BG towards Earnest Money Deposit prior to entering into agreement.

- The successful bidder shall invariably furnish the details of online payment / BG towards Earnest Money Deposit, 2.5% of ECV certificates/ documents of the uploaded scanned copies to the tender inviting Authority before entering into agreement either personally or through courier or post and the receipt of the same within the stipulated date shall be the responsibility of the successful bidder.

- The Department will not take any responsibility for any delay in receipt/non receipt of Details of Online payment / BG towards earnest money deposit, certificates/Documents, from the successful bidder before the stipulated time. On receipt of documents, the Department shall ensure the genuinity of the / Details of Online payment / BG towards Earnest Money Deposit and all other certificates/documents uploaded by the bidder in e-procurement system in support of the qualification criteria before concluding the agreement.

- If any successful bidder fails to submit the original Hard copies of uploaded certificates/documents, Details of payment towards Earnest Money Deposit within the stipulated time or if any variation is noticed between the uploaded documents and the hard copies submitted by the bidder, the successful bidder will be suspended from participating in the tenders on e-procurement platform for a period of 3 years. The e-procurement system would deactivate the user ID of such defaulting successful bidder based on the trigger/recommendation by the tender inviting authority in the system. Besides this, the Department shall invoke all processes of law including criminal prosecution of such defaulting bidder as on act of extreme deterrence to avoid delays in the tender process for execution of the development schemes taken up by the Government.

- Steps for registration and submission of bids are described in detail in the “Bidders Training Booklet” available as at the above web site.

- The Corporation will not hold any risk and responsibility for the loss in transit during uploading of the scanned documents, for the invisibility of the scanned documents online and any other problem(s) encountered by the bidder while submitting his bids in online.

- The bidder shall authenticate the bid with his digital certificate for submitting the bid electronically on e-procurement platform and the bids not authenticated by digital certificate of the bidder will not be accepted on the e-procurement platform.

- Qualification requirements: To qualify for consideration of award of the contract each bidder should fulfil the following criteria:

- Assessed available bid capacity as per formula (3AN-B) should be greater than Estimated Contract Value as specified in the bid document.

- The details and certificates are to be furnished as per the proforma available in the bid document.

- (a)	The bidder should have satisfactorily completed Similar nature of works (Buildings) of value not less than Rs. 8,97,70,772/- as a prime contractor in the same name and style in any one year during the financial years 2016-17 to 2025-26 updated to 2026-27 price level. GPA holder’s experience shall not be taken into account. The bidder should enclose certificate issued by the Engineer-in-Charge of the State/Central Government Departments/State Government undertakings and Central Government undertakings not below the rank of Executive Engineer or equivalent and countersigned by the Officer of the rank of Superintending Engineer or equivalent.

4.	The bidder should have executed the minimum quantities of items of work as given below in any one year during the financial years for Similar nature of works 2016-17 to 2025-26. The bidder should enclose certificate issued by the Engineer-in-Charge of the State/Central Government Departments/State Government undertakings and Central Government undertakings not below the rank of Executive Engineer or equivalent and countersigned by the Superintending Engineer or equivalent.

| Sl.No | Description of item | Quantity |
| --- | --- | --- |
| 1 | Earth Work Item | 2520 Cum |
| 2 | R.R Masonry or C.R.S Masonry or Brick Masonry or RBM or combined quantity | 2217 Cum |
| 3 | PCC or VCC or RCC or VRCC or combined quantity | 2034 Cum |
| 4 | Plastering or ornamental Plastering or Impervious Coat of any thickness (Combined quantity) | 41158 Sqm |
| 5 | Shahabad/Granite/Marble/Ceramic Tiles /Polished Kadapa Slabs/Unpolished Napa Slabs Flooring, Skirting, Dadooing, Treads, Raisers or combined quantity | 237 Sqm |

The bidder should submit the particulars invariably in the prescribed format specified in the bid document along with necessary certificates, failing which his bid shall be treated as incomplete and summarily rejected.

5.	The bidder should further demonstrate:

(i) Availability (either owned or leased) of the following key and critical equipment.

Bidder to submit a self-declaration as prescribed in Statement-V. Sufficient proof of document in support of own equipment such as invoice/ self-Certificate of regn.by competent authority in support of the critical equipment.

| Sl.No | Equipment type and characteristics | Minimum Nos. required |
| --- | --- | --- |
| 1 | Steel centring | 2000 Sqm |
| 2 | Pin vibrators | 6 Nos |
| 3 | Pan vibrators | 6 Nos |
| 4 | Concrete mixers | 5 No |
| 5 | Weigh batchers | 1 No |
| 6 | QC Lab | 1 No |

  - In case of own equipment:

1) Certificate issued by Engineer not earlier than 3 years

(OR)

2) Declaration on Rs.100/- stamp paper in prescribed format along with copies of invoices.

  - In case of lease equipment:

Lease agreement with lessor shall be furnished not earlier than one

year on Rs.100/- Non-judicial Stamp Paper.

Note:	The major equipment to attain the completion of works in accordance with the prescribed construction schedule is to be shown in the above table.

Quality Control Laboratory:

The bidder shall submit quality plan and also show proof of owning Quality Control Laboratory because this work is costing more than 2.00 crores. The following equipment is required for each work site:

    - Vernier calipers 0-150 mm: 3 Nos

    - Screw gauge 0-25 mm: 3 Nos

    - Measurement tapes both Steel (3.0 m, 5.0 m) & Fibre (15.0 m) 30 cm steel scale: 5 Nos each & 5 Nos steel scales

    - Weighing Machines 5.0 kg capacity: 3 Nos

    - Sieves for Coarse aggregate: 3 Nos

    - Sieves for fine aggregate: 3 Nos

    - Cube moulds ISI marked 150 x150 x 150 mm (6 Nos): 30 Nos

    - Compression testing machine 100 MT, hand operated /arrangement for testing at approved lab: 2 Nos

    - Slump cone: 3 Nos

    - Carpenter’s square 150 mm with graduations:6 Nos

    - Electrical Meggar 1100 V: 6 Nos

    - Spirit level: 6 Nos

    - Plum bobs: 6 Nos

    - Measuring Jars (2) 250ml: 6 Nos

    - Magnetic compass: 6 Nos

    - Weigh batching plant 30cum/hour capacity: 2 Nos

    - Non-destructive concrete strength equipment: 1 No

- Availability of the following key technical personnel with adequate experience:

(i)	Graduate Engineers (Civil) – 	            3 Nos

(ii)	Diploma Holder (Civil)         -  	2 Nos

- Graduate Engineers (Electrical) – 	2 Nos

6.	Liquid Assets/Credit facilities/Solvency Certificate from Nationalised bank /Schedule Bank in their proforma as per the guidelines of the RBI (OR) the Net worth certificate issued by the chartered accountant of value not less than Rs.4,48,85,386/- and shall not be taken earlier than one year i.e., 12.10.2025.

7.	Non refundable Processing fee of Rs. 1,18,000/-(including GST @ 18%) to be paid by way of online payment only through e-procurement platform and to upload the copy of Receipt slip.  Failure to pay the Processing fee in the aforesaid manner will entitle for rejection of the bid and debarred not to participate in APEWIDC tenders for a period of 3 Years.

8.	All the participating bidders should mandatorily pay electronically the transaction fee of Rs. 11800/- (0.03% of ECV + GST as applicable) to Managing Director, APTS, Vijayawada through “Payment Gateway” Service on e-procurement Platform” which can be done at any of the ICICI Bank or HDFC Bank. The Electronic Payment Gateway accepts all Master & Visa Cards issued by any bank and direct debit facility/Net banking of ICICI Bank/HDFC to facilitate the transaction. This is in compliance as per G.O Ms No. 13, IT&C Department Dated: 05/07/2006. (The ceiling amount of transaction fee for works costing ECV up to Rs 50.00 Crores is Rs 10,000.00 and for works costing with ECV above Rs.50.00 Crores, the ceiling amount of transaction fee is Rs 25,000.00).

9.	E.M. D of Rs. 17,95,415/- (i.e., 1% of ECV) to be paid along with the bids in the form of Online payment / Bank Guarantee as per GO MS No. 8, Dt. 08.05.2016 in favour of Managing Director, APEWIDC, Door No. 9-76, Sai Fortune Heights , Block – A, Vaddeswaram (V), Tadepally (M), Guntur District, Amaravathi

10.	GST registration certificate shall be uploaded.

11.	Copy of PAN Card to be uploaded and copy of turn over certificate issued by the CA for the Last 10 Years to be uploaded.

Copy of latest I.T returns in the form of SARAL with profit and loss balance statements to be uploaded. The applicant shall also upload SARAL with profit and loss statement for the last 3 years in addition to latest IT returns.

12.	The bidder should submit details of existing commitments of works as per the proforma available in the bid document.

The bidder should submit the particulars preferably in the formats specified in the bid document.

13.	The bidder is subjected to be black listed and the EMD forfeited if he is found to have misled or furnished false information in the forms/statements/certificates submitted in proof of qualification requirements or record of performance such as abandoning of works, non completion of works properly in time in earlier contracts, inordinate delays in completion of the works, litigation history and/or financial failures and/or participated in the previous bidding for the same work and had quoted unreasonably high bid prices.

14.	Even while execution of the work, if found that the contractor had produced false/fake certificates of experience /incomplete/part information, he will be black listed and the contract will be terminated.

15.	The bidder should submit signed undertaking of bid online.

16.	Transaction fee:

A transaction fee at 0.10% of the estimated contract value of the work towards service charges has to be paid by successful bidder at the time of concluding agreement in the form of online in favour of:

a) Managing Director, APTS, Vijayawada for Corpus Fund @ 0.04% through online payment to Managing Director, APTS, Vijayawada (Ceiling amount of transaction fee for works costing ECV up to Rs 50.00 Crores is Rs 10,000/- and for works costing with ECV above Rs 50.00 Crores, the ceiling amount of transaction fee is Rs 25,000/-).

b) Managing Director, APEWIDC, Door No. 9-76, Sai Fortune Heights, Block – A, Vaddeswaram (V), Tadepally (M), Guntur District, Amaravathi Rs. 1,27,115/- including GST @ 18%) (@ 0.06% of estimated contract value).

    - No relaxation will be given to any of the qualification criterion.

NOTE:

- Sub Contractor’s experience, in his name will be taken in to account in determining the bidder’s compliance to the qualification criterion, if it is as per G.O Ms No. 94, I&CAD (PW-COD) Department Dated: 1/07/2003.

- The certificates in support of similar works / quantities must be in State /Central Government Departments or State/Central Government undertakings only issued by the concerned Executive Engineer and countersigned by the Superintending Engineer or equivalent authority.

- The GPA holder’s is for the purpose of submitting on behalf of the Firms and  experience shall if any not be taken in to account in determining the bidder’s compliance with qualifying criterion.

# INSTRUCTIONS TO BIDDERS

A – GENERAL

# NAME OF THE WORK:	Construction of 208 Houses along with infrastructure and amenities at R.Ganapavaram Village (Colony), Buttaigudem Mandal, Eluru District for Rehabilitaton of the PDFs of Chinturu ITDA.

- Scope of work:

- Give brief description and location of work: Providing Infrastructure facilities

- List out principal components of the work: Earth Work, PCC, VRCC, Brick Masonry work, Plastering, Flooring, Joinery etc, Water Supply & Sanitary arrangements, Internal & External electrification, Roads etc.

E.C.V put to tender: Rs. 17,95,41,544/-

- Period of completion: 12 Months

- SSR adopted: Building SSR 2026-27 adopting rates of Cement and Steel – July, 2026 rates

- Rates adopted for:

(i) Cement		:	Rs. 4220 /MT

(ii) HYSD Bars Fe 500	:	Rs. 61000/MT

(iii) Mild Steel		:	Rs. 60000 /MT

- Details of provisions included in ECV put to tender:

(i) Seigniorage charges: As per Clause 100

(ii) GST: (AS APPLICABLE FROM TIME TO TIME)

(iii) Over head charges & Contractors profit: 13.615%

(iv) LA & L.I allowance: ---

- Municipal area allowance:  where ever applicable as per lead statement of sanctioned estimate.

- Reimbursable provisions:

(i) Technical personnel		: 	(Already included in the data under overheads)

(ii) Insurance premium		: 	NIL

(iii) Avagahana Sadassulu	: 	NIL

  - The Managing Director, APEWIDC, Door No. 9-76, Sai Fortune Heights , Block – A, Vaddeswaram (V), Tadepally (M), Guntur District, Amaravathi invites bids for the above works vide  NIT No: 49/MD/APEWIDC/VJA/2026-27, Dated: 12.10.2026.

  - The intending bidders would be required to enrol themselves on the e-procurement market place at www.tender.apeprocurement.gov.in .

  - The bids should be submitted in the prescribed form invited on e-procurement by the Chief Engineer that can be downloaded free of cost from the website www.tender.apeprocurement.gov.in .

  - The dates stipulated in the tender notice are firm and under any circumstances they will not be relaxed unless officially extended.

  - The bidder should upload scanned copies of registration in required class and other required documents along with his online bid. The successful bidder should produce the originals of all uploaded documents for verification if asked for by the APEWIDC

  - The bid opening authority will not consider any bid received after expiry of date and time fixed for receipt of bids.

  - Bidders shall furnish declaration that they have not been blacklisted in any department in Andhra Pradesh. Any wrong declaration in this regard which comes to notice at a later date will disqualify them and the tenders so received will be rejected.

1.7(a)	The data filled by the bidder in the online form shall be the sole criteria for the evaluation of responsiveness and assessing the bid capacity and any other supplemental data shall not be accepted by the tender accepting authorities for evaluation.

1.7(b)	The bidders are solely responsible for the correctness of the particulars furnished in online bid form.

1.7(c)	While submitting the bids, the bidder shall invariably upload legible scanned copies of certificates and documents in the e-procurement platform in support of the data furnished in online form. The bidders are advised to upload all their qualification criteria in the common folder facility available to them in the supplier registration module in e-procurement platform. The bidders shall create a tender specific folder and compulsorily upload the entire relevant documents specific to the bid by exercising selection option. The bidder shall sign on all statements, documents and certificates uploaded by him accepting responsibility for their correctness/authenticity.

1.7(d)	Apart from all the required certificates/documents, the intending bidder should scan and upload the online payment towards bid processing fee and Bank Guarantee / details of online payment towards earnest money deposit.. The Department will notify the successful (L1) bidder for submission of original hard copies of all the uploaded documents, Online payment / Bank Guarantee details towards earnest money deposit prior to entering into agreement.

1.7(e)	The Department will not hold any risk and responsibility for the loss in transit during uploading of the scanned document, for the invisibility of the scanned document online and any other problem(s) like any internet connectivity, loss of power supply etc., encountered by the bidders while submitting his bids in online.

  - The successful bidder is expected to complete the work within the time period specified in the Tender Notice.

- Firms/Contractors eligible to bid:

  - The bidders who

- Possess the valid registration in the class and category mentioned in the NIT and satisfy all the conditions therein.

- are not blacklisted or debarred or suspended by the competent authority for whatever the reason, prohibiting them not to continue in the contracting business

- Have complied with the eligibility criteria specified in the NIT are the eligible bids.

  - Bidders ineligible to bid:

- A retired officer of the Govt. of AP or Govt. of India and their under takings is not eligible for biding for a period of two years from the date of retirement without the prior permission of the Government.

- The bidder who has employed any retired officer as mentioned above shall be considered as an ineligible bidder.

- The contractor himself or any of his employees is found to be Gazetted Officer who retired from Government service and had not obtained permission from the Government for accepting the contractor’s employment within a period of 2 years from the date of his retirement.

- The Contractor or any of his employees is found at any time after award of contract, to be such a person who had not obtained the permission of the Government as aforesaid before submission of the bid or engagement in the Contractor’s service.

- Contractor shall not be eligible to bid for works in the division ,where any of his near relatives are employed in the rank of Sub Engineer or Sub Executive Engineers and above on the Engineering side and Divisional Accounts Officer and above on the administrative side. The Contractor shall intimate the names of persons who are working with him in any capacity or are subsequently employed. He shall also furnish a list of Gazetted/Non-Gazetted, State Government Employees related to him. Failure to furnish such information bidder is liable to be removed from the list of approved contractors and his contract is liable for cancellation.

Note:  Near relatives include

- Sons, step sons, daughters and stepdaughters

- Son-in-law and daughter-in-law

- Brother-in-law, and sister-in-law

- Brothers and Sisters

- Father and Mother

- Wife/Husband

- Father-in-law and Mother-in-law

- Nephews, nieces, uncle and aunts

- Cousins and

- Any person residing with or dependent on the contractor

- Qualification data of the bidders

  - The bidder shall furnish the following particulars in the formats enclosed supported by documentary evidence as specified in the prescribed formats.

- Check slip to accompany the bid (in Annexure-I)

Attested copies of documents relating to the registration of the firm, registration as Civil contractor, partnership deed, articles of association,

- Copy of PAN card and copy of latest IT returns to be submitted along with proof (SARAL form) with profit and loss statement and balance sheet for the latest assessment year.

Copy of PAN Card to be uploaded and copy of turn over certificate issued by the CA for the Last 10 years to be uploaded.

Copy of latest I.T returns in the form of SARAL with profit and loss balance statements to be uploaded. The applicant shall also upload SARAL with profit and loss statement for the last 3 years in addition to latest IT returns.

Note:	The partnership firms which are registered as contractors shall intimate the change in partnership deed if any as per G.O Ms No. 58, I&CAD Dated: 23.4.2002 within one month of such change. Failure to notify the change to the registration authority in time will entail the firms to forfeit their registration and their bid will be rejected. The intimation of change of partners if any and the acceptance by the registration authority may be enclosed.

- Value of all Civil Engineering works executed by the bidder every year during the last ten financial years (i.e., from 2016-17 to 2025-26) in statement-I

- Details of Similar nature of works of completed work (Completed building work only) in the name of the bidder as prime contractor during the last ten financial years i.e., from 2016-17 to 2025-26 showing year wise break up of value of work executed in Statement- II

- Year wise specified quantities executed by the bidder during the last ten financial years i.e., from 2016-17 to 2025-26 in Statement-III

- Details of the existing commitments i.e works on hand and works for which bids are submitted in Statement –IV only. (Self statements will not be considered)

- Availability of key & critical construction/quality control equipment in Statement-V

- Availability of key personnel for administration/site management and execution viz., technical personnel (Statement -VI)

- Information regarding any litigation with Government in which the bidder is involved in (Statement-VII)

- Liquid Assets/Credit facilities/Solvency Certificate from Nationalised bank /Schedule Bank in their proforma as per the guidelines of the RBI (OR) the Net worth certificate issued by the chartered accountant.

- The proposed methodology and program of construction backed with equipment planning and deployment duly supported with broad calculations, justifying their capability of execution and completion of the work as per technical specifications within the stipulated period of completion as per milestones.

- The particulars of quality control testing laboratory either owned OR tie up with established quality control testing laboratories for the works with estimated contract value is costing more than Rs. 200.00 Lakhs

- A self declaration by the bidder in proof of going through all bid conditions.

- Consent letters from eligible contractor’s for Public Health Engineering & Electrical works with ‘A” Grade Licence along with their registrations is required if self registration is not available.

NOTE:	The bidder shall sign all the statements/documents and certificates uploaded by him owning the responsibility for their correctness/authenticity

  - Bids from Joint Ventures are not acceptable.

  - QUALIFICATION CRITERIA FOR OPENING OF THE PRICE BID

- To qualify for opening the price bid, each bidder in his name, should have, during the last ten financial years from 2016-17 to 2025-26 (specify the financial years; those immediately preceding the financial year in which the bids are invited)

- The bidder should have satisfactorily completed Similar nature of works (building) of value not less than Rs. 8,97,70,772/- as a prime contractor in the same name and style in any one year during the financial years 2016-17 to 2025-26 updated to 2026-27 price level. GPA holder’s experience shall not be taken into account. The bidder should enclose certificate issued by the Engineer-in-Charge of the State/Central Government Departments/State Government undertakings and Central Government undertakings not below the rank of Executive Engineer or equivalent and countersigned by the Superintending Engineer or equivalent.

Note:	The cost of completed works of previous years shall be given weight age of 10% per year to bring them to current price level, (the financial year in which bids are invited).

- Executed in any one year the following minimum physical quantities.

| Sl.No | Description of item | Quantity |
| --- | --- | --- |
| 1 | Earth Work Item | 2520 Cum |
| 2 | R.R Masonry or C.R.S Masonry or Brick Masonry or RBM or combined quantity | 2217 Cum |
| 3 | PCC or VCC or RCC or VRCC or combined quantity | 2034 Cum |
| 4 | Plastering or ornamental Plastering or Impervious Coat of any thickness (Combined quantity) | 41158 Sqm |
| 5 | Shahabad/Granite/Marble/Ceramic Tiles /Polished Kadapa Slabs/Unpolished Napa Slabs Flooring, Skirting, Dadooing, Treads, Raisers or combined quantity | 237 Sqm |

- Each bidder should further demonstrate:

- Availability (either owned or leased) of the following key and critical equipment for this work: Bidder to submit a self-declaration as prescribed in Statement-V. Sufficient proof of document in support of own equipment such as invoice/ self-Certificate of regn.by competent authority in support of the critical equipment.

| Sl.No | Equipment type and characteristics | Minimum Nos. required |
| --- | --- | --- |
| 1 | Steel centring | 2000 Sqm |
| 2 | Pin vibrators | 6 Nos |
| 3 | Pan vibrators | 6 Nos |
| 4 | Concrete mixers | 5 No |
| 5 | Weigh batchers | 1 No |
| 6 | QC Lab | 1 No |

  - In case of own equipment:

1) Certificate issued by Engineer not earlier than 3 years

(OR)

2) Declaration on Rs.100/- stamp paper in prescribed format along with copies of invoices.

  - In case of lease equipment:

Lease agreement with lessor shall be furnished not earlier than one

year on Rs.100/- Non-judicial Stamp Paper.

Note:	The major equipment to attain the completion of works in accordance with the prescribed construction schedule is to be shown in the above table.

Quality Control Laboratory:

For all works costing more than Rs. 200.00 Lakhs, the bidder shall submit quality plan and also show proof of owning quality control laboratory or tie up with an established quality control testing laboratories. The following equipment is required for each work site:

    - Vernier calipers 0-150 mm: 3 Nos

    - Screw gauge 0-25 mm: 3 Nos

    - Measurement tapes both Steel (3.0 m, 5.0 m) & Fibre (15.0 m) 30 cm steel scale: 5 Nos each & 5 Nos steel scales

    - Weighing Machines 5.0 kg capacity: 3 Nos

    - Sieves for Coarse aggregate: 3 Nos

    - Sieves for fine aggregate: 3 Nos

    - Cube moulds ISI marked 150 x150 x 150 mm (6 Nos): 30 Nos

    - Compression testing machine 100 MT, hand operated /arrangement for testing at approved lab: 2 Nos

    - Slump cone: 3 Nos

    - Carpenter’s square 150 mm with graduations:6 Nos

    - Electrical Meggar 1100 V: 6 Nos

    - Spirit level: 6 Nos

    - Plum bobs: 6 Nos

    - Measuring Jars (2) 250ml: 6 Nos

    - Magnetic compass: 6 Nos

    - Weigh batching plant 30cum/hour capacity: 1 No.

    - Non-destructive concrete strength equipment: 1 No

- Availability of the key personnel

(i) Graduate Engineers (Civil) 	– 	3 Nos

(ii)  Diploma Holder (Civil)         	-  	2 Nos

(iii) Graduate Engineers (Electrical) – 	2 Nos

- Liquid assets/credit facilities/solvency certificate from any nationalised bank /scheduled bank in their proforma as per the guidelines of the RBI (OR) the net worth certificate issued by the chartered accountant value not less than Rs.4,48,85,386/- and shall not be taken earlier than one year i.e., 12.10.2025

- Non refundable Processing fee of Rs. 1,18,000/- (including GST @ 18%) to be paid by way of online payment only through e-procurement platform and to upload the copy of receipt slip. Failure to pay the Processing fee in the aforesaid manner will entitle for rejection of the bid and debarred not to participate in APEWIDC tenders for a period of 3 Years.

- All the participating bidders should pay electronically the transaction fee of              Rs. 11800/- (0.03% of ECV + GST as applicable) to Managing Director, APTS, Vijayawada  through “Payment gateway service on e-procurement platform”.

- E.M.D of Rs.17,95,415/- (i.e., 1% of ECV) to be paid along with the bids in the form of online / Bank Guarantee as per Go MS No. 8, Dt. 08.05.2016 in favour of Managing Director, APEWIDC, Door No. 9-76, Sai Fortune Heights, Block – A, Vaddeswaram (V), Tadepally (M), Guntur District, Amaravathi.

- GST registration certificate under GST  Act

- Copy of PAN card and copy of latest IT returns to be submitted along with proof (SARAL form) with profit and loss statement and balance sheet for the latest assessment year.

- Statement showing the existing commitments of works as per the proforma available in the bid document.

- Copies of registrations in Civil (Mandatory), water supply & sanitary and electrical,

- Information on litigation history in which bidder is involved if any.

- Bidder to submit a self-declaration as prescribed in Statement-V. Sufficient proof of document in support of own equipment such as invoice/ self-Certificate of regn.by competent authority in support of the critical equipment.

- In case of own equipment:

1) Certificate issued by Executive Engineer not earlier than 3 years

(OR)

2) Declaration on Rs.100/- stamp paper in prescribed format along with

copies of invoices.

- In case of lease equipment:

Lease agreement with lessor shall be furnished not earlier than one year on

Rs.100/- Non-judicial Stamp Paper.

- Signed undertaking of tender

Bid capacity

The bidder who meets the above qualification criteria and whose available bid capacity is more than the estimated contract value will be qualified for opening of price bid. The available bid capacity will be calculated as under:

Available bid capacity	: 	3AN-B > ECV

Where,

A =	Maximum value of Civil Engineering works executed in the name of bidder in any one financial year during the last ten financial years (updated to current price level) taking into account the works completed as well as works in progress.

N =	Number of years prescribed for completion of the work for which bids are invited [months / 12].

B =	Updated value (at current price level), of all existing commitments i.e., on going works, works likely to be awarded to be executed during the next 12 Months. (Period of completion of work for which bids are invited)

Annual turnover cost of completed works and balance works on hand etc., shall be updated by giving weightage of 10% per year to bring them to current price level.

Note.1:	Sub contractor’s experience, in his name will be taken in to account in determining the bidder’s compliance to the qualification criteria if it is as per G.O Ms No. 94, I & CAD (PW-COD) Department Dated: 01/07/2003.

Note 2:	(i) The certificates in support of 3.3 (A) (a), 3.3 (A) (b) & 3.3 (B) (i) in State/Central Government Departments or State/Central Government undertakings  issued by the concerned Executive Engineer and counter signed by the Superintending Engineer  or equivalent authority.

(iii) The GPA holder’s experience shall not be taken into account in determining the bidder’s compliance with qualifying criteria.

Note 3:	Annual turnover, Similar Nature of works experience and existing commitments will be updated to 2026-27 price level by giving a weightage of 10% per annum to bring them to present price level.

Note 4:	Tenders from joint ventures will not be accepted.

Note 5:	Contractors against whom vigilance/disciplinary/blacklisting cases are pending in the Corporation are not entitled to participate in the tender for the above work.

Note 6:	To quality for a contract made up of this work and other works for which bids are invited in the same Tender Notice, while evaluation for this work, the remaining works shall be taken as existing commitments and added to “B” in the formula “3AN – B” and works will be awarded based on satisfying the bid capacity.

[No relaxation will be given to any of the qualification criteria]

  - Even though the bidders meet the above qualifying criteria, they are liable to be disqualified/debarred/suspended/blacklisted if they have

i)	Furnished false/fabricated particulars in the forms, statements /incomplete information and / annexures submitted in proof of the qualification requirements

ii)	Not turned up for entering into agreement within the time specified

iii)	Record of poor progress such as abandoning the works, not properly completing the contract, inordinate delays in completion, litigation history or financial failures etc.

iv)	Participated in the previous bidding for the same work and had quoted unreasonably high bid percentage and

v)	Even while execution of the work, if found that the work was awarded to the contractor based on false/fake certificates of experience, the contractor will be blacklisted and work will be taken over invoking clause 61 of PS to APSS.

vi)	The tender of the contractor will be disqualified along with the forfeiture of E.M.D and the contractor will be debarred from future tendering for a further period of 3 years in the event of furnishing of false/fraudulent certificates along with the tender

  - Bids with an excess of above 5% of the estimated contract value will

summarily be rejected

  - Additional security Deposit:

For tenders up to 25% less than the estimated contract value of work, no additional security deposit is required. For tenders which are less by more than 25% of the estimated Contract Value of work, the difference between the tendered amount and 75% of the estimated contract value, shall be paid by the successful bidder at the time of concluding agreement as an additional security to fulfil the contract through a net banking details valid till completion of the work in all respects

  - a)	If the percentage quoted by a bidder is found to be either abnormally high or within the permissible ceiling limits prescribed but under collusion or due to unethical practices adopted at the time of bidding process, such bids shall be rejected.

b)	A bidder submitting a bid which the bid accepting authority considers excessive and or indicative of insufficient knowledge of current prices or definite attempt of profiteering will render himself liable to be debarred permanently from biding or for such period as the bid accepting authority may decide.  The bidder overall percentage should be based on the controlled prices for the materials, if any, fixed by the Government or the reasonable prices permissible for the bidder to charge a private purchaser under the provisions of clause-6 of the hoarding and profiteering prevention ordinance of 1943 as amended from time to time and on similar principle in regard to labour supervision on the construction.

  - CONDITIONAL TENDER:

Conditional tenders are not accepted. Submission of tender would be construed as acceptance to all the terms and conditions of the tender which include conditions of contract, drawings and accompanying specifications.

- One bid per bidder:

  - Each bidder shall submit only one bid for the work. A bidder who submits more than one bid will cause disqualification of all the bids submitted by the bidder.

- Cost of biding:

  - The bidder shall bear all costs associated with the preparation and submission of his bid and the bid inviting authority will in no case be responsible and liable for those costs.

- Site visit:

  - The bidder at his own cost & risk shall obtain Geotag address of this site from the bid authority and visit the site for preparing bid. The bidder shall upload the photograph / Undertaking of site visit.

- Bid Document

- Contents of bid document:

  - One set of bid document comprises of the following:

Technical bid

1)	Notice inviting tender (NIT)

2)	Instruction to bidders

- Forms of bid and qualification information

4) 	Conditions of contract

5)	Specifications

6)	Drawings

- Forms of securities i.e.  EMD, Additional security etc.

Price bid

Bill of quantities and price bid

- Clarification on bid documents:

  - A prospective bidder requiring any clarification on bid documents may contact the bid inviting officer at the address indicated in the NIT. The bid inviting officer will also respond to any request for clarification, received through post.

- Amendment to bid documents:

  - Before the last date for submission of bids, the bid inviting officer may modify any of the contents of the bid notice, bid documents by issuing amendment/addendum.

  - Any addendum/amendments issued by the bid inviting officer shall be part of the bid document and it shall either be notified in the news papers in which NIT was published or displayed in e-market place.

  - To give prospective bidders reasonable time to take an addendum into account in preparing their bids, the bid inviting officer may extend if necessary, the last date for submission of bids.

- PREPARATION OF BIDS

- Language of the bid:

  - All documents relating to the bid shall be in the English language only.

- Documents comprising of the bid:

  - The bidders who are desirous of participating in e-procurement shall submit their Technical Bids, Price Bids etc., in the standard formats prescribed in the bid documents, displayed at ‘e’ market place. The bidders should upload the scanned copies of all the relevant certificates, documents etc., in the ‘e’ market place in support of their technical bids. The bidder shall sign on all the statements, documents, certificates uploaded by him owning responsibility for their correctness/authenticity.

  - Furnishing of hard copies by the bidder before opening of the price bid is dispensed with.

  - The technical bid evaluation of the bidder will be done on the certificates/documents uploaded through online only towards qualification criteria furnished by them.

  - The bidder shall invariably upload the receipt of on line payment towards bid process fee in favour of Managing Director

  - The bidder shall mandatorily pay the transaction fee to APTS through the electronic payment gateway.

  - The successful bidder shall furnish the original hard copies of all the documents/certificates/statements uploaded by him before concluding agreement.

  - Deleted.

  - The bidder shall furnish a declaration in online stating that the soft copies uploaded by them are genuine. Any incorrectness/deviation noticed will be viewed seriously and apart from cancelling the work duly forfeiting the EMD, criminal action will be initiated including suspension of business.

  - The bidder shall authenticate the bid with his digital certificate for submitting the bid electronically on e-procurement platform and the bids not authenticated by digital certificate of the bidder will not be accepted on the e-procurement platform.

  - The technical bids will be opened on line by the Tender Committee  at the time and date as specified in the bid documents. All the statements, documents, certificates, Net banking details etc., uploaded by the bidders will be down loaded for technical evaluation. Clarifications, particulars if any required from the bidders will be obtained in the conventional method (off line) by addressing the bidders. The technical bids will be evaluated against the specified parameters/criteria same as in the case of conventional bids and the technically qualified bidders will be identified. The result of technical bid evaluation will be displayed on the e market place which can be seen by all the bidders who participated in the bids.

  - Similarly if any of the certificates, documents etc furnished by the bidder is found to be false/fabricated/bogus/incomplete/part information, the bidder will be black listed and the E.M.D will be forfeited.

Note:	As per G.O Ms No. 174, I&CAD (PW-Reforms) Department Dated: 01/09/2008, the following modifications are made:

- All the bidders shall invariably upload the scanned copies of BG / Details of Online payment in e-procurement system and this will be primary requirement to consider the bid as responsive.

- The Department shall carry out the Technical Bid Evaluation solely based on the uploaded certificates/documents,  Details of Online payment / BG towards EMD in the e-procurement system and open the price bids of responsive bidders.

- The Department will notify the successful bidder for submission of original hard copies of all uploaded documents, / Details of online payment / Bank Guarantee payment  towards Earnest Money Deposit prior to entering into agreement.

- The successful bidder shall invariably furnish the original / Details of Online payment / BG towards Earnest Money Deposit, certificates/ documents of the uploaded scanned copies to the tender inviting authority before entering into agreement either personally or through courier or post and the receipt of the same within the stipulated date shall be the responsibility of the successful bidder.

- The Department will not take any responsibility for any delay in receipt/non receipt of original / Details of online payment / BG towards earnest money deposit, certificates/Documents from the successful bidder before the stipulated time. On receipt of documents, the Department shall ensure the genuinety of the / Details of Online payment / BG towards Earnest Money Deposit and all other certificates/documents uploaded by the bidder in e-procurement system in support of the qualification criteria before concluding the agreement.

- If any successful bidder fails to submit the original hard copies of uploaded certificates/documents, / Details of online payment / BG  towards Earnest Money Deposit within the stipulated time or if any variation is noticed between the uploaded documents and the hard copies submitted by the bidder, the successful bidder will be suspended from participating in the tenders on e-procurement platform for a period of 3 years. The e-procurement system would deactivate the user ID of such defaulting successful bidder based on the trigger/recommendation by the tender inviting authority in the system. Besides this, the Department shall invoke all processes of law including criminal prosecution of such defaulting bidder as an act of extreme deterrence to avoid delays in the bidding process for execution of the development schemes taken up by the Government.

- Bid Offer:

  - Bill of quantities called Schedule-A and the bid offer accompanies the bid document as Volume-II. It shall be explicitly understood that the bid inviting officer does not accept any responsibility for the correctness or completeness of this schedule-A and this Schedule-A is liable to alterations by omissions, deductions or additions at the discretion of the Chief Engineer, APEWIDC, Vaddeswaram or as set forth in the conditions of the contract. The Schedule-A shall contain the items of work indicated as Part–I and LS provisions as Part–II. The percentage quoted by the bidder shall be applicable only to Part-I.  However, the provisions contained in the Part-II will be operable basing on the conditions provided in the bid document. The bidders will have to state clearly their willingness to execute the work at certain specific percentage of excess or less or at par of the ECV indicated in Part-I at the space provided therein in Schedule-A. The L.S amounts indicated in Part-II are maximum reimbursable amounts. The bidder should however quote his lump sum bid based on this schedule of quantities. He should quote his offer as a overall bid percentage. The over all bid percentage should be written both in words and figures.

  - The Schedule-A (or price bid) contains not only the quantities but also the rates worked out by the Department and the amount for each item and total value of the estimated contract. The bidder should workout his own rates keeping in view the work, site conditions and quote his overall bid percentage with which he intends to execute the work.

  - The bid offer shall be for the whole work and not for individual items/part of the work.

  - All duties, taxes, and other levies payable by the contractor as per State/Central Government rules excluding GST shall be included in the bid percentage quoted by the bidder.

  - The bidded contract amount as computed based on overall bid percentage is subject to variation during the performance of the contract in accordance with variation in quantities etc.

  - a) Charges payable to Managing Director, APTS, Vijayawada

All the participating bidders should mandatorily pay electronically the transaction fee of Rs.11800/- (0.03% of ECV + GST as applicable) to Managing Director, APTS, Vijayawada through “Payment Gateway Service on e-procurement Platform” which can be done at any Nationalised/Schedule Bank. (The ceiling amount of transaction fee for works costing ECV up to Rs 50.00 Crores is Rs 10,000.00 and for works costing with ECV above Rs 50.00 Crores, the ceiling amount of transaction fee is Rs 25,000.00).

b) Charges payable to Managing Director, APTS, Vijayawada

The successful bidder should pay CORPUS FUND @ 0.04% through online payment to Managing Director, A.P Technology Services, Vijayawada towards corpus fund and hand over the same to the concerned Managing Director at the time of concluding agreement. (The ceiling amount of transaction fee for works costing ECV up to Rs 50.00 Crores is Rs 10,000.00 and for works costing with ECV above Rs 50.00 Crores, the ceiling amount of transaction fee is Rs 25,000.00). The Managing Director, APEWIDC will send the said demand draft to the Managing Director, A.P Technology Services, Vijayawada.

c) Service charges payable to Managing Director, APEWIDC, Door No. 9-76, Sai Fortune Heights , Block – A, Vaddeswaram (V), Tadepally (M), Guntur District, Amaravathi: The successful bidder should pay transaction fee of Rs.1,27,115/- at (0.06% on ECV+ GST @ 18%) of the estimated contract value of the work towards service charges to be paid by way of Crossed Demand Draft at the time of concluding agreement.

- Validity of bids:

  - Bids shall remain valid for a period of 3 (Three) months from the last date for receipt of technical bids as specified in NIT.

  - During the above mentioned period no plea by the bidder for any sort of modification of the bid based upon or arising out of any alleged misunderstanding of misconceptions or mistake or for any reason will be entertained.

  - In exceptional circumstances, prior to expiry of the original time limit, the bid inviting officer may request the bidders to extend the period of validity for a specified additional period. Such request to the bidders shall be made in writing. A bidder may refuse the request without forfeiting his E.M.D. A bidder agreeing to the request will not be permitted to modify his bid, but will be required to extend the validity of his E.M.D for a period of the extension.

- Earnest money deposit:

  - All the intending bidders shall furnish the E.M.D equivalent to 1% of ECV to be paid along with the bids in the form of either Online Payment / BG as per GO MS No. 8 Dt. 08.05.2016 in favour of Managing Director, APEWIDC, Door No. 9-76, Sai Fortune Heights , Block – A, Vaddeswaram (V), Tadepally (M), Guntur District, Amaravathi. This will be the primary requirement to consider the bid as responsive. Original bank slips is to be scanned and uploaded along with the bid. Only successful bidder notified by the Department has to submit the original bank slips BG to the Managing Director through registered post/courier/in person so as to reach before the date specified in the intimation notice for concluding agreement. The Department will not take any responsibility for any delay in receipt/non receipt of original Online payment details towards Earnest Money Deposit. Failure to furnish the original Bank Guarantee / Online payment details within the stipulated date & time, the bidder will be suspended from participating in tenders on e-procurement platform for a period of 3 years including criminal prosecution as per G.O Ms No.174, Irrigation & CAD (PW-Reforms) Department Dated: 1/09/2008. The suspension of bidder shall be automatically enforced by the e-procurement system.

The balance EMD @ 1½% of ECV/TCV whichever is higher shall be paid at the time of concluding agreement by the successful bidder.  This EMD can be in the form of: Online payment / BG details from any Nationalised/Schedule Bank.

  - BG towards 1% EMD shall be valid for a period of 6 (Six) months from the date of bid notice.

  - Deleted

  - Successful bidder has to submit the original online payment details / BG to the Managing Director through registered post/courier/in person so as to reach before the date specified in the intimation notice. However, this 1% E.M.D paid by the successful bidder along with submission of bid, will be discharged only after signing the agreement if the bidder furnishes bank guarantee for the full EMD of 2½% of tender contract value/estimated contract value whichever is higher at the time of concluding agreement. For tenders which are less by more than 25% of the estimated contract value of work, the difference between the tendered amount and 75% of the estimated contract value, shall be paid by the successful bidder at the time of concluding agreement as an additional security to fulfil the contract through a Online payment / BG till completion of the work in all respects.

  - The earnest money deposited by the successful bidder will not carry any interest and it will be dealt with as provided in the conditions stipulated in the tender. The E.M.D given in the form of online payment / Bank Guarantee on a nationalised /scheduled bank, shall be valid for the duration of contract period plus defect liability period of two years and in case any valid extension of contract period is granted, the validity of Bank Guarantee shall also be extended for the corresponding period. The Bank Guarantee on nationalised/scheduled bank furnished by the bidder towards additional security amount shall be valid till the work is completed in all respects.

  - The E.M.D. shall be forfeited

- if the bidder withdraws the bid during the validity period of bid.

- in the case of a successful bidder, if he fails to sign the agreement for whatever the reason.

  - In consideration of the Executive Engineer/Managing Director /Chief Engineer /Tender Committee of this Corporation undertaking to investigate and to take into account each tender and in consideration of the work thereby involved, all earnest monies deposited by the bidder will be forfeited to the Government in the event of such bidder either modifying or withdrawing his bid at his instance within the said validity period of 3 (Three) months.

  - If any successful bidder fails to submit the original hard copies of Online payment / BG details towards earnest money deposit with in the stipulated time or if any variation is noticed between the uploaded Net banking payment and the hard copies submitted by the bidder, the successful bidder will be suspended from participating in the tenders on e-procurement platform for a period of 3 years.  The e-procurement system would deactivate the ID of such defaulting successful bidder based on the trigger/recommendation by the tender inviting authority in the system. Besides this, the Department shall invoke all processes of law including criminal prosecution of such defaulting bidder as on act of extreme deterrence to avoid delays in the tender process for execution of the development schemes taken up by the Government.

- Signing of bids:

  - If the bid is made by an individual, it shall be signed with his full name and his address shall be given. If it is made by a firm or by Power of Attorney who shall also sign his own name, and the name and address of each member of the firm shall be given, if the bid is made by a corporation it shall be signed by a duly authorised officer who shall produce with his bid, satisfactory evidence of his authorisation. Such bidding corporation may be required before the contract is executed, to furnish evidence of its corporate existence. Bids signed on behalf of G.P.A. holder will be rejected.

NOTE: In all cases, the bid must be digitally signed

  - The bid shall contain no alterations or additions except those to comply with instructions issued by the bid inviting officer or as necessary to correct errors made by the bidder in which case all such corrections shall be initialled by the person signing the bid.

  - No alteration which is made by the bidder in the contract form, the conditions of the contract, the drawings, specifications or statements/formats or quantities accompanying the same will be recognised and if any such alterations are made the bid will be void.

D.	SUBMISSION OF BIDS

- Submission of bids

  - All the intending bidders who are desirous of participating in e-procurement shall submit their technical bids & price bids etc., in the Standard formats prescribed in the on line bids submission displayed at e-market place/e-procurement. The bidders should upload the scanned copies in support of their Technical bids. The documents are to be uploaded in ZIP format only. The bidders shall sign on all the statements, documents, certificates uploaded by him owning responsibility for their correctness/authenticity.

  - The documents uploaded online will only be considered for evaluation. After uploading the technical/price bid. If any of the certificates, documents, etc., furnished by the bidder is found at a later date to be false /fabricated /bogus /Incomplete information the bidder will be blacklisted and the EMD forfeited. If the successful bidder fails to submit the original hard copy of Online Payment / BG towards EMD which is scanned and uploaded along with the bid before the specified time in the intimation notice in online/off-line, the bidder will be suspended /disqualified from participating in the tenders on e-Procurement platform for a period of 3 (Three) years from the date of bid submission. The suspension of such bidder shall be automatically enforced by the e-Procurement system.

  - The Corporation will not hold any risk and responsibility for the loss in transit during uploading of the scanned document for the invisibility of the scanned document online and any other problem(s) like any internet connectivity, loss of power supply etc., encountered by the bidder while submitting his bid online.

  - Related certificates, documents etc., duly self attested are to be scanned and uploaded on to the e-procurement platform at www.tender.apeprocurement.gov.in.

  - The bidder shall mandatorily pay the transaction fee to APTS through the electronic payment gateway.

  - The following certificates, documents etc., to substantiate the figures indicated against criteria in online bid form shall be scanned and uploaded on to the e-procurement platform at www.eprocurement.gov.in The bidder shall invariably ensure that the following are uploaded online:

- Check slip

- Copy of contractors Registration Certificate under appropriate Class with Government of Andhra Pradesh

- Copy of PAN card and copy of latest IT returns to be submitted along with proof (SARAL form) with profit and loss statement and balance sheet for the latest assessment year.

Copy of latest I.T returns in the form of SARAL with profit and loss balance statements to be uploaded. The applicant shall also upload SARAL with profit and loss statement for the last 3 years in addition to latest IT returns.

- Copy of GST registration certificate under GST Act 2017 and latest GST clearance certificate. (to be furnished by successful bidder to the Managing Director , APEWIDC at the time of concluding Agreement)

- Particulars of value of Civil Engineering works executed in the name of bidder in the last ten financial years in Statement-I along with work done certificates in support of the figures.

- Details of similar works executed as Prime Contractor (in the same name) during the last ten financial years showing year wise break up of value of work executed in Statement-II duly supported with work done certificates, work wise and year wise.

- Physical quantities of specified works executed as Prime Contractor (in the same name) in the last ten financial years with year wise break up work wise in Statement- III duly supported with work done certificates.

- Information on ‘existing commitments’ with supporting certificates in Statement-IV.

- Availability of Key & critical equipment in Statement- V: Bidder to submit a self-declaration as prescribed in Statement-V. Sufficient proof of document in support of own equipment such as invoice/ self-Certificate of regn.by competent authority in support of the critical equipment.

  - In case of own equipment: 1) Certificate issued by Executive Engineer not earlier than 3 years

(OR)

2) Declaration on Rs.100/- stamp paper in prescribed format along with

copies of invoices.

  - In case of lease equipment: Lease agreement with lessor shall be furnished not earlier than one year on Rs.100/- Non-judicial Stamp Paper.

- Availability of Key personnel in Statement -VI.

- Information on litigation history in Statement- VII.

- Proof of Liquid assets/credit facilities/solvency certificate from any ationalised/scheduled bank in their proforma as per the guidelines of the RBI (OR) the net worth certificate issued by the chartered accountant not less than one year.

- Proposed methodology and program of construction, backed with equipment planning and deployment, duly supported with broad calculations, justifying their capability of execution and completion of the work as per technical specifications within the stipulated period of completion as per milestones.

- Particulars of quality control testing Lab owned OR tie up with established quality control testing laboratories along with required equipments as per statement-VIII.

- Self declaration by the bidder in proof of going through all bid conditions (see format below check list)

- Online payment / BG valid for 6 months  towards Earnest Money Deposit

- Transaction fee through electronic payment gateway.

- Non refundable bid processing fee in shape of Online payment in favour of concerned Managing Director

  - Important Note:

The bidder shall authenticate the bid with his digital certificate for submitting the bid electronically on e-procurement Platform and the bids not authenticated by Digital certificate of the bidder will not be accepted on the e-procurement platform.

- Deleted

- Last date/time for submission of the bids:

  - Bids must be submitted not later than the date and time specified in NIT. In the event of the specified date/time for the submission of bids declared as holiday, the bids will be received on the next working day up to the time specified only after issue of corrigendum.

  - The APEWIDC may extend the dates for issue and receipt of bids by issuing an amendment in which case all rights and obligations of APEWIDC and the bidders will remain same as previously.

- Late bids:

  - E-procurement platform will not receive any bids after the last date/time prescribed in NIT/bid document.

- Modification to the bid

  - No bid shall be modified after the last date /time of submission of bids.

# BID OPENING AND EVALUATION

- Bid opening

  - The technical bids will be opened online by the Tender Committee  at the time and date as specified in the Notice Inviting Tender. All the statements, documents, certificates, BG / online Payment details etc., uploaded by the bidders will be downloaded for technical evaluation. The technical bids will be evaluated against the specified parameters/criteria same as in the case of conventional bids and the technically qualified bidders will be identified. The result of technical bids evaluation will be displayed on the e-market place, which can be seen by all the bidders who participated in the bids.

- Clarification on the technical bid

  - The tender opening authority may call up on any bidder for clarification on the statements, documentary proof relating to the technical bid. The request for clarification and response thereto shall be in writing and it shall be only on the qualification information furnished by the bidder. The clarification called for from the bidder shall be furnished within the stipulated time, which shall not be more than a week.

  - The bidder if so desirous, shall agree in writing to furnish the clarification called for within the stipulated time and, for disqualification and rejection of his bid in the event of failure to do so.

- Examination of technical bids and determination of responsiveness

  - The APEWIDC  will evaluate whether each bidder is satisfying the eligibility criteria prescribed in the tender document and declares them as a qualified bidder.

  - If the technical bid of a bidder is not satisfying any of the eligibility criteria it will be rejected by the APEWIDC . However, if the bid accepting authority / Tender Committee detects any error in the evaluation of bids, the bid accepting authority / Tender Committee while returning the bids may direct the APEWIDC / Tender Committee as the case may be, to re-evaluate the bids.

  - If any alteration is made by the bidder in the bid documents, the conditions of the contract, the drawings, specifications or statements/formats or quantities, the bid will be rejected.

- Price bid opening

  - Only the price bids of qualified bidders whose technical bids are found satisfying the eligibility criteria shall be opened on line.

  - The price bid of the bidders whose technical bids are not satisfying eligibility criteria, will not be opened.

  - Bids shall be scrutinised in accordance with the conditions stipulated in the bid document. In case of any discrepancy of non-adherence conditions, the bid accepting authority shall communicate the same which will be binding both on the bid opening authority and the bidder. In case of any ambiguity, the decision taken by the bid accepting authority on bids shall be final.

- Evaluation and comparison of price bids:

  - The Tender Committee will evaluate and compare the price bids of all the qualified bidders.

  - Negotiations at any level are strictly prohibited.  However, as a good gesture rebate, if offered by the lowest bidder prior to finalisation of bids may be accepted by the bid accepting authority.

  - Selection of bidder among the lowest & equally quoted bidders will be in the following orders:

- The bidder whose bid capacity is higher will be selected.

- In case the bid capacity is also same, the bidder whose annual turnover is more will be preferred.

- Even if the criteria incidentally become the same, the turnover on similar works and thereafter machinery available for the work and then the clean track record will be considered for selection.

- Discrepancy in bid percentage quoted:

  - Deleted

- Process to be confidential

  - Information relating to the examination, clarification, evaluation and comparison of bids and recommendations for the award of a contract shall not be disclosed to bidders or any other persons not officially concerned with such process until the award to the successful bidder has been announced by the bid accepting authority. Any effort by a bidder to influence the processing of bids or award decisions may result in the rejection of his bid.

  - No bidder shall contact the Chief Engineer /Managing Director or any authority concerned with finalisation of bids on any matter relating to its bid from the time of the bid opening to the time the contract is awarded.

  - Before recommending /accepting the bid, the bid recommending/accepting authority shall verify the correctness of certificates submitted to meet the eligibility criteria and specifically experience. The authenticated agreements of previous works executed by the lowest bidder shall be called for.

  - The Tender Committee shall scrutinize the bids submitted by the APEWIDC in accordance with the conditions stipulated in the bid document and in case any discrepancy of non-adherence to the conditions, the same shall be communicated which will be binding both on the bid concluding authority and bidder. In case of any ambiguity the decision taken by the Tender Committee on bids shall be final.

# F.	AWARD OF CONTRACT

- Award criteria:

  - The  Tender Committee will award or recommend to the competent bid accepting authority for award of the contract to the bidder who is found technically qualified as per the bid conditions and whose price bid is lowest.

  - The bid accepting authority reserves the right to accept or reject any bid or all bids and to cancel the biding process, at any time prior to the award of contract, without thereby incurring any liability to the affected bidder or bidders or any obligation to inform the affected bidder or bidders of the reasons for such action.

- Notification of award and signing of agreement:

  - The bidder whose bid has been accepted will be notified of the award of the work by the Managing Director  prior to expiration of the bid validity period by registered letter/e-mail in online/Fax. This letter (hereinafter and in the conditions of contract called “Letter of acceptance”) will indicate the sum that the Government will pay the contractor in consideration of the execution, completion, and maintenance of the works by the contractor as prescribed by the contract (hereinafter and in the contract called the “Contract amount”).

  - When a bid is accepted the concerned bidder shall attend the office of the Managing Director  on the date fixed in the letter of acceptance. Upon intimation being given by the Managing Director of acceptance of his bid, the bidder shall make payment of the balance E.M.D and additional security deposit wherever needed by way of Bank Guarantee or Online payment from a Nationalised Bank/Schedule Bank with a validity period of duration of Contract period of 12 Months plus defects liability period of 2 years (i.e., Total 36 months) along with required documents notified in the intimation notice and sign an agreement in the form prescribed by the Department for the due fulfilment of the contract. Failure to attend the Managing Director’s office on the date fixed in the written intimation to enter into the required agreement shall entail forfeiture of the earnest money deposited. The written agreement to be entered into between the contractor and the Corporation shall be the foundation of the rights and obligations of both the parties and the contract shall not be deemed to be completed until the agreement has first been signed by the contractor and then by the proper officer authorised to enter into contract on behalf of the Corporation.

  - The successful bidder has to sign an agreement within a period of 15 days from the date of receipt of communication of acceptance of his bid by registered letter/e-mail in online/Fax. On failure to do so his bid will be cancelled duly forfeiting the E.M.D paid by him without issuing any further notice and action will be initiated for black listing the bidder.

  - The successful bidders who back out from entering into agreement at the last minute, causing loss to the Government will be debarred for one year from participating in the tendering process of any department of the Government besides forfeiture of the 1% EMD.

  - In case a successful bidder of a single bid received backs out from entering into agreement, the EMD will be forfeited but the period debarring him from participating in the tendering process of any department of the Government will be restricted to six months only.

- Corrupt or fraudulent practices:

  - The Corporation require that the bidders/suppliers/contractors under Government financed contracts, observe the highest standard of ethics during the procurement and execution of such contracts.  In pursuance of this policy, the Government

- define for the purposes of the provision, the terms set forth below as follows:

- “corrupt practices” means the offering, giving, receiving or soliciting of any thing of value to influence the action of a Government official in procurement process or in contract execution: and

- “fraudulent practice” means a misrepresentation of facts in order to influence a procurement process or the execution of a contract to the detriment of the Government and includes collusive practice among bidders (prior to or after bid submission) designed to establish in bid prices at artificial non-competitive levels and to deprive the Government of the benefits of free and open competition.

- Will reject a proposal for award if it determines that the bidder recommended for award has engaged in corrupt or fraudulent practices in competing for the contract in question.

- Will blacklist/or debar  a firm, either indefinitely or for a stated period of time, if at any time determines that the firm has engaged in corrupt or fraudulent practices in competing for, or in executing a Government contract.

- Furthermore, bidders shall be aware of the provisions stated in the general conditions of contract.

- Right of the Corporation:

  - The Managing Director/ reserves the right to reject any or all of the tenders, without assigning any reason whatsoever.

  - In the event of any dispute regarding any of the tender conditions, the decision of the Managing Director shall be final

  - During the execution the work, Engineer-in-charge/ Chief Engineer of the work reserves the right for their selves to withdraw any of the items/work to be executed or add from the scope of work.

FORMS OF BID

QUALIFICATION INFORMATION

AND

## UNDER TAKING OF BIDDER

QUALIFICATION INFORMATION

## Annexure –I

###### CHECKLIST TO ACOMPANY THE BID

Documents to be submitted by bidder on the e-procurement platform on line

| Sl. No | Document to be uploaded to profile | Description to be given | Scanned documents to be uploaded | Page No. (see Note below) |
| --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 |
| 1 | Contractors valid registration under appropriate class and category with Government of Andhra Pradesh (for Civil, PH and Electrical categories) (b) Partnership deed in case of firms & article of association in case of companies | Civil Registration | Yes / No |  |
| 2 | Consent letters from eligible register contractor’s for Public Health Engineering & Electrical works with ‘A” Grade Licence along with their registrations is required if self-registration is not available. | PH & Electrical Registrations | Yes / No |  |
| 3 | Copy of PAN Card to be uploaded. Copy of turn over certificate issued by the CA for the Last 10 years to be uploaded. Copy of latest I.T returns in the form of SARAL with profit and loss balance statements to be uploaded. The applicant shall also upload SARAL with profit and loss statement for the last 3 years in addition to latest IT returns | Income Tax Documents | Yes / No |  |
| 4 | Copy of GST registration | GST Document | Yes / No |  |
| 5 | Scanned copy of EMD Paid by way of Online / BG as per GO MS No. 8 dt. 08.05.2016 to the Account of Managing Director, APEIWDC, Vijayawada, (S.B. A/c No.052310100081066 having in Union Bank of India, Suryaraopeta, Vijayawada. IFSC Code:- UBIN0805238. and copy of Bank slip should be scanned will be attached to Uploaded documents. | EMD | Yes / No |  |
| 6 | Scanned copy of Bid processing fee by way Online payment | Bid processing Fee | Yes / No |  |
| 7 | Scanned Copy of Transaction fee through electronic gateway payment | Transaction Fee | Yes / No |  |
| 8 | Liquid assets/credit facilities/solvency certificate from any nationalised/ scheduled bank in their proforma as per the guidelines of the RBI (OR) the net worth certificate issued by the chartered accountant. | Credit facilities | Yes / No |  |
| 9 | Details of Civil Engineering works executed in the last 10 financial years any one financial year in Statement-I in the bidder’s name with supporting certificates duly issued by the EEs and countersigned by the SE/Higher authorities. (OR) Annual turnover certificate certified by CA along with profit and balance sheet issued by the Executive authority and duly signed by competent authority for works executed in any one financial year during the preceding 10 years | Annual Turnover | Yes / No |  |
| 10 | Details of Similar nature of works completed as prime contractor (in the same name) during the last 10 financial Years for any one financial year in Statement-II with supporting certificates duly issued by the EEs and countersigned by the SE/Higher authorities. | Similar Works | Yes / No |  |
| 11 | Quantities of works executed as prime contractor (in the same name) in the last 10 financial years for any one financial year in Statement-III with supporting certificates duly issued by the EEs and countersigned by the SE/Higher authorities. | Executed Quantities | Yes / No |  |
| 12 | Statement of existing commitments in ongoing Govt. works along with supporting experience certificates as in Statement- IVA Note: Information about B value of the Bidders available through online will be considered for evaluation purpose. | Existing commitments | Yes / No |  |
| 13 | Statement of works for which tenders are submitted and likely to be awarded as in Statement IV-B | Works awarded/likely to be awarded | Yes / No |  |
| 14 | Bidder to submit a self-declaration as prescribed in Statement-V. Sufficient proof of document in support of own equipment such as invoice/ self-Certificate of regn.by competent authority in support of the critical equipment. - In case of own equipment: 1) Certificate issued by Executive Engineer not earlier than 3 years (OR) 2) Declaration on Rs.100/- stamp paper in prescribed format along with copies of invoices. - In case of lease equipment: Lease agreement with lessor shall be furnished not earlier than one year on Rs.100/- Non-judicial Stamp Paper. | Critical Equipment | Yes / No |  |
| 15 | Availability of key personnel in Statement-VI along with qualification certificates and willingness letters. | Technical Agents | Yes / No |  |
| 16 | Information on litigation history as in Statement VII | Litigation history | Yes / No |  |
| 17 | Proof of owning quality control laboratory or Tie up with an established quality control testing laboratory along with the required equipment as specified in bid document for the works with ECV more than Rs. 200.00 Lakhs | QC Lab | Yes / No |  |
| 18 | Declaration on quality control laboratory along with required equipment on non-judicial stamp paper worth of Rs. 100/- as per Statement-VIII | Declaration on QC Lab | Yes / No |  |
| 19 | Self-declaration by the bidder in proof of going through all bid conditions (see format below check list) | Declaration | Yes / No |  |
| 20 | Declaration in online stating that the soft copies uploaded by them are genuine | Undertaking | Yes / No |  |
| 21 | The bidder at his own cost & risk shall obtain Geotag address of this site from the bid authority and visit the site for preparing bid. The bidder shall upload the photograph / Undertaking of site visit. | site visit (Optional) | Yes/No |  |
| 22 | Shall be uploaded any other document required as per bid document. | Optional | Yes/No |  |

Note:-

      - Documents may be uploaded in ZIP format with suitable description as defined above.

      - The scanned documents shall be legible failing which they will not be considered.

      - Shall sign on all statements, documents, certificates uploaded owning responsibility for their correctness/authenticity.

      - All experience certificates including those in support of existing commitments issued by an Officer not below the rank of Executive Engineer and should be countersigned by the Superintending Engineer or equivalent authority.

      - The E.M.D should be in shape of Online payment / BG adhered to as per bid conditions. Any deviation will result in making the bid non-responsive. Further all other BG / Online payment to be submitted at the time of agreement and for advance payment should also be in the formats prescribed in the bid document.

      - All the statements, copies of the certificates, documents etc., enclosed to the technical bid shall be signed by the bidder and given page numbers on the right corner of each certificate, which will be indicated in column (5) against each item. The statements furnished shall be in the prescribed formats appended to the bid document.

      - The information shall be filled-in by the bidder in the checklist and statements-I to VIII and shall be enclosed to the technical bid for the purposes of verification as well as evaluation of the bidder’s compliance to the qualification criteria as provided in the bid document. All the certificates, documents, statements as per check-list shall be submitted by the bidder.

### DECLARATION

I/We ……………………………………………………………… have gone through carefully all the bid conditions and solemnly declare that I/We will abide by any penal action such as disqualification or black listing or determination of contract or any other action deemed fit, taken by the Department against me/us if it is found that the statements, documents, certificates produced by me/us are false/fabricated.

I/We hereby declare that, I/We have not been blacklisted/debarred/suspended/demoted in any department in Andhra Pradesh or in any State due to any reasons.

Signature of the bidder

STATEMENT – I

Details of value of Civil Engineering works executed in each year during the last ten financial years by the bidder:

| Sl. No | Financial Year | Value in Rs. |
| --- | --- | --- |
| 1. 2. 3. 4. 5. 6. 7. 8. 9. 10. | 2016-17 2017-18 2018-19 2019-20 2020-21 2021-22 2022-23 2023-24 2024-25 2025-26 |  |

Attach certificate(s) issued by the Executive Engineer/Equivalent officer concerned and counter signed by Superintending Engineer / Equivalent officer showing work wise/year wise value of work done in respect of all the works executed by the bidder during last ten years.

(Or)

Certificate from Chattered Accountants supported with annual balance sheet tallying with IT Certificates.

Signature of the bidder

STATEMENT – II

Details of similar works completed in the name of the bidder during the last ten financial years:

| Sl. No | Name of the work | Address of Agt. concluding authority | Agreement No. & date | Value of contract |
| --- | --- | --- | --- | --- |
| 1 1 | 2 | 3 | 4 | 5 |

| Stipulated period of completion | Actual date of completion | Value of work done year wise during the last ‘ten’ years |  |  |  |  | Total value of work done |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1st Year | xxxx | xxxx | xxx | 10th Year |  |
| 6 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 |

Attach certificates issued by the Executive Engineer/Equivalent officer concerned and countersigned by Superintending Engineer / Equivalent officer showing work wise/year wise value of work done in respect of all the works executed by the bidder during the last ten years.

Signature of the bidder

STATEMENT – III

Physical quantities executed by the bidder in the last ten financial years [work wise/year wise]:

| Sl No | Financial Year | Name of the work | Agt.No | Quantities executed / Year wise. |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | EWE | PCC/ RCC/ VRCC | Stone /RBM/ Brick masonry | Plastering Items of any thickness | Flooring Items |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| 1 | 2016-17 |  |  |  |  |  |  |  |
| 2 | 2017-18 |  |  |  |  |  |  |  |
| 3 | 2018-19 |  |  |  |  |  |  |  |
| 4 | 2019-20 |  |  |  |  |  |  |  |
| 5 | 2020-21 |  |  |  |  |  |  |  |
| 6 | 2021-22 |  |  |  |  |  |  |  |
| 7 | 2022-23 |  |  |  |  |  |  |  |
| 8 | 2023-24 |  |  |  |  |  |  |  |
| 9 | 2024-25 |  |  |  |  |  |  |  |
| 10 | 2025-26 |  |  |  |  |  |  |  |

Attach certificates in support of above quantities issued by the Executive Engineer/Equivalent officer concerned and counter signed by Superintending Engineer /Equivalent officer duly showing the quantities executed year wise during last ten years.

Signature of the bidder

STATEMENT – IV

Details of existing commitments

Details of works on hand and, yet to be completed as on the date of submission of the bid and works for which bids have been submitted are to be furnished.

- Existing commitments on ongoing works:

| Sl.No | Name of work | Address of Agt. conclu-ding authority | Agt. No. & Date | Value of cont-ract | Stipul-ated period of comp-letion | Value of work done so far | Balance Value of works to be comple-ted | Antici-pated date of comp-letion | Updated value of balance work |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |

Attach certificates issued by the Executive Engineer/equivalent officer concerned and countersigned by Superintending Engineer /equivalent officer indicating the balance work to be done and likely period of completion.

Signature of the bidder

STATEMENT – IV

- Details of works for which bids are submitted [awarded/likely to be awarded]:

| Sl. No | Name of work | Address of Agt. concluding authority | Estimated value of work | Stipulated period of completion | Date on which bid was submitted | Present stage of bid |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |

Note: Value of the works available through online will be taken in to account for evaluation

purpose.

Signature of the bidder

STATEMENT - V

Availability of critical equipment:

The bidder should furnish the information required below, regarding the availability of the equipment, required for construction/quality control.

| Sl.No | Details of equipment | Number required | Number |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Owned | Leased | To be procured |
| 1 | 2 | 3 | 4 | 5 | 6 |
| 1 | Steel centring | 2000 Sqm |  |  |  |
| 2 | Pin vibrators | 6 Nos |  |  |  |
| 3 | Pan vibrators | 6 Nos |  |  |  |
| 4 | Concrete mixers | 5 No |  |  |  |
| 5 | Weigh batchers | 1 No |  |  |  |
| 6 | QC Lab | 1 No |  |  |  |
| 8. | Vibratory Roller |  |  |  |  |

Signature of the bidder

- In case of own equipment: - the bidder has to submit either a certificate issued by the Executive Engineer not earlier than 3 years

(OR)

A declaration regarding the equipment owned shall be produced by the bidder on a non-judicial stamp paper of Rs. 100/- as prescribed below with sufficient proof of documents in support of owing such as invoice/ Certificate of Registration by competent authority in support of critical equipment, as below.

DECLARATION

I ……………………………………. do hereby solemnly affirm and declare that I/we own the following equipment for using on the subject work and also declare that I/We will abide by any action such as disqualification or determination of Contract or blacklisting or any action deemed fit, if the department detects at any stage that I/we do not possess the equipment listed below.

| Sl. No | Details of each equipment | Year of purchase | Regn. Number | Capacity | Any other data | Is it in working condition |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |

Signature of the bidder

- In case of Lease equipment: - The bidder has to furnish a lease agreement not earlier than one year.

STATEMENT – VI

Availability of key personnel:

Qualification and experience of key personnel proposed to be deployed for execution of the contract:

| Sl. No | Name | Designation | Qualification | Total experience | Working with the bidder since |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 |

Note: a) Attach qualification certificates and willingness letters of the technical personnel,

b) if the bidder / partner are technically qualified as required, they have to furnish a

declaration to that effect along with their qualification certificates.

Signature of the bidder

STATEMENT – VII

Information on litigation history in which bidder is the petitioner:

| Sl. No | Case No/Year | Court where filed | Subject matter/prayer in the case | Répondent i.e., SE/CE | Present stage |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 |

Signature of the bidder

STATEMENT - VIII

(IN CASE OF WORKS COSTING MORE THAN RS.2.00 CRORES)

DECLARATION

“I/We ……………………………………. do hereby solemnly affirm and declare that I /we own /tie up the following equipment for using on the subject work at each and every work site and also declare that I / We will abide by any action such as disqualification or determination of Contract or blacklisting or any action deemed fit, if the department detects at any stage that I/we do not possess the equipment listed below at each and every work site.

| Sl. No | Details of each equipment | Equipment required for each work site. | Own | Tie up |
| --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 |
| 1 | Vernier Calipers 0-150 mm | 3 Nos |  |  |
| 2 | Screw gauge 0-25 mm | 3 Nos |  |  |
| 3.a 3.b | Measurement tapes both Steel (3.0 m, 5.0 m) & Fibre (15.0 m) 30 cm steel scale | 5 Nos 5 Nos |  |  |
| 4 | Weighing Machines 5.0 kg capacity | 3 Nos |  |  |
| 5 | Sieves for Coarse aggregate | 3 Nos |  |  |
| 6 | Sieves for fine aggregate | 3 Nos |  |  |
| 7 | Cube moulds ISI marked 150 x150 x 150 mm (6 nos.) | 30 Nos |  |  |
| 8 | Compression testing machine 100 MT, hand operated /arrangement for testing at approved lab. | 2 Nos |  |  |
| 9 | Slump cone | 3 Nos |  |  |
| 10 | Carpenter’s square 150 mm with graduations | 6 Nos |  |  |
| 11 | Electrical Meggar 1100 V | 6 Nos |  |  |
| 12 | Spirit level | 6 Nos |  |  |
| 13 | Plum bobs | 6 Nos |  |  |
| 14 | Measuring Jars (2) 250ml | 6 Nos |  |  |
| 15 | Magnetic compass | 6 Nos |  |  |
| 16 | Weigh batching plant 30cum/hour capacity | 1 No. |  |  |
| 17 | Non-destructive concrete strength equipment | 1 No |  |  |

Note: Shall upload the Declaration on quality control laboratory along with required equipment on non-judicial stamp paper worth of Rs. 100/-

UNDERTAKING OF BIDDER

Date: ……………

To:

The Managing Director ,

APEWIDC, Vijayawada

Sir,

I/We do hereby bid and if this bid be accepted, I/We undertake to execute the following work viz.,  Construction of 208 Houses along with infrastructure and amenities at R.Ganapavaram Village (Colony), Buttaigudem Mandal, Eluru District for Rehabilitaton of the PDFs of Chinturu ITDA. as shown in the drawings and described in the specifications available in online and also in the office of The Managing Director, APEWIDC, Door No. 9-76, Sai Fortune Heights , Block – A, Vaddeswaram (V), Tadepally (M), Guntur District, Amaravathi  with such  variations by way of alterations or additions to, and omissions from the said works and method of payment as provided for in the “conditions of the contract” for the sum of Rs. 17,95,41,544/- (Rupees Seventeen Crores Ninety Five Lakhs Forty One Thousand Five Hundred Forty Four Only) or such other sum as may be arrived under the clause of the standard preliminary specifications relating to “payment on lump-sum basis or by final measurement at unit rates”

I/We have also quoted percentage excess or less on E.C.V., in Schedule-A Part-I

annexed (in words and figures) for which I/We agree to execute the work when the lump sum payment under the terms of the agreement is varied by payment on measurement quantities.

I/We have quoted Percentage excess or less on E.C.V., in Schedule-A Part-I in figures in online shall only prevail.

I/We agreed to keep the offer in this bid valid a period of three months mentioned in the bid notice and not to modify the whole or any part of it for any reason within above period.  If the bid is withdrawn by me/us for any reasons whatsoever, the earnest money paid by me/us will be forfeited to Corporation.

I/We hereby distinctly and expressly, declare and acknowledge that, before the submission of my/our bid I/We have carefully followed the instructions in the bid notice and have read the A.P.S.S. and the preliminary specifications therein and the A.P.S.S. addenda volume and that I/We have made such examination of the contract documents and the plans, specifications and quantities and of the location where the said work is to be done, and such investigation of the work required to be done, and in regard to the material required to be furnished as to enable me/us to thoroughly understand the intention of same and the requirements, covenants, agreements, stipulations and restrictions contained in the contract, and in the said plans and specifications and distinctly agree that I/We will not hereafter make any claim or demand upon the Government based upon or arising out of any alleged misunderstanding or misconception/or mistake on my/or our part of the said requirement, covenants, agreements, stipulations, restrictions and conditions.

I/We enclosed to my/our bid a crossed Bank Guarantee valid for 6 months / Online payment (No.…………………….Dated:..........) for Rs…............/- as earnest money not to bear interest.

I/We enclosed to my/our bid through Online Payment / Bank Guarantee valid for  6 months (No. ……………..Dated:………) for Rs. …………/- towards  Processing fee which is non-refundable.

I/We shall not assign the contract or sublet any portion of the same. In case, if it becomes necessary such subletting with the permission of the Engineer-in-Charge, shall be limited to (1) Labour contract (2) Material contract (3) Transport contract (4) Engaging specialists for special items of work enjoined in A.P.S.S

If MY/OUR bid is successful, on notification by the Department, I/We will submit the original BG  / Onoline payment details towards the EMD to the concerned Managing Director  through registered post/courier/in person so as to reach before the date specified in the intimation notice. If my/our bid is accepted the earnest money shall be retained by the Corporation as security for the due fulfilment of this contract. If upon written intimation to me/us by the O/o the Managing Director, APEWIDC office, I/We fail to attend the said office on the date herein fixed or if upon intimation being given to me/us by the Managing Director / Tender Committee or acceptance of my/our bid, and if I/We fail to make the additional security deposit or to enter into the required agreement then I/We agree the forfeiture of the earnest money. Any notice required to be served on me/us here under shall be sufficiently served on me/us if delivered to me/us hereunder personally or forwarded to me/us by post to (registered or ordinary or e-mail or fax) or left at my/our address given herein.  Such notice shall if sent by post be deemed to have been served on me/us at the time where in due course of post it would be delivered at the address to which it is sent.

I/We fully understand that the written agreement to be entered into between me/us and Corporation shall be the foundation of the rights of the both the parties and the contract shall not be deemed to be complete until the agreement has first been signed by me/us and then by the proper officer authorised to enter into contract on behalf of Corporation.

I/WE agree to pay the corpus fund at 0.04% or as amended from time to time on estimated contract value of the work through online payment in favour of Managing Director, A.P Technology Services, Vijayawada at the time of conclusion of Agreement.

I/WE agree to pay the service charges at 0.06% or as amended from time to time on estimated contract value of the work through a demand draft drawn in favour of Managing Director, A.P Education Welfare Infrastructure Development Corporation, Guntur  at the time of conclusion of Agreement.

I am/we are professionally qualified and my/our qualifications are given below:

| Name & Address | Qualification |
| --- | --- |

I/We will employ the following technical staff for supervising the work and will see that

one of them is always at site during working hours, personally checking all items of works and pay extra attention to such works as required special attention (eg) reinforced concrete work

| Name of members of technical staff proposed to be employed | Qualification |
| --- | --- |

I/We declare that I/We agree to recover the salaries of the technical staff actually

engaged on the work by the department, from the work bills, if I/We fail to employ technical staff as per the bid condition.

BIDDER’S/CONTRACTOR’S CERTIFICATE:

- I/We hereby declare that I/We have perused in detail and examined closely the Andhra Pradesh Standard Specifications/BIS/IRC MORTH, all clauses of the preliminary specifications with all amendments and have either examined all the standards specifications or will examine all the standard specifications for items for which I/We bid, before I/We submit such bid and agree to be bound and comply with all such specifications for this agreement which I/We execute in Corporation.

- I/We certify that I/We have inspected the site of the work before quoting my percentage excess or less on ECV, I/We have satisfied about the quality, availability and transport facilities for all the materials.

- I/We am/are prepared to furnish detailed data in support of all my quoted rates, if and when called upon to do so without any reservations.

- I/We hereby declare that I/We will pay an additional security deposit in terms of instructions to bidders.

- I/We hereby declare that I am/we are accepting to reject my bid in terms of instructions to bidders.

- I/we hereby declare that I/we abide by the decision of the Corporation regarding obtaining specific approval from the Government for payment of any price adjustment. The decision of the Government will be final.

- I/We hereby declare that I am/We are accepting for the defect liability period as 24 Months

- (A) I/We declare that I/WE will procure the required construction materials including earth and use for the work after approval of the Engineer-in-Charge. The responsibility for arranging and obtaining the land for borrowing or exploitation in any other way shall rest with me/us for the materials for construction, I/We shall ensure smooth and un-interrupted supply of materials.

(b) I/We declare that the responsibility for arranging and obtaining the land for disposal of spoil/soil not useful for construction purposes shall rest with me/us.

(C) I/We declare that I/We shall not claim any compensation or any payment for the land so arranged for disposal of soil and the land for borrow area.  My/our quoted percentage excess over or less than ECV are inclusive of the land so arranged and I/We will hand over the land so arranged for disposal of soil to the Corporation after completion of work.

(D) I/We declare that I/WE will not claim any extra amount towards any material used for the work other than the quoted works for respective schedule-A items.

- I/We declare that I/WE will execute the work as per the mile stone programme, and if I/WE fail to complete the work as per the mile stone programme I abide by the condition to recover liquidated damages as per the bid conditions.

- I/We declare that I/WE will abide for settlement of disputes as per the bid conditions.

DECLARATION OF THE BIDDER:

- I/We have not been black listed in any Department/Corporation of State/Central Govt. due to any reasons.

- I/We have not been demoted to the next lower category for not filing the bids after buying the bid schedules in a whole year and my/our registration has not been cancelled for a similar default in two consecutive years.

- I/We agree to disqualify me/us for any wrong declaration in respect of the above and to summarily reject my/our bid.

I/WE ……………………………………………………………….  have gone through carefully all the bid conditions and solemnly declare that  I/we will abide by any penal action such as disqualification or black listing or determination of contract or any other action deemed fit, taken by, the Department against us, if it is found that the statements, documents, certificates produced by us are  false/fabricated.

Address of the bidder:

Phone No:

Fax No:

E-mail:

# Signature of the bidder

Note:	If the bid is made by an individual, it shall be signed with his full name and his address shall be given.  If it is made by a firm, it shall be signed with the co-partnership name by a member of the firm, who shall also sign his own name and the name and address of each member of the firm shall be given. If the bid is made by a corporation, it shall be signed by a duly authorised officer / GPA Holder who shall produce with his tender satisfactory evidence of his authorisation. Such tendering corporation may be required before the contract is executed, to furnish evidence of its corporate existence.  Bids signed on behalf of G.P.A holder will be rejected.

# Conditions of Contract

- General

1. Interpretation:

1.1 In interpreting these conditions of contract, singular also means plural, male also means female, and vice-versa. Headings have no significance. Works have their normal meaning under the language of the contract unless specifically defined. The Engineers-in-Charge will provide instructions clarifying queries about the conditions of contract.

1.2	The documents forming the contract shall be interpreted in the following order of priority:

1. Agreement

2. Letter of acceptance, notice to proceed with the works

3. Contractor’s bid (Technical bid)

4. Conditions of contract

5. Specifications

6. Drawings

7. Bill of quantities (Price bid)

8. Any other document listed as forming part of the contract

2. Engineer-in-Charge’s decisions:

2.1 Except where otherwise specifically stated, the Engineer-in-Charge / Chief Engineer will decide the contractual matters between the Department and the contractor in the role representing the Department.

3. Delegation:

3.1 The Engineer-in-Charge / Chief Engineer may delegate any of his duties and responsibilities to other officers and may cancel any delegation by an official order issued.

- Communications and legal address – Notices:

Communications between parties, which are referred to in the conditions, are effective only when in writing. A notice shall be effective only when it is delivered (in terms of Indian Contract Act).

- Sub-contracting: 	- Not Allowed –

The contractor / firm will not be permitted to sub let either the whole work or a part of the work without prior permission from the competent authority. If the contractor / firm is found at any instance during the period of execution, that the whole work or a part of the work is Sub-let to any other agency / firm or to any other contractor without the approval of competent authority, legal proceedings will be initiated and such contractor for the default and further the work done not paid and all the security deposits lodged by the contractor will be forfeited and no correspondence will be entertained in this regard.

6. Other contractors:

6.1	The contractor shall cooperate and share the site with other contractors, public authorities, utilities, and the Department. The contractor shall also provide facilities and services for them as directed by the Engineer-in-Charge.

7. Personnel:

7.1 	The Contractor / Agency Should employ separate Technical Personnel on each work. The Contractor / Agency shall upload, the qualification Certificates of the Technical Agents employed and their consent letters

B – The Contractor shall employ the required key personnel named in the schedule of key personnel to carry out the functions stated in the Schedule or other personnel approved by the Engineer-in-Charge / Chief Engineer. The Engineer-in-Charge / Chief Engineer will approve any proposed replacement of key personnel only if their qualifications, abilities and relevant experience are substantially equal to or better than those of the personnel listed in the schedule. The Technical Agents shall ensure their attendance at site as directed by APEWIDC.

7.2 Schedule of Key Personnel:

The successful tender shall have to employ the following technical staff on full time basis to be available at site.

| Cost of work (Technical sanction amount) | Qualification of Technical Staff |
| --- | --- |
| 1 | 2 |
| From Rs. 20,000/- to Rs. 1.00 lakhs | One I.T.I candidate |
| Above Rs. 1.00 lakhs upto Rs. 15.00 lakhs | One diploma holder |
| Above Rs. 15.00 lakhs upto Rs. 50.00 Lakhs | One Graduate Engineer |
| Above Rs. 50.00 lakhs upto Rs. 100.00 Lakhs | One Graduate Engineer and One Diploma holder |
| Above Rs. 100.00 lakhs upto Rs. 500.00 Lakhs | Two Graduate Engineers |
| Above Rs. 500.00 lakhs upto Rs. 1000.00 Lakhs | Two Graduate Engineer and One Diploma holder |
| Above Rs. 1000.00 lakhs and Above | Three Graduate Engineer and Two Diploma holders & Two Electrical Engineers |
| Above Rs. 5000.00 lakhs and above | Six Graduate Engineers and Two Electrical Engineers |

7.3 	Employment of technical personnel shall be with reference to the estimate cost of work 	put to tender.

7.4	The appointment of technical staff shall be on full time basis.

The Technical staff shall be available at work site for supervising the work including quality checking of all items from time to time. Failure to employ the required technical personnel by the contractor, amounts will be recovered at the following rates from the contractor.

Diploma Engineer	- Rs. 37,650 /- Per Month

Graduate Engineer	- Rs. 48,750 /- Per Month

7.5	The Engineer-in-charge/Agreement authority is the sole judge (a) to decide whether 	qualified technical staff is actually supervising the work and (b) to decide the actual 	period of absence of such staff which requires the above recovery to be enforced and 	his decision is final and binding on the contractor.

7.6	The technical agents appointed by the contractor shall have to maintain properly all the 	records required by the department under safe custody at site, like checklists, calibration registers/records, quality test registers, test reports file site order book etc., and make signatures at appropriate places towards proof of verifications, conduction of  tests, compliance to instructions etc.,

7.7	The technical personnel should be on full time and available at site whenever required by Engineer-in-Charge to take instructions. The technical staff shall be available at work site for supervising the work including quality checking of all items from time to time and 	shall have to maintain properly all the records required by the department under safe custody at site like checklists, calibration registers/records, quality test registers, test 	reports file, site order book, etc. and make signatures at appropriate places towards 	proof of verifications, conduction of tests, compliance to instructions etc.

7.8	The names of the technical personnel to be employed by the contractor should be 	furnished in the statement enclosed separately for each work and should not be 	employed elsewhere on any other work. Even if the contractor is himself a technically 	qualified person, he shall employ required technical staff on the scale prescribed for 	supervising all the works separately irrespective of location of work sites in case the 	overheads are allowed in the data for each work.

7.9	In case the contractor is already having more than one work on hand and has undertaken more than one work at the same time, he should employ separate technical 	personnel on each work.

7.10	If the contractor fails to employ required technical personnel as specified in the 	agreement, work will be suspended or department will engage required technical 	personnel and recover the cost from the contractor at penal rate of two times thereof as 	per the respective SSR rates.

7.11	If the Engineer-in-Charge asks the contractor to remove a person who is a member of 	contractor’s staff or his work force stating the reasons the contractor shall ensure that 	the person leaves the site forthwith and has no further connection with the work in the 	contract.

The contractor has to open an account in nearest bank in the name of the technical staff appointed by them and their salary should be paid through the account only

The contractor has to certify that the same technical persons appointed shall not be utilized during agreement period on any other work in any other organization and if found at any stage, liable to recover the amount in addition to the normal recovery.

No reimbursement will be made to the contractor towards engaging technical staff as the data includes overhead charges which covers engaging technical staff also. The contractor should produce paid vouchers and bank extracts of the technical staff salary particulars paid by the contractor whenever the Engineer-in-Charge/Agreement authority asks for the same from the contractor.

7.12	The Engineer-in-Charge/Agreement authority is the sole judge to decide (a) whether qualified technical staff is actually supervising the work and (b) the actual period of absence of such staff which requires the above recovery to be enforced and his decision is final and binding on the contractor.

- Contractor’s risks:

8.1	All risks of loss of or damage to physical property and of personnel injury and death, which arise during and in consequence of the performance of the contract are the responsibility of the contractor.

- Insurance: Deleted as per G.O Ms No 5, Dt:05.03.2014 of Finance (W & P) Department.

- Site inspections:

10.1 The contractor should inspect the site and also proposed quarries of choice for 	materials, source of water and quote his percentage including quarrying, 	conveyance

and all other charges etc.

10.2	The responsibility for arranging the land for borrow area rests with the contractor and no separate payment will be made for procurement or otherwise. The contractor’s quoted percentage will be inclusive of land cost.

- Contractor to construct the works:

11.1	The contractor shall construct and commission the work in accordance with the 	specifications and drawings.

12.	Diversion of streams/vagus/drains:

12.1	The contractor shall at all times carry out construction of cross drainage works in a manner creating least interference to the natural flow of water while consistent with the satisfactory execution of work. A temporary diversion shall be formed by the contractor at his cost where necessary. No extra payment shall be made for his work.

12.2	No separate payment for bailing out sub soils, water drainage or locked up rain water for diversion and such other incidental will be made. The percentage to be quoted by the contractor is for the finished item of work in situ and including all the incidental charges. The borrow pits are also to be dewatered by the contractor himself at his expense, if that should be found necessary.

12.3	The work of diversion arrangements should be carefully planned and prepared by the contractor and forwarded to the Executive Engineer technically substantiating the proposals and approval of the Executive Engineer obtained for execution.

12.4	The contractor has to arrange for bailing out water, protection to the work in progress and the portion of works already completed and safety measures for men and materials and all necessary arrangements to complete the work.

12.5	All the arrangements so required should be carried out and maintained at the 	cost of the contractor and no separate or additional payments is admissible.

12.6	Coffer dams:

Necessary coffer dams and ring bunds have to be constructed at the cost of 	contractor and same are to be removed after the completion of the work. The 	contractor has to quote his percentage keeping the above in view.

13)     Power supply:

13.1	The contractor shall make his own arrangements for obtaining power from the electricity Department at his own cost. The contractor will pay the bills of 	electricity Department for the cost of power consumed by him.

13.2	The contractor shall satisfy all the conditions and rules required as per Indian 	electricity Act 1910 and under Rule-45(I) of the Indian Electricity Rules, 1956 as 	amended from time to time and other pertinent rules.

13.3	The power shall be used for bonafide Corporation work only.

13.4	The contractor shall at all times during the currency of the contract, comply fully with all existing Acts, regulations and bylaws including all statutory amendments 	and re-enactment’s of state or central govt., and other local authorities and any other enactment’s, notification and acts that may be passed in future either by the state or the central government or local authority including Indian workmen’s compensation Act- 1923,  Control labour (Regulation and Abolition) Act- 1970, The child labour prohibition and regulation Act-1986 and equal remuneration Act- 1976, Factories Act, minimum wage Act- 1948, provident fund regulations, Employees provident fund Act- 1952 schedules made under the same Act.  The 	buildings and other construction workers (Regulation of employment and condition of service ) Act- 1996, The Cess Act- 1996 and also applicable labour 	regulations, health and sanitary arrangement for workmen, insurance and other benefit and shall keep department indemnified in case any action is commenced 	by competent authorities for contravention by the contractor.

13.5	The electrical contractor has to keep his licence in currency till the work is 	completed.  If the licence is suspended during the period in which the work is in 	progress the contract will be terminated and awarded to some other agency 	recovering the extra cost if any.

13.6	The materials used in the work should be as per the list of materials enclosed and as per specifications mentioned in BOQ works. The department reserves the right to insist upon using any of the materials from this list of approved materials.

13.7	The work shall be carried out strictly in conformity with (i)code of practice for 	Electrical wiring and fittings in Government Buildings, (ii) The Indian standard 	specification (iii) The Department specification.  If the work carried out does not 	comply with the code of practice and the Departmental specifications and if the 	workmanship is unsatisfactory it will be binding on the contractor to redo the job 	without any extra cost and pay penalty as decided by the Department towards 	inconvenience caused if any.

13.8	The work should be carried out under the direct supervision of persons holding a certificate of competency for the type of work involved.

13.9	After completion of work a plan of building installation should be prepared and furnished indicating the location of various main and sub boards and also the fittings together with a circuit diagram duly numbered (in the diagram).  The final 	bill will not be paid till the above plan and the diagram is submitted and approved after verification. Such completion drawings shall be signed by the licenced electrical contractor through whom the work is executed.

13.10	Lugs should be provided for all required number of earth connections.

13.11	The contractor himself should arrange for the transportation of men and 	materials to the work spot.

13.12	Concreting to the pole and providing independent earthing should be done in 	presence of Departmental staff.

13.13	On completion of the Electrical Installation a certificate shall be furnished by the Contractor countersigned by a licensed supervisor, that under direct supervision 	the installation was carried out.   This certificate shall be in the prescribed from as required by the local supply authority.  The contractor shall be responsible for getting the Electrical Installation inspected and approved by the local authority 	concerned.

13.14	The contractor shall pay for any inspection fees and for permits required for the installation of the work wherever necessary.  The APEWIDC shall arrange only 	for payment of service connection charges and any other security deposit for 	getting electrical supply. On completion of the work, the contractor shall obtain 	and deliver to the APEWIDC, certificates of final inspection and approval by the  concerned Electric Authority as may require. The APEWIDC shall have full powers to require the materials or work to be tested by an independent agency at the Electrical contractor’s expense in order to prove their soundness and 	adequacy.

13.15	Contractor shall provide everything necessary for the proper execution of works   according to the intent and meaning of the drawings, specifications, schedule of quantities. Any discrepancy in the documents shall be brought to the notice of 	the  APEWIDC and got clarified prior to taking up the installation.

13.16	Materials and workmanship:

All materials and workmanship shall confirm to the specifications, relevant IS standards and code of practice and comply with APSEB/CEIG requirements as the case may be.  Any work that is not up to the standards shall be dismantled and reconstructed by the contractor to the satisfaction of the APEWIDC.

13.17	Liaison Work:

The Contractor shall be responsible for all liaison work with Electricity 	Board/CEIG.

13.18	“The Civil Contractor shall get all the electrical works done only through the licensed electrical contractors/permit holders as registered with or licensed by A.P State Electrical Licensing Board. A copy of such valid license/permit should be furnished by successful Civil Contractor, at the time of concluding agreement, 	for each work separately. The commencement and completion certificate and 	drawings for each work issued by the electrical licensed Contractor/Permit holder 	should be furnished by Civil Contractor, for releasing payment of electrical work”.

14.	Temporary diversions (Works on highways):

14.1	The contractor shall at all times carryout work on the highway in a manner creating least interference to the flow of traffic while consistent with the 	satisfactory execution of the same. For all works involving improvements to the existing highway, the contractor shall in accordance with the directions of the Engineer-in-Charge provide and maintain during the execution of the work a passage for traffic, either along a part of the existing carriage way under improvement or along a temporary diversion constructed close to the highway.

14.2	If in the opinion of the Engineer-in-Charge, it is not possible to pass the traffic on part width of the carriage-way for any reason, a temporary diversion close to the highway shall be constructed as directed. It shall be paved with the materials such as hard morrum, gravel and stone, metal to the specified thickness as directed by the Engineer-in-Charge. In all cases, the alignment, gradients and surface type of the diversion including its junctions, shall be approved by the 	Engineer-in-Charge before the highway is closed to traffic.

14.3	The contractor shall take all necessary measures for the safety of traffic during construction and provide, erect and maintain such barricades, including signs, markings, flags, lights and information and protection of traffic approaching or passing through the section of the highway under improvement. Before taking up any construction, an agreed phased programme for the diversion of traffic on the highway shall be drawn up in consultation with the Engineer-in-Charge.

  - The barricades erected on either side of the carriage way portion of the carriage

way closed to traffic, shall be of strong, design to resist vibration and painted with alternative black and white stripe. Red lanterns or warnings lights of similar type shall be mounted on the barricades at night and kept lit throughout from sunset to sunrise

- Ramps:

Ramps required during execution may be formed wherever necessary and same are to be removed after completion of the work. No separate payment will be made for this purpose.

- Monsoon damages:

Damages due to rain or flood either in cutting or in banks shall have to be made good by the contractor till the work is handed over to the Department. The responsibility of de-silting and making good the damages due to rain or flood rests with the contractor. No extra payment is payable for such operations and the contractor shall therefore, have to take all necessary precautions to protect the work done during the construction period.

- The works to be completed by the intended completion date:

17.1	The contractor may commence execution of the works on the start date and shall carry out the works in accordance with the programme submitted by the contractor, as updated with the approval of the Engineer-in-Charge and complete the work by the intended completion date.

- Safety:

18.1	The contractor shall be responsible for the safety of all activities on the site.

- Discoveries:

19.1	Anything of historical or other interest or of significant value unexpectedly

discovered on the site is the property of the Government. The contractor is to notify the Engineer-in-Charge of such discoveries and carry out the Engineer-in-Charge’s instructions for dealing with them.

- Possession of the site:

20.1	The Corporation shall give possession of the site to the contractor. If possession of a part site is given, the Corporation will ensure that the part site so handed over is amenable to carryout the work at site by the contractor.

- Access to the site:

21.1	The contractor shall provide the Engineer-in-Charge and any person authorised by the Engineer-in-Charge, access to the site and to any place where the work in connection with the contract is being carried out or is intended to be carried out.

- Instructions:

22.1	The contractor shall carry out all instructions of the Engineer-in-Charge and comply with all the applicable local laws where the site is located.

- Settlement of disputes:

23.1	If any dispute of difference of any kind whatsoever arises between the Corporation and the contractor in connection with, or arising out of the contract, whether during the progress of the works or after their completion and whether before or after the termination, abandonment or breach of the contract, it shall in the first place, be referred to and settled by the Engineer-in-Charge  who shall, 	within a period of thirty days after being requested by the contractor to do so, give written notice of his decision to the contractor. Upon receipt of the written 	notice of the decision of the Engineer-in-Charge the contractor shall promptly proceed without delay to comply with such notice of decision.

23.2	If the Engineer-in-Charge fails to give notice of his decision in writing within a period of fifteen days after being requested or if the contractor is dissatisfied with 	the notice of the decision of the Engineer-in-Charge, the contractor may within thirty days after receiving the notice of decision appeal to the Corporation who shall of per an opportunity to the contractor to be heard and to offer evidence in support of his appeal, the Corporation shall give notice of his decision within a period of thirty days after the contractor has given the said evidence in support of his appeal, subject to arbitration, as hereinafter provided. Such decision of the Corporation in respect of every matter so referred shall be final and binding upon the contractor and shall forthwith be given effect to by the contractor, who shall proceed with the execution of the works with all due diligence whether he 	requires arbitration as hereinafter provided, or not. If the Corporation has given written notice of his decision to the contractor and no claim to arbitration, has been communicated to him by the contractor within a period of thirty days from receipt of such notice the said decision shall remain final and binding upon the contractor. If the Corporation fail to give notice of his decision, as aforesaid within a period of thirty days after being requested as aforesaid, or if the contractor be dissatisfied with any such decision, then and in any such case the contractor within thirty days after the expiration of the first named period of thirty days as the case may be, require that the matter or matters in dispute be 	referred to arbitration as detailed below:-

Settlement of Claims:

Settlement of claims for Rs. 20,000/- and below by arbitration.

All disputes or difference arising of or relating to the Contract shall be referred to the adjudication as follows:

a)	Claims up to a value of Rs. 20,000/-: Managing Director , APEWIDC, Amaravathi

b)	Claims above Rs.20,000/- and up to Rs. 20,000/-: Chief Engineer, (R&B) Buildings, Vijayawada.

The arbitration shall be conducted in accordance with the provisions of Indian Arbitration and Conciliation Act 1996 or any statutory modification thereof.

The arbitrator shall state his reasons in passing the award.

Claims above Rs.75,000/-.

All claims of above Rs.75,000/- are to be settled by a Civil Court of competent jurisdiction by way of civil suit and not by arbitration.

A reference for adjudication under this clauses shall be made by the contractor within six months from the date of intimating the contractor of the preparation of final bill or his having accepted payment which ever is earlier.

- Time FOR COMPLETION

- Program:

  - The total period of completion is 12 Months from the date of entering with

agreement to proceed including rainy season.  Keeping in view, the schedule for handing over of site given in condition 24.4 below, work should be programmed such as to achieve the mile stones as in “Rate of progress statement” enclosed. Mile stones will be drawn by the concerned Managing Director  in consultation with the executing agency at the time of concluding agreement.

  - The attention of the bidder is directed to the contract requirement at the time of

beginning of the work, the rate of progress and the dates for the whole work and its several parts as per milestones. Time is the essence of the contract. The 	following rate of progress and proportionate value of work done from time to time 	as will be indicated by the Engineer-in-Charge’s certificate for the value of work done and completion of milestones will be required. The date of commencement of their program will be the date of concluding agreement.

24.3	After signing the agreement, the contractor shall forthwith begin the work, shall 	regularly and continuously proceed with them. Work programme of achieving of 		milestones (statement) should be submitted from time to time.

24.4	The following rate of progress will be required to be maintained by the contractor as a minimum. The start date of this work is the date of signing the agreement but not the date of handing over the site. Contractor may give a separate time schedule for the completion of the whole work and the consideration will be given for accelerated programme. It is imperative that the work progress shall be ahead of the rate of progress given below:

Rate of progress: The work is to be completed within 12 Months from the date of commencement and as per the schedule given below:

i) Work programme of achieving the milestones (Statement).

| Mile Stone I | As per agreement | Upto 04 Months |
| --- | --- | --- |
| Mile Stone 2 | As per agreement | Upto 08 Months |
| Mile Stone 3 | As per agreement | Upto 12 Months |

(failing which action will be initiated as per clause no.48.3)

Note:	Detailed programme in terms of collection of necessary materials and labour and in terms of finished items of work, to confirmation of the above rate of progress shall be prepared by the contractor and got approved by the Engineer-in-Charge/Agreement authority concerned and which shall be strictly adhered to. This programme of work shall be given based on PERT/CPM charts for works where ECV exceeds Rs.100 Lakhs in the approved format.

ii) 	Site schedule of programme of handing over site to the Contractor (Statement)

24.5	The contractor shall commence the works on site within the period specified

under condition 24.1 to 24.4 above after the receipt by him of a written order to this

effect from the Managing Director  and shall proceed with the same with due expedition and without delay, except as may be expressly sanctioned or ordered by the Managing Director , or be wholly beyond the contractor’s control.

24.6	same in so far as the contractor may prescribe, the extent of portions of the site

of which the contractor is to be given possession from time to time and the order 	in

which such portions shall be made available to him and, subject to any requirement in

the contract as to the order in which the works shall be executed, the Managing Director  will, give the Executive Engineer’s written order to commence the works, The

Engineer-In-Charge will give to the contractor possession of so much of the site as may be required to enable the contractor to commence and proceed with the execution of the works in accordance with the programme if any, and otherwise in accordance with such reasonable proposals of the contractor as he shall by written notice to the Engineer-In-Charge and will 	from time to time as the works proceed give to the contractor possession of such further portions of the site as may be required to enable the contractor to proceed with the execution of the works with due dispatch in accordance with the said programme or proposals as the case maybe, if the contractor suffers delay or incurs cost from failure on the part of the Engineer-In-Charge  to give possession in accordance with the terms of this clause, the Managing Director APEWIDC shall grant an extension of time for the completion of works.

24.7	The contractor shall bear all costs and charges for special or temporary way leases required by him in connection with access to the site. The contractor shall also provide at his own cost any additional accommodation outside the site 	required by him for the purposes of the work.

24.8	Subject to any requirement in the contract as to completion of any section of the works before completion of the whole of the works shall be completed in 	accordance with provisions of clauses in the schedule within the time stated in the contract calculated from the last day of the period named in the statement to the bid as that within which the works are to be commenced or such extended time as may be allowed.

24.9	Delays and extension of time:

No claim for compensation on account of delays or hindrances to the work from any cause whatever shall lie, except as hereafter defined.  Reasonable extension of time will be allowed by the Managing Director, APEWICD, Amaravathi or by the officer competent to sanction the extension, for unavoidable delays, such as may result from causes, which in the opinion of the Executive Engineer are undoubtedly beyond the control of the contractor. The Executive Engineer shall assess the period of delay or hindrance caused by any written instructions issued by him, at twenty five per cent in excess or the actual 	working period so lost. In the event of the Executive Engineer failing to issue necessary instructions and thereby causing delay and hindrance to the contractor, the latter shall have the right to claim an assessment of such delay by the Managing Director of the 	Corporate whose decision will be final and binding. The contractor shall lodge in writing with the Executive Engineer a statement of claim for any delay or 	hindrance referred to above, within fourteen days from its commencement, otherwise no extension of time will be allowed. Whenever authorised alterations or additions made during the progress of the work are of such a nature in the opinion of the Executive Engineer as to justify an extension of time in consequence thereof, such extension will be granted in writing by the Managing Director, APEWIDC, Amaravathi or other competent authority when ordering such alterations or additions.

- Construction programme:

25.1	The contractor shall furnish within one month of the order of the work a 	programme showing the sequence in which he proposed to carry out the work, monthly progress expected to be achieved, also indicating date of procurement of materials, plant and machinery. The schedule should be such that it is practicable to achieve completion of the whole work within the time limit fixed and in keeping with the mile stone programme specified and shall obtain the approval of the Engineer-in-charge. Further rate of the progress as in the program shall be kept up to date. In case it is subsequently found necessary to alter this program, the contractor shall submit sufficiently in advance the revised program incorporating necessary modifications and get the same approved by the Managing Director, APEWIDC, Amaravathi. No revised program shall be operative without approval of Managing Director, APEWIDC, Amaravathi

25.2	The Managing Director, APEWIDC  shall have all times the right, without any way violating this contract, or forming grounds for any claim, to alter the order of progress of the works or any part thereof and the contractor shall after receiving such directions proceed in the order directed. The contractor shall also report the progress to the Chief Engineer Concerned within 7 days of the Executive Engineer’s direction to alter the order of progress of works.

25.3	The contractor shall give written notice to the Engineer-in-Charge whenever planning or progress of the works is likely to be delayed or disrupted unless any further drawings or order including a direction, instruction or approval is issued by the Engineer-in-Charge within a reasonable time. The notice shall include details of the drawing or order required and of why and by when it is required and of any delay or disruption likely to be suffered if it is late.

- Speed of work:

26.1	The contractor shall at all times maintain the progress of work to conform to the latest operative progress schedule approved by the Engineer-in-Charge / Chief Engineer. The contractor should furnish progress report indicating the programme and progress once in a month.  The Engineer-in-Charge may at any time in writing direct the contractor to slow down any part or whole of the work for any reason (which shall not be questioned) whatsoever, and the contractor shall comply with such orders of the Engineer-in-Charge. The compliance of such orders shall not entitle the contractor to any claim of compensation. Such orders of the Engineer-in-Charge for slowing down the work will however be duly taken into account while granting extension of time if asked by the contractor for which no extra payment will be entertained.

26.2	Delays in commencement or progress or neglect of work and forfeiture of earnest money, security deposit and withheld amounts:

If, at any time, the Engineer-in-Charge shall be of the opinion that the contractor is delaying commencement of the work or violating any of the provisions of the contract or contractor is neglecting or delaying the progress of the work as defined by the tabular statement. “Rate of progress” in the articles of agreement, he shall so advise the contractor in writing and at the same time demand compliance in accordance with conditions of bid notice/bid document/Agreement. If the contractor neglects to comply with such demand within seven days after receipt of such notice, it shall then or at any time there after, be lawful for the Engineer-in-Charge / Chief Engineer to take suitable action in accordance with Clause 60 of APSS.

- Suspension of works by the contractor:

27.1	If the contractor suspend the works, or sublet the work without sanction of the Engineer-in-Charge, or in the opinion of the Engineer-in-Charge neglect or fail to proceed with due diligence in the performance of his part of the contract as laid down in the schedule rate of progress, or if he continue to default or repeat such default in the respects mentioned in clause 27 of the APSS, Engineer-in-Charge shall take action in accordance with clause 61 of APSS.

27.2	If the contractor stops work for 28 days and the stoppage has not been authorised by the Engineer-in-Charge the contract will be terminated under Clause 61 of APSS.

27.3	If the contractor has delayed the completion of works the contract will be terminated under clause 61 of APSS.

- Extension of the intended completion date:

28.1	The Managing Director, APEWIDC, Amaravathi shall extend, in accordance with the Government orders in force, the intended completion date if a variation is issued which makes it impossible for completion to be achieved by the intended completion date.

28.2	The Engineer-in-Charge shall decide whether and by how much to extend the intended completion date within 21 days of the contractor asking the Engineer for a decision upon the effect of a variation and submitting full supporting information. If the contractor has failed to give early warning of a delay or has failed to cooperate in dealing with a delay, the delay by this failure shall not be considered in assessing the new intended completion date.

- Delays ordered by the Engineer-in-Charge:

29.1	The Engineer-in-Charge may instruct the contractor to delay the start or progress of any activity within the work.

- Early warning:

30.1	The Engineer in charge is to warn the Contractor at the earliest opportunity of the future specific events or likely circumstances that may adversely affect the execution of works.

30.2	The contractor shall cooperate with the Engineer-in-Charge in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone involved in the work and in carrying out any resulting instruction of the Engineer-in-Charge.

- Management meetings:

31.1	The Engineer-in-Charge may require the contractor to attend a management meeting.  The business of a management meeting shall be to review the programme for remaining work and to deal with matters raised in accordance with the early warning procedure.

- Quality Control

- Identifying defects:

32.1	The Engineer-in-Charge shall check the contractor’s work and notify the contractor of any defects that are found. Such checking shall not affect the contractor’s responsibilities. The Engineer-in-Charge may instruct the contractor to verify the defect and to uncover and test any work that the Engineer considers may be a defect.

- Tests:

33.1	If the Engineer-in-Charge instructs the contractor to carry out a test not specified in the specification to check whether any work has a defect and the contractor shall pay for the test and any samples.

- Correction of defects:

34.1	The Engineer-in-Charge shall give notice to the contractor of any defects before the end of the defects liability period, which begins on completion. The defect liability period shall be extended for as long as defects remain to be corrected by the contractor.

34.2	Every time notice of a defect is given, the contractor shall correct the notified defect within the length of time specified by the Engineer-in-Charge’s notice.

- Uncorrected defects:

35.1	If the Contractor has not corrected the defects within the time specified in the Engineer in charge’s notice, the Engineer in charge will assess the cost of having the defect corrected and the cost of correction of such defects will be recovered from the Contractor’s deposits and from any money due to the Contractor from any work executed or being executed in this Corporation or in any other Corporation or in ay other department of the State Government under RR Act.

35.2	The Engineer-in-Charge shall introduce O.K cards and prescribed the formats there of O.K cards shall relate to all major components of the work. The contractor/his authorised representative shall be required to initiate and fill in and present the O.K card to the construction staff who would check the respective items and send to the quality control staff for final check and clearance/O.K. Any defects pointed out by the construction supervision staff or by the quality control staff shall promptly be attended to by the contractors and the fact of doing so be duly recorded on the back of O.K card.

35.3	The Engineer-in-Charge may also introduce checklists, which shall be kept in bound registers by the construction supervision staff. The contractor may be required to fill up these lists in the first instance and shall be subsequently checked by the construction/quality control Engineers.

- Quality control:

i)	Establishment of quality control laboratory: The contractor shall establish a quality control laboratory at the site of work equipped with calibrated equipment (as per list given below) to perform field tests, batch wise, for various materials, then and there itself, as per quality plan and standards.

ii)	Calibration of equipment: All the equipment maintained by the contractor at site shall be calibrated from time to time according to the calibration frequency mentioned hereunder, with calibrations traceable to national standards. Records for proof of such calibrations done for each instrument, with instrument number shall be maintained by the contractor and shall be made available for verification/counter signature by the Engineer-in-Charge / Chief Engineer. Proper storage, handling and use of these instruments shall be ensured so that their calibration does not get disturbed due to weather factors etc., Frequency of the calibration shall be as decided by the Engineer-in-Charge.

iii)	List of equipment which should be made available at site by the contractor for testing of materials and cubes etc., is given below:

| Sl.No | Description of item | Recommended calibration frequency |
| --- | --- | --- |
| 1. | Vernier calipers 0-150 mm | 1 year |
| 2. | Screw gauge 0-25 mm | 1 year |
| 3. a 3. b | Measurement tapes both steel (3.0 m, 5.0 m) & fibre (15.0 m) 30 cm steel scale | At the time of purchase and the tapes to be changed after 6 months, if any error is observed |
| 4. | Weighing machine 5.0 kg capacity | 6 months |
| 5. | Sieves for coarse aggregate | - |
| 6. | Sieves for fine aggregate | - |
| 7. | Cube moulds ISI marked 150 x150 x 150 mm (6 Nos) | - |
| 8. | Compression testing machine 100 MT, hand operated at every work site whose estimated contract value is Rs. 100 Lakhs and above. For less than Rs. 100 Lakhs, arrangement for testing at approved lab. | 6 months |
| 9. | Slump cone | - |
| 10. | Carpenter’s square 150mm with graduations |  |
| 11. | Electrical Meggar 1100 V | At the time of purchase |
| 12. | Spirit level | - |
| 13. | Plum bob | - |
| 14. | Measuring jars (2) 250 ml | - |
| 15. | Magnetic compass | - |
| 16. | Batching and mixing plant for concrete mixing (30 cum capacity) | - |

iv)	Quality plan for raw materials: The contractor shall collect various raw materials well in advance before its use and shall get them tested as per the quality plan supplied by the Engineer-in-Charge based on quality management system of ISO: 9001-2000. He shall ensure that no raw material is used unless it passes all the checks / tests as per the acceptance criteria given and a record of all checks / tests/ verifications shall be maintained at site. Tests which are required to be conducted at outside labs shall be done at those labs which have availability of required instruments traceable to national standards and which are approved by the Engineer-in-charge. Reports obtained from such labs should indicate the calibration status and traceability to national standards of their equipments for accepting the results.

v)	If the Engineer-in-Charge instructs the contractor to carryout a test not specified in the specification to check whether any work has a defect, the contractor shall conduct the test at his own cost.

vi) 	Quality control inspections: In addition to the normal inspection by the regular in charge of the construction, the work will also be inspected by the staff of quality control wings or by the state or district level vigilance cell unit and any authorized external agency and if any sub-standard work or excess payments are noticed with reference to measurement books etc., during inspection, recovery will be ordered based on their observations and these will be effected by the Engineer-in-Charge of the execution of the work.

In addition, the Corporation may engage external agencies for conducting quality audit in which case the following methodology would be adopted:

a)	The external agency shall conduct quality control tests as per the standard -procedures in the presence of Construction and Quality Control Engineers and the Contractor who is executing the work.

b)	The observations of the external agencies on the quality of work should be recorded then and there and signatures of all the concerned obtained as a token of acceptance of the observations.

The recovery for any sub standard work or excess payments noticed if any on account of the external quality also would be made as mentioned in the Para above.

The final bill will be released after a certificate furnished by the Engineer-in-Charge that the work has been executed as per the standard specifications with  ATRs for the Quality control / 3rd party checking and counter signature of ATRs as per the guide lines issued by Finance Department  and then only the final bill can be released.

Records to be maintained at site:

vii)	Drawings: One copy of the drawings furnished to the contractor shall be kept by the contractor on the site and same shall be available for inspection and use by the Departmental officers.

viii)	Variations by way of modification, omissions or additions:

For all modifications omissions from or additions to the drawings and specifications, the Engineer-in-Charge will issue revised plans, or written instructions, or both and modification, omission or additions shall be made unless authorised and directed by the Engineer-in-Charge in writing.

ix)	Engineer-in-Charge shall have the privilege of ordering modifications, omission or additions at any time before the completion of the work and such orders shall not operate to annual those portions of the specifications with which said changes do not conflict.

x)	Site Order Book: The site order book shall be maintained by the contractors at the site of the work.  As far as possible all orders regarding the work are to be entered in this book.  All entries shall be signed and dated by the Departmental Officer who issues such orders and signed by the contractor or by his representative towards compliance.  The Site order book shall not be removed from the work spot except with the written permission of the Engineer-in-charge.

xi)	Quality Test Register (QTR): The contractor shall maintain the QTR at the site in the format specified and record therein the results of all the tests conducted by him. The relevant reports of the tests conducted shall be maintained in a separate file.

xii)	Other Documents: Other prescribed documents like register on calibration of equipments maintained at site and other checklists shall be maintained at site and produced for verification of inspecting officers.

xiii)	Return of site documents: All the site records / documents mentioned therein must be returned to the engineer-in-charge in full shape after the satisfactory completion of work.

In addition to the normal inspection by the regular staff in-charge of the construction of work, the work will also be inspected by the Executive Engineer, quality control & vigilance or by the State or District level vigilance cell unit and any other authorised external agency if any sub standard work or excess payments are noticed with reference to measurement books etc., during inspection, action will be taken based on their observations and these will be effected by the Engineer-in-Charge of the execution of the work.

For all works costing more than Rs.2.00 Crores the Contractor shall submit quality plan and also show proof of owning quality lab .

# D. Cost Control

- Bill of quantities:

37.1	The bill of quantities shall contain items for the construction work to be done by the contractor.

37.2	The Contractor is paid for the quantity of the work done at the estimate rate in the bill of quantities for each item and plus or minus tender percentage will be operated on the overall work done in each bill.

- Changes in the quantities:

38.1	The contractor is bound to execute all supplemental works that are found essential, incidental and inevitable during execution of main work.

38.2	The payment of rates for such supplemental items of work will be regulated as under: Supplemental items directly deducible from similar items in the original agreement.

38.2.1	The rates shall be derived by adding to or subtracting from the agreement rate of such similar item the cost of the difference in the quantity of materials labour between the new items and similar items in the agreement worked out with reference to the standard schedule of rates adopted in the sanctioned estimate with which the bids are accepted plus or minus over all bid percentage.

38.2.2	(a) Similar items but the rates of which cannot be directly deduced from the 	original agreement.

(b) Purely new items which do not correspond to any item in the agreement.

38.2.3	The payment for all such items shall be estimated rates plus or minus overall Bid 	percentage.

- Extra items:

39.1	Extra items of work shall not vitiate the contract. The contractor shall be bound to execute extra items of work as directed by the Engineer-in-Charge. The rates for extra items shall be worked out by the Executive Engineer as per the conditions of the contract and the same are binding on the contractor.

39.2	The contractor shall before the 15th day of each month, submit in writing to the Executive Engineer a statement of extra items if any that they have executed during the preceding month failing which the contractor shall not be entitled to claim any.

39.3	Entrustment of additional items:

39.3.1	Where ever additional items not contingent on the main work and outside the scope of original agreement are to be entrusted to the original contractor dispensing with bids and if the value of such items exceeds the limits up to which the officer is empowered to entrust works initially to contractor without calling for bids, approval of the competent authority shall be obtained. Entrustment of such items on nomination shall be at rates not exceeding the estimated rates in case of premium tenders and in case of discount tenders, it will be estimated rates (-) original tender percentage.

39.3.2	Entrustment of the additional items contingent on the main work will be authorised by the officers up to the monetary limits up to which they themselves are competent to accept items in the original agreement so long as the total amounts up to which they are competent to accept in an original agreement rates for such items shall be worked out in accordance with the procedure (I) For all items of work in excess of the quantities shown in the bill of quantities of the bids, the rate payable for such items shall be estimate rates for the items (+) or (-) over all bid percentage accepted by the competent authority.

39.3.3	Entrustment of either the additional or supplemental items shall be subject to the provisions of the agreement entered into by a competent authority after the bid is accepted. The Chief Engineer, APEWIDC, Vijayawada being the authority, who entered into the agreement approves the rate for the items/variation in quantity in the current agreement. The items shall not be ordered by an officer on his own responsibility if the revised estimate or deviation statement providing for the same requires the sanction of higher authority.

Note:	It may be noted that the term estimate rate used above means the rate in the sanctioned estimate with which the bids are accepted, or if no such rates is available in the estimate, the rate derived will be with reference to the standard schedule of rates adopted in the sanctioned estimate with which bids are accepted.

- Cash flow forecasts:

40.1	When the program is updated, the contractor is to provide the Engineer-in-Charge with an updated cash flow forecast.

- Payment certificates:

41.1	The contractor shall submit to the Engineer-in-Charge monthly statements of the estimated value of the work completed less the cumulative amount certified previously.

41.2	The Engineer-in-Charge shall check the contractor’s monthly statement within 14 days.

41.3	The value of work executed shall be determined by the Engineer-in-Charge.

41.4	The value of work executed shall comprise the value of the quantities of the items in the bill of quantities completed.

41.5	The Engineer-in-Charge may exclude any item certified in a previous certificate or reduce the proportion of any item previously certified in any certificate in the light of later information.

- Payments:

42.1	 On-line payment will be made to the Contractors, individual accounts for which the Contractor has to furnish is Bank Account details such as Account Number…………… , Bank……………….., Branch …………………….., RTGS/IFCS Code ……………..etc., Payments will be effected as and when funds received through PAO from finance department under the sanctioned Head of Account. Work wise passed bills along with latest photographs of work with Engineer-In-Charge and Contractor are to be submitted to the PAO, and out of total value of work done, the PAO will release net payable amount to the Contractor’s account through Electronic Clearance System and recoveries such as PS Charges, GST, Seigniorage Charges, income tax, NAC etc., payable to the Division office will be released to the concerned Executive Engineer through Electronic Clearance System. Copy of the bills sent to Chief Engineer/Managing Director, APEWIDC for monitoring the payments.

42.2	Payment for the work done by the contractor will be made for the finished work based on the measurements recorded in measurement books by an officer of the department not lower in rank than an Sub Engineer and check measured by any officer not lower in rank than a Deputy Executive Engineer. The measurement shall be recorded at various stages of the work done and also after work is completed. The contractor shall be present at the time of recording of each set of measurement and their check measurement and accept them then and there so as to avoid disputes at a later stage. If the contractor is not available at the work spot at the time of recording measurements or check measurements the particulars of measurements shall be signed by the authorised agent of contractor based on which the contractor shall accept the set of measurements without any further dispute. If for any reason the contractor’s authorised agent is also not available at site when the department decides to suspend the work recording of measurements in the absence of the contractor or his authorised representative the department shall not entertain any claim from the contractor for any loss incurred by him on this account.  The contractor shall however note that the department cannot indefinitely wait for recording the measurement due to the absence of the contractor and his authorised agent and check measure them even in the absence of the contractor.

42.3	The actual volume of stone and aggregates shall be computed after deducing the following percentages from the volume computed by stack measurements.

| Sl. No | Standard size of aggregate and stone | Percentage reduction in volume computed by stack measurements to arrive at the volume to be paid for |
| --- | --- | --- |
| 1. 2. 3. 4. 5. | Stone and 65mm metal 40 mm and 25 mm 20 mm, 12 mm, 10 mm & 6 mm Fine aggregate Gravel | 20 10 5 Nil 5 |

[Note: The above table may be modified depending on the type of work]

Unless otherwise directed, measurements shall not be taken until sufficient materials for use on work have been collected and stacked. Immediately after measurement, the stack shall be marked by white wash or other means as directed by the Engineer-in-Charge.

42.4	Payments and certificates:

42.4.1.	Payments shall be adjusted for recovery of advance payments, liquidated damages in terms of bid conditions and security deposit for the due fulfilment of the contract.  Payment will be made to the contractor under the certificate to be issued at reasonably frequent intervals by the Engineer-in-Charge, and intermediate payment will be the sum equal to 92½% of the value of work done as so certified and balance of 7½% will be withheld and retained as security for the due fulfilment of the contract under the certificate to be issued by the Engineer-in-Charge. On completion of the entire works the contractor will receive the final payment of all the moneys due or payable to him under or by virtue of the contract except earnest money deposit retained as security and a sum equal to 2½ percent of the total value of the work done. The amount withheld from the final bill will be retained under deposits and paid to the contractor together with the earnest money deposit retained as security after a period of 24 Months as all defects shall have been made good according to the true intent and meaning there of.

42.5.2	In case of over payments or wrong payment if any made to the contractor due to wrong interpretation of the provisions of the contract, APSS or contract conditions etc., such unauthorised payment will be deducted in the subsequent bills or final bill of the work or from the bills under any other contracts with the Government/Corporation or at any time there after from the deposits available with the Government/. Corporation

42.5.3	Any recovery or recoveries advised by the Government department either state or central, due to non-fulfilment of any contract entered into with them by the contractor shall be recovered from any bill or deposits of the contractor.

42.5.4	No claim shall be entertained, if the same is not represented in writing to the Engineer-in-Charge within 15 days of its occurrence.

42.5.5	The contractor is not eligible for any compensation for inevitable delay in handing over the site or for any other reason.  In such case, suitable extensions of time will be granted after considering the merits of the case.

42.6	Intermediate payments:

42.6.1	For intermediate stage of work, only part rates as fixed by the Engineer-in-Charge will be paid.

42.6.2	Part rates shall be worked out for the work done portion based on the actual operations involved keeping in view the value of the balance work to be done, to avoid unintended benefit to the contractor in initial stage.

42.6.3	Full rate shall be paid when the work is completed to the full profile as noted in 	the   drawings.

42.6.4	For earthwork in cutting, 10% of the quantity will be withheld for intermediate payments and the same will be released after completing the work to the profiles as per drawings and disposal of the spoil material at the specified places and handing over the balance useful stone. For this purpose, a length of 25 mt will be taken as a unit (for road works only).

42.6.5	For earthwork, embankment formation work, 10% of the quantity will be withheld for intermediate payments and the same will be released after completing the bund to the profiles as per drawings including trimming of side slopes and all other works contingent to the bund profile. For this purpose, 25 mt of length will be taken as a unit (for road works only).

42.6.6	For the structural works either with masonry or concrete where the height of structure is more than three meters, the quantities executed in the lower level will be withheld at the rate of one percent for every three meters height, if the balance height of the structure work is more than three meters in being over the 	executed level and the same will be released only after the entire work is  	completed as certified by the Engineer-in-Charge  (for road works only).

42.6.7	For C.M & C.D works and for lining works, spread over more than 2 Km in length 	5 percent of the concrete and masonry quantities will be withheld and the same will be released after completion of all C.M & C.D works and lining for the entire length certified by the Engineer-in-Charge (for road works only).

42.6.8	Where payment is intended for aggregates by bill of quantities item based on stack measurements, 10% of the quantity measured will be withheld. No payment or advance will be made for unfixed materials when the rates are for 	finished work in site (for road works only).

42.6.9	The contractor shall supply as built drawings drawn to scale in 5 sets along with original tracings within 28 days of the issue of certificate of completion of work failing which an amount of Rs.20,000/- per each component Work will be withheld from the amounts due to the contractor.

| - A list of payments and deductions from bills |  |  |  |  |
| --- | --- | --- | --- | --- |
| Nature of contract Class of bill Amount of payment Nature of Deduction Refund or deduction |  |  |  |  |
| (1) (2) (3) (4) (5) |  |  |  |  |
| Piece work contract -do- | Intermediate Bill Final Bill | (i) Total value of work done, if it is less than 20 times earnest money. (ii) Total value of work done less amount if any withheld for proper maintenance (L.S.) Contract. | Nil 5% of value of work in excess of 20 times earnest money to be held as security. To be credited to deposit only for the withheld amount excess Rs. 500/-. A suitable amount at the discretion of the Engineer for the proper maintenance. | Nil To be refunded after final bill or deposit as stated in, otherwise to be refund in the final bill itself. To be refunded after expiry of the maintenance period of three months. |
| L.S. contract (supply of materials only) -do- | Intermediate Bill Final Bill | 90% of the value of work Total value of work done | 10% of value towards security. Nil | Nil The 10% value withheld towards security to be refunded after expiry of Guarantee period. |
| L.S. contract (Supply of materials and constructions) -do- | Intermediate Bill Final Bill | 92 ½% of value or work done. 92 ½% of value of work done less amount if any with held for proper maintenance/rectifications. | 7½% of value towards security. 7½% of value towards security. | Nil 1) 5% out of 7½% so far collected from bills to be refunded in final bill. 2) Balance 2 ½% to be refunded on expiry of defects liability period or on rectification of any defects that appears during the defects liability period whichever is later 3)The E.M.D. collected at the time of entering into agreement is also returnable along with item (2) above. |

No payment will be made for the supply of materials at site. Payment will be made for finished item of work executed as per agreement specifications and conditions.

- Interest on money due to the contractor:

43.1	No omission by the Executive Engineer or the Sub Divisional Officer to pay the amount due upon certificates shall vitiate or make void the Contract, nor shall the contractor be enttitled to interest upon any guarantee fund. Payments in arrears, resulting due to omissions of petty items. Discrepancies and errors in calculations or upon any balance whtich may in the final settlement of his accounts shall not carry any interest.

- Certificate of completion of works:

44.1	Certificate of completion of works:

44.1.1	When the whole of the work has been completed and has satisfactory passed any final test that may be prescribed by the contract, the contractor may give a notice to that effect to the Engineer-in-Charge accompanied by an undertaking to carryout any rectification work during the period of maintenance, such notice and undertaking shall be in writing and shall be deemed to be request by the contractor for the Engineer-in-Charge to issue a certificate of completion in respect of the works. The Engineer-in-Charge shall, within twenty one days of the date of delivery of such notice either issue to the contractor, a certificate of completion stating the date on which, in his opinion, the works were completed in accordance with the contract or give instructions in writing to the contractor specifying all the works which, in the Engineer-in-Charge’s opinion, required to be done by the contractor before the issue of such certificate. The Engineer-in-Charge shall also notify the contractor of any defects in the works affecting completion that may appear after such instructions and before completion of the works specified there in. The contractor shall be entitled to receive such certificate of the completion within twenty one days of completion to the satisfaction of the Engineer-in-Charge of the works so specified and making good of any defects so notified.

44.1.2	Similarly, the contractor may request and the Engineer-in-Charge shall issue a certificate of completion in respect of:

a)	Any section of the permanent works in respect of which a separate time for completion 	is provided in the contract, and

b)	Any substantial part of the permanent works which has been both completed to the satisfaction of the Engineer-in-Charge and occupied or used by the Department.

44.1.3	If any part of the permanent works shall have been completed and shall have satisfactorily passed any final test that may be prescribed by the contract, the Engineer-in-Charge may issue such certificate, and the contractor shall be deemed to have undertaken to complete any outstanding work in that part of the works during the period of maintenance.

- Taxes included in the bid:

45.1	The percentage quoted by the bidder is exclusive of GST but inclusive of all 	other taxes, duties on all materials, that the contractor will have to purchase for 	performance of this contract.

- Price adjustment:

Price adjustment is applicable as per conditions of G.O. Ms. No: 62, Dated: 30.11.2021 of the Water Resources (Reforms) Department.

- Retention:

47.1	The department shall retain from each payment due to the contractor @ the rate 	of 7.5% of bill amount until completion of the whole of the Works.

47.2	On completion of the whole of the works 5% of the total amount retained is re-paid to the Contractor and 2 ½% when the Defects Liability Period has passed and the Engineer-in-Charge has certified that all the Defects notified by the Engineer-in-Charge to the Contractor before the end of this period have been 	corrected.

47.3	DELETED (As Per G.O.Ms No. 12, Dated: 11.12.2013 of Finance (W&P) Dept

- Liquidated Damages:

48.1	If for any reason, which does not entitle the contractor to an extension of item, the rate of progress of works, or any section is at any time, in the opinion of the Engineer- In-Charge  too slow to ensure completion by the prescribed time or extended time for completion The Engineer-In-Charge  shall so notify the contractor in writing and the contractor shall there upon take such steps as are 	necessary and the Superintending Engineer may approve to expedite progress so as to complete the works or such section by the prescribed time or extended time. The contractor shall not be entitled to any additional payment for taking 	such steps. If as a result of any notice given by the Engineer-In-Charge  under this clause the contractor shall seek the Engineer-In-Charge s permission to do any work at night or on Sundays, if locally recognised as days of rest, or their 	locally recognised equivalent, such permission shall not be unreasonably refused.

48.2	If the contractor fails to complete whole of the works or any part thereof or

section of the works within the stipulated periods of individual mile stones (including any bonafide extensions allowed by the competent authority without levying liquidated damages), the Engineer-In-Charge  may without prejudice to any other method of recovery will deduct one tenth of one percent of contract value per calendar day or part of the day for the period of delays subject to a maximum of 10% of the contract value not as a penalty from any monies in his hands due or which may become due to the contractor. The payment or deductions of such damages shall not relieve the contractor from his obligation to complete the works, or from any other of his obligations and liabilities under the contract.

48.3	The liquidated damages for the whole of the work are Rs. 1,79,542/- Day (will be 	decided at the time of entering in to agreement)

| For milestone 1 | Rs. 59,847/- | Per day |
| --- | --- | --- |
| For milestone 2 | Rs. 59,847/- | Per day |
| For milestone 3 | Rs. 59,847/- | Per day |

The maximum amount of liquidated damages for the whole of the works is ten percent of final contract price.

The mile stones will be filled at the time of Agreement after obtaining a Program of the work.

- Mobilisation Advance: (Deleted)

- Securities

The earnest money deposit and additional security (for discount bid percentage beyond 25%) shall be provided to the Department not later than the date specified in the letter of acceptance and shall be issued in an amount form or by an irrevocable and unconditional bank guarantee acceptable to the Department. The earnest money shall be valid until a date 28 days from the date of expiry of defects liability period and the additional security shall be valid until a date 28 days from the date of issue of the certificate of completion.

- Cost of repairs:

51.1	Loss or damage to the works or materials to the works between the start date 	and the end of the defects correction periods shall be remedied by the contractor 	at the contractor’s cost if the loss or damage arises from the contractor’s acts or 	omissions.

E.    Finishing the Contract

- Completion:

52.1	The contractor shall request the Engineer-in-Charge to issue a certificate of 		completion of the Works and the Engineer-in-Charge will do so upon deciding 		that the work is completed.

- Taking Over:

53.1	The Department shall takes over the Site and the works within seven days of the Engineer-in-Charge issuing a certificate of completion.

- Final account:

54.1	The Contractor shall supply to the Engineer-in-Charge a detailed account of the 	total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Engineer-in-Charge shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within 56 days of receiving the Contractor’s account if it is correct and complete.  If it is not, the Engineer-in-Charge shall issue within 56 days a schedule that states the scope of the corrections or additions that are necessary.  If the final 	Account is  still unsatisfactory after it has been resubmitted, the Engineer-in-Charge shall decide on the amount payable to the Contractor and issue a 	payment certificate with in 56 days of receiving the Contractor’s revised account.

- Termination:

55.1	The Corporation may terminate the Contract if the contractor causes a 			fundamental breach of the Contract.

55.2	Fundamental breaches of Contract include, but shall not be limited to the 			following:

- The Contractor stops work for 28 days when no stoppage of work is shown on the current program and the stoppage has not been authorised by the Engineer-in-Charge.

- The Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation.

- The Engineer-in-Charge gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Engineer-in-Charge;   and

- The Contractor does not maintain a security which is required and

- The Contractor has delayed the completion of works by the number of days for which the maximum amount of liquidated damages can be paid as defined.

- If the contractor, in the judgement of the Department has engaged in corrupt or fraudulent practices in competing for or in the executing the contract.

- The Contractor has contravened Sub-Clause 5 of Conditions of Contract and sublet the work.

- The Contractor does not adhere to the agreed construction program (Clause 24.1 to 24.4 of Conditions of Contract) and also fails to take satisfactory remedial action as per agreements reached in the management meetings (Clause 31) for a period of 15 days.

- The Contractor fails to carry out the instructions of Engineer-in-Charge within a reasonable time determined by the Engineer-in-Charge.

For the purpose of this paragraph: “corrupt practice” means the offering, giving, receiving or soliciting of anything of value to influence the action of a public official in the procurement process or in contract execution.  “Fraudulent practice” means a misrepresentation of facts in order to influence a procurement process or the execution of a contract to the detriment to the Government and includes collusive practice among Bidders (prior to or after Bid submission) designed to establish Bid prices at artificial non-competitive levels and to deprive the Government of the benefits of free and open competition.

55.3	Notwithstanding the above, the corporation may terminate the Contract for 	convenience when the contract is for convenience the account will be finalised 	as if the contract is closed and payment will be made to the Contractor after deducting all the amounts as per the terms and conditions and due to the APEWIDC.

55.4	If the Contract is terminated, the Contractor shall stop work immediately, make 		the Site safe and secured leave the Site as soon as reasonably possible.

- Payment upon termination:

56.1	If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Engineer-in-Charge shall issue a certificate for the value of the work done less advance payments received upon the date of the issue of the certificate, less other recoveries due in terms of the Contract, less taxes due to be deducted at source as per applicable law and less the percentage to apply to the work not completed.   Additional Liquidated Damages shall not apply.  If the total amount due to the Department exceeds any payment due to the Contractor the difference shall be a debt payable to the Corporation.

- Property:

57.1	All materials on the Site, Plant, Equipment, Temporary Works and Works are 			deemed to be the property of the Corporation if the Contract is terminated because of

Contractor’s default.

- Release from performance:

58.1	If the Contract is frustrated by the outbreak of war or by any other event entirely outside the control of either the Corporation or the Contractor the Engineer-in-Charge shall certify that the contract has been frustrated.  The Contractor shall 	make the site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all works carried out before receiving it and for any work carried out after wards to which commitment was made.

F.    Special Conditions

- Water Supply:

The Contractor has to make his own arrangements at his own cost for water required for the work and to the colonies and work sites, which are to be established by the Contractor.

- Electrical Power:

The Contractor has to make his own arrangements for drawing electric power from the nearest power line after obtaining permission from the APTRANSCO/Competent authority as applicable at his own cost.  In case of failure of electricity, the Contractor has to make alternative arrangements for supply of electricity by Diesel Generator sets of suitable capacity at place of work.  If the supply is arranged by the Department, necessary Tariff rates shall have to be paid based on the prevailing rates.

The contractor will pay the bills of Electricity Department for the cost of power consumed by him.

The contractor shall satisfy all the conditions and rules required as per Indian Electricity Act 1910 and under rule –45(I) of the Indian Electricity Rules, 1956 as amended from time to time and other pertinent rules.

The power shall be used for bonafide Departmental works only.

60.1	Electric Power for Domestic Supply:

a)	The contractor has to make his own arrangements at his own cost for the supply of electric power for domestic purposes and the charges for this purpose have to be paid by him at the rates as fixed by the APTRANSCO/Competent authority as applicable from time to time.

b)	The contractor will have to make his own arrangements to lay and maintain the necessary distribution lines and wiring for the camp at his own cost.  The layout and the methods of laying the lines and wiring shall have the prior approval of the Engineer-in-Charge. All camp area shall be properly electrified. All lines, streets, approaches for the camp etc., shall be sufficiently lighted for the safety of staff and labour of the contractor, at the cost of the Contractor and it will be subject to the approval of the Engineer-in-Charge.

- Land:

61.1	Land for Contractor’s use:

The contractor will be permitted to use Government land for execution of work. 	The contractor shall have to make his own arrangements for acquiring and clearing the site, levelling, providing drainage and other facilities for labour staff colonies, site office, work-shop or stores and for related activities.  The 	Contractor shall apply to the Department within a reasonable time after the award of the contract and at least 30 days in advance of its use, the details of land required by him for the work at site and the land required for his camp and should any private land which has not been acquired, be required by the contractor for his use.  The same may be acquired by the contractor at his own cost by private negotiations and no claim shall be 	admissible to him on this account.The Engineer-in-Charge reserves the right to refuse permission for use of any government land for which no claim or compensation shall be admissible to the contractor.  The contractor shall, however, not be required to pay cost or any rent for the Government land given to him.

61.3	Surrender of Occupied Land:

(a)	The Government land as here in before mentioned shall be surrendered to the Engineer-in-Charge within seven days, after issue of completion certificate.  Also no land shall be held by the contractor longer than the Engineer-in-Charge shall deem necessary and the contractor shall on the receipt of due notice from the Engineer-in-Charge, vacate and surrender the land which the Engineer-in-Charge may certify as no longer required by the Contractor for the purpose of the work.

(b)	The contractor shall make good to the satisfaction of the Engineer-in-Charge any damage to areas, which he has to return or to other property or land handed over to him for purpose of this work. Temporary structures may be erected by the contractor for storage sheds, offices, residences etc., for non-commercial use, with the permission of the Executive Engineer on the land handed over to him at his own cost.  At the completion of the work these structures shall be dismantled site cleared and handed over to the Executive Engineer.  The land required for providing amenities will be given free of cost from Government lands if available otherwise the contractor shall have to make his own arrangements.

Contractor not to dispose off Spoil etc. :-

The contractor shall not dispose off or remove except for the purpose of fulfilment of this contract, sand, stone, clay ballast, earth, trees and shrubs or other materials obtained in the excavation made or lying on the site of the work, and all such materials and produce shall remain property of the Government. The Department may upon request from the contractor, or if so stipulated in the conditions of the contract allow the contractor to use any of the above materials for the works either free of cost or after payment as may be specifically mentioned or considered necessary during the execution of the work.

- Roads:

In addition to existing public roads and roads Constructed by Government, if any, in work area all additional approach roads inside work area and camp required by the Contractor shall be constructed and maintained by him at his own cost.  The layout design, construction and maintenance etc. of the roads shall be subject to the approval of the Engineer-in-Charge.  The contractor shall permit the use of these roads by the Government free of charge.

It is possible that work at, or in the vicinity of the work site will be performed by the Government or by other contractors engaged in work for the Government during the contract period.  The contractor shall without charge permit the government and such other contractor and other workmen to use the access facilities including roads and other facilities, constructed and acquired by the contractor for use in the performance of the works. The contractor’s heavy construction traffic or tracked equipment shall not traverse any public roads or bridges unless the contractor has made arrangement with the authority concerned.  In case contractor’s heavy construction traffic or tracked equipment is not allowed to traverse any public roads or bridges and the contractor is required to make some alternative arrangements, no claim on this account shall be entertained.

The contractor is cautioned to take necessary precautions in transportation of construction materials to avoid accidents.

- Payment for Camp Construction:

No payment will be made to the contractor for construction, operation and maintenance of camp and other camp facilities and the entire cost of such work shall be deemed to have been included in the bided rate for the various items of work in the schedule of quantities and bids.

- Explosive and fuel storage tanks:

No explosive shall be stored within ½ (half) Km of the limit of the camp sites. The storage of gasoline and other fuel oils or of Butane, Propane and other liquefied petroleum gases, shall confirm to the regulations of Andhra Pradesh State Government and Government of India.  The tanks, above ground and having capacity in excess of 2000 litres, shall not be located within the camp area, nor within 200m of any building.

- Labour:

The contractor shall, make his own arrangements for the engagement of all staff and labour, local or other, and for their payment, housing, feeding and transport.

Labour importation and amenities to labour and contractor’s staff shall be to the contractor’s account.  His quoted percentage shall include the expenditure towards importation of labour amenities to labour and staff;

The contractor shall, if required by the Engineer-in-Charge, deliver to the Engineer-in-Charge a written in detail, is such form and at such intervals as the Engineer-in-Charge may prescribe, showing the staff and the numbers of the several classes of labour from time to time employed by the contractor on the Site and such information in respect of contractor’s equipment as the Engineer-in-Charge may require.

65.1	Transportation of labour:

The contractor shall make his own arrangements at his own cost for the daily transportation of the labour and staff from labour camps/colonies to the work spot and back. No labour or staff of the contractor shall stay at the work spot. No extra payment will be made to the contractor for the above transportation of the labour and his quoted percentage to the work shall include the transportation charges of labour from colonies to work spot and back.

The contractor will at all times duly observe the provisions of employment of children Act  XXVI of 1938 and any enactment or modification of the same and will not employ or permit any person to do any work for the purpose under the provisions of this agreement in contravention of said Act. The contractor here by agrees to indemnify the department from and against all claims, penalties which may be suffered by the department or any person employed by the department by any default on the part of the contractor in the observance and performance of the provisions of the employment of children Act XXVI of 1938 or any enactment or modification of the same.

As per Government memo No.721/Gr.(1)/81-35 Dated: 17/11/1987, the contractor shall obtain the insurance at his own cost to cover the risk on the works to labour engaged by him during period of execution against fire and other usual risks and produce the same to the Executive Engineer concerned before commencement of work.

- Safety measures:

- The contractor shall take necessary precautions for safety of the workers and preserving their health while working in such jobs, which require special protection and precautions. The following are some of the measures listed but they are not exhaustive and contractor shall add to and augment these precautions on his own initiative where ever necessary and shall comply with directions issued by the Executive Engineer or on his behalf from time to time and at all times.

- Providing protective foot wear to workers in situations like mixing and placing of mortar or concrete sand in quarries and places where the work is done under much wet conditions.

- Providing protective head wear to workers at places like under ground excavations to protect them against earth /rock falls.

- Providing masks to workers at granulates or at other locations where too much fine dust is floating about and sprinkling water at frequent intervals by water hoses on all stone crushing area and storage bins abate to dust.

- Getting the workers in such jobs periodically examined for chest trouble due to too much breathing in to fine dust.

- Taking such normal precautions like fencing and lightening in excavation of trenches, not allowing rolls and metal parts of useless timber spread around, making danger areas for blasting providing whistles etc.

- Supply work men with proper belts, ropes etc., when working in precarious slopes etc.

- Avoiding un-insulated and sub standard electrical wire etc., as they would electrocute the works.

- Taking necessary steps towards training the workers concerned on the machinery before they are allowed to handle them independently and taking all necessary precautions in and around the areas where machines hoists and similar units are working.

- Fair wage clause:

1.	The contractor shall pay not less than fair wages to labourers engaged by him on the work.

2.	“Fair” wages means wages whether for time of piecework notified by the Government from time in the area in which the work is situated.

3.	The contractor shall not withstanding the revisions of any contract to the contrary cause to be paid to the labour, in directly engaged on the work including any labour engaged by the sub contractor in connection with the said work, as if the labourers had been directly employed by him.

4.	In respect of labour directly or indirectly employed in the works for the purpose of the contractors part of the agreement the contractor shall comply with the rules and regulations on the maintenance of suitable records prescribed for this purpose from time to time by the Government. He shall maintain his accounts and vouchers on the payment of wages to the labourers to the satisfaction of the Executive Engineer.

5.	The Executive Engineer shall have the right to call for such record as required to satisfy himself on the payment of fair wages to the labourers and shall have the right to deduct from the contract amount a suitable amount for making good the loss suffered by the worker or workers by reason of the “fair wages” clause to the workers.

6.	The contractor shall be primarily liable for all payments to be made and for the observance of the regulations framed by the Govt., from time to time without prejudice to his right to claim indemnity from his sub contractors.

7.	As per contract labour (Regulation and abolition) Act 1970 the contractor has to produce the license obtained from the licensing officers of the labour department along with the tender or at the time of agreement.

8.	Any violation of the conditions above shall be deemed to be a breach of his contract.

9.	Equal wages are to be paid for both men and women if the nature of work is same and similar.

10.	The contractor shall arrange for the recruitment of skilled and unskilled labour local and imported to the extent necessary to complete the work within the agreed period as directed by the Executive Engineer in writing.

- Indemnity bond:

The bidders should submit indemnity bond at the time of the agreement as specified below:

Name of work:  Construction of 208 Houses along with infrastructure and amenities at R.Ganapavaram Village (Colony), Buttaigudem Mandal, Eluru District for Rehabilitaton of the PDFs of Chinturu ITDA.

I, __________________________________, contractor S/o ________________ aged ____________________________ Resident of ______________________ do hereby bind myself to pay all the claims may come (a) under Workmen’s Compensation Act 1933 with any statutory modification there on and rules there under or otherwise for or in respect of any damage or compensation payable in connection with any accident or injury sustained (b) under Minimum Wages Act 1948 (c) under payment of wages Act 1936 (d) under the Contractor Labour (Regulation and Abolition) Act 1970 by workmen engaged for the performance of the business relating to the above contract ie., failing such payment of claims of workmen engaged in the above work, I abide in accepting for the recovery of such claims, effected from any of my assets with the Corporation and with other Government Departments/Corporations.

- Compliance with labour regulations:

During continuance of the contract, the contractor or his agents shall abide at all times by all existing labour enactments and rules made there under, regulations, notifications and bye laws of the State or Central Government or local authority and any other labour law (including rules), regulations, bye laws that may be passed or notifications that may be issued under any labour law in future either by the State or the Central Government or the local authority and also applicable labour regulations, health and sanitary arrangements for workmen, insurance and other benefits. Salient features of some of the major labour laws that are applicable to construction industry are given below. The contractor shall keep the Corporation indemnified in case any action is taken against Corporation by the competent authority on account of contravention of any of the provisions of any act or rules made there under, regulations or notifications including amendments. If the Corporation is caused to pay or reimburse, such amounts as may be necessary to cause or observe, or for non observance of the provision stipulated in the notifications/bye laws/acts/rules/regulations including amendments, if any, on the part of the contractor, the Engineer-in-charge/Corporation shall have the right to deduct any money due to the contractor including his amount of performance security.

The Corporation/Engineer-in-Charge shall also have right to recover from the contractor any sum required or estimated to be required for making good the loss or damage suffered by the Corporation.

The employees of the contractor and his agents in no case shall be treated as the employees of the Corporation at any point of time.

- Salient features of some major labour laws applicable to establishment engaged in buildings and other construction work:

(a)	Workmen compensation Act 1923: The Act provides for compensation in case of injury by accident arising out of and during the course of employment.

(b)	Payment of Gratuity Act 1972: Gratuity is payable to an employee under the Act on satisfaction of certain conditions on separation if any employee has completed 5 years service or more, or on death, at the rate of 15 days wages for every completed year of service. The Act is applicable to all establishments, employing 10 or more employees.

(c)	Employees P.F. and Miscellaneous provision Act 1952: The Act provides for monthly contributions by the Department plus workers @ 10% or 8.33%. The benefits payable under the Act are:

1.Pension or family pension on retirement or death, as the case may be.

2.Deposit linked insurance on the death in harness of the worker.

3.Payment of P.F accumulation on retirement/death etc.,

(d)	Maternity Benefit Act 1951: The Act provides for leave and some other benefits to women employees in case of confinements or miscarriage etc.

(e)	Contract Labour (Regulation & Abolition) Act 1970: The act provides for certain welfare measures to be provided by the contractor to contract labour and in case the Contractor fails to provide, the same are required to be provided by the principal Department by Law. The Principal Department is required to take certificate of registration and the contractor is required to take license from the designated Officer. The act is applicable to the establishments or contractor of principal Department if they employ 20 or more contract labour.

(f)	Minimum wages act 1948: The Department is supposed to pay not less than the minimum wages fixed by appropriate Government as per provisions of the act if the employment is a scheduled employment. Construction of buildings, roads, runways are scheduled employments.

(g)	Payment of wages act 1936:	It lays down as to by what date the wages are to be paid, when it will be paid and what deductions can be made from the wages of the workers.

(h)	Equal remuneration act 1979: The act provides for payment of equal wages for work of equal nature to male or female workers and for not making discrimination against Female employee in the matters of transfers, training and promotions etc.

(i)	Payment of bonus act  11500: The act is applicable to all establishments employing 20 or more employees. The act provides for payment of annual bonus subject to a minimum of 8.33% of wages and maximum of 20% of wages to employees drawing Rs. 3500/- per month or less. The bonus to be paid to employees getting Rs. 2500/- per months or above and up to Rs. 3500/- per month shall be worked out by taking wages as Rs. 2500/- per month only. The act does not apply to certain establishments. The newly set up establishments are exempted for five years in certain circumstances. Some of the state Governments have reduced the employment size from 20 to 10 for the purpose of applicability of this act.

(j)	Industrial disputes act 1947: The act lays down the machinery and procedure for resolution of Industrial disputes, in what situations a strike or lockout becomes illegal and what are the requirements for laying off or retrenching the employees or closing down the establishment.

(k)	Industrial Employment (standing orders) Act 1946: It is applicable to all establishments employing 100 or more workmen (employment size reduced by some of the State and Central Government to 50). The act provides for laying down rules governing the conditions of employment by the Department on matters provided in the act and get the same certified by the designated authority.

(l)	Trade Unions Act 1926: The act lays down the procedure for registration of trade unions of workmen and Departments. The trade unions registered under the act have been given certain immunities from civil and criminal liabilities.

(m)	Child Labour (Prohibition & Regulation) Act 1986: The act prohibits employment of children below 14 years of age in certain occupations and processes and provides for regulation of employment of children in all other occupations and processes, Employment Child Labour is prohibited in building and construction industry.

(n)	Inter State Migrant workmen’s (Regulation of Employment & Conditions of service) Act 1979: The act applicable to an establishment, which employs 5 or more inter state migrant workmen through an intermediary (who has recruited workmen in one state for employment in the establishment situated in another State). The inter state migrant workmen, in an establishment to which this act becomes applicable, are required to be provided certain facilities such  as housing, medical aid, travelling expenses from home up to the establishment and back, etc.

(o)	The Building and Other Construction workers (regulation of employment and conditions of service) act 1996 and the Cess Act of 1996:  All the establishments who carryon any building or other construction work and employs 10 or more workers are covered under this Act.  All such establishments are required to pay cess at the rate not exceeding 2% of the cost of construction as may be modified by the Government.  The Department of the establishment is required to provide safety measures at the building or construction work and other welfare measures, such as canteens, first aid facilities, Ambulance, housing accommodations for workers near the work place etc.  The Department to whom the act applies has to obtain a registration certificate from the registering officer appointed by the Government.

(p)	Factories Act 1948: The act lays down the procedure for approval of plans before setting up a factory, health and safety provisions, welfare provisions, working hours, annual earned leave and rendering information regarding accidents or dangerous occurrences to designated authorities. It is applicable to premises employing 10 person or more with aid of power or 20 or more persons without the aid of power engaged in manufacturing process.

- Liabilities of the contractor:

71.1	Accident relief and workmen compensation:

The contractor should make all necessary arrangements for the safety of 	workmen on the occurrence of the accident, which results in the injury or death 	of any of the workmen employed by the contractor, the contractor shall within 24hours of the happenings of the accident or accidents should be intimated in	writing to the concerned Asst. Engineer/Asst. Executive Engineer of the 	Corporation the act of such accident. The contractor shall indemnify Corporation against all loss or damage sustained by the Corporation resulting directly or indirectly from his failure to give intimation in the manner aforesaid including the penalties or fines if any payable by Corporation as a consequence of Corporation failure to give notice under workmen’s compensation act or otherwise conform to 	the provisions of the said act in regard to such accident.

71.2	In the event of an accident in respect of which compensation may become payable under the workmen’s compensation Act VIII 23 whether by the contractor, by the Government it shall be lawful for the Engineer-in-Charge to retain such sum of money which may in the opinion of the Engineer-in-Charge be sufficient to meet such liability.  The opinion of the Engineer-in-Charge shall be final in regard to all matters arising under this clause.

71.3	The contractor shall at all times indemnify the Corporation against all claims which may be made under the workmen’s compensation act or any statutory modification thereafter or rules there under or otherwise consequent of any damage or compensation payable in consequent of any accident or injuries sustained or death of any workmen engaged in the performance of the business relating to the contractor.

- Contractor’s staff, representatives and labour:

(a)	The contractor shall, at all times, maintain on the works, staff of qualified Engineers, and Supervisors of sufficient experience of similar other jobs to assure that the quality of work turned out shall be as intended in the specifications. The contractor shall also maintain at the works, a Work Manager or sufficient status, experience and office and duly authorise him to deal with all aspects of the day-today work. All communications to any commitments by the Work Manager shall be considered as binding on the Contractor.

(b)	The Contractor shall at all times submit details of skilled and unskilled labour and equipment employed to the Engineer-in-Charge in prescribed proforma as he may require to assess and ensure the proper progress of work.

(c)	If the contractor fails to employ required technical personnel as specified in the agreement, work will be suspended or department will engage required technical personnel and recover the cost from the contractor at penal rate of two times thereof as per the respective SSR rates.

- Accommodation and food:

The contractor should arrange accommodation he needs, at his own cost.  The contractor shall make his own arrangements for supply of food grains, fuel and other provision to his staff and labourers including controlled commodities.

- Relationship:

Contractor shall have to furnish information along with tender, about the relationship he is having with any officer of the Corporation of the rank Sub Engineer and above engaged in the work and any officer of the rank of Sub Secretary and above of the Department of Government of Andhra Pradesh.

- Protection of adjoining premises:

The contractor shall protect adjoining sites against structural, decorative and other damages that could be caused by the execution of these works and make good at his cost any such damages.

- Work during night or on Sundays and holidays:

The works can be allowed to be carried out during night, Sundays or authorised holidays in order to enable him to meet the schedule targets and the work shall require almost round the clock working keeping in view:

- The provisions of relevant labour laws being adhered to:

- Adequate lighting, supervision and safety measures are established to the satisfaction of the Engineer-in-Charge and

- The construction programme given by the Contractor and agreed upon by the Engineer-in-Charge envisages such night working or working during Sundays or authorised holidays.

- Layout of materials stacks:

The contractor shall deposit materials for the purpose of the work on such parts only of the ground as may be approved by the Engineer-in-Charge before starting work. A detailed survey, clearly indicating position and areas where materials shall be stacked and sheds built is to be conducted by the contractor at his own cost and only after obtaining necessary approval of the plan for use of sites by the Engineer-in-Charge, the Contractor can use the sites accordingly.

- Use of blasting materials:

Procurement of blasting materials and its storage is the responsibility of the contractor.  The contractor shall engage licensed blaster for blasting operation. The contractor is to act in accordance with Indian Explosive Act and other rules prevailing, during the execution of work. It is the responsibility of the contractor to see, that works by other agencies in the vicinity are not hampered, in such cases if any claim is made by other agencies that should be borne by the contractor. Carriage of blasting materials from the magazine to the work site is the responsibility of the contractor.

- Plant and equipment:

79.1	The contractor shall have sufficient plant, equipment and labour and shall work 	such hours and shifts as may be necessary to maintain the progress on the work 		as per the approved progress schedule. The working and shifts hours shall 		comply with the Government regulations in force.

79.2	It is to expressly and clearly under stood that contractor shall make his own 	arrangements to equip himself with all machinery and special tools and plant for 	the speedy and proper execution of the work and the Corporation does not 	undertake responsibility towards their supply.

79.3	The Corporation shall supply such of the machinery that may be available on hire basis but their supply cannot be demanded as matter of right and no delay in progress can be attributed to such non-supply of the plant by the Corporation and the department cannot be made liable for any damage to the contractor. The Contractor shall be responsible for safe custody of the Corporation machinery supplied to him (which will be delivered to contractor at the machinery yard at site of work) and he has to make good all damages and losses if any other than fire, wear and tear to bring it to the conditions that existed at the time of issue to the contractor before handing over the same to the Corporation. The hire charges for the machinery handed over to the contractor will be recovered at the rate prevalent at the time of supply. The contractor will have to execute supplemental agreement with Engineer-in-Charge at the time of supply of the machinery.

79.4	The acceptance of Corporation machinery on hire is optional to the contractor.

- Steel forms:

Steel forms should be used for all items involving and use of centering and shuttering shall be single plane without any dents and undulations.

- Inconvenience to public:

The contractor shall not deposit materials at any site, which will cause inconvenience to public. The Engineer-in-Charge may direct the contractor to remove such materials or may undertake the job at the cost of the contractor.

- Conflict of interest:

Any bribe, commission, gift or advantage given, promised or offered by on behalf of contractor or his partner, agent or servant or any one on his behalf to any officer, servant, representatives, agents of Engineer-in-Charge, or any persons on their behalf, in relation to the obtaining or to execution of this, or any other contract with Engineer-in-Charge shall in addition to any criminal liability, which it may occur, subject to the cancellation of this or all other contracts and also to payment of any loss or damage resulting from any such cancellation. Engineer-in-Charge shall then be entitled to deduct the amount, so payable from any money, otherwise due to the contractor under this or any other contract.

- Contract documents and materials to be treated as confidential:

All documents, correspondences, decisions and orders, concerning the contract shall be considered as confidential and/or restricted in nature by the contractor and he shall not divulge or allow access to them by any un-authorised person.

- General obligations of contractor:

84.1	The contractor shall, subject to the provision of the contract and with due care and diligence, execute and maintain the works in accordance with specifications 	and drawings.

84.2	The contractor shall promptly inform the Corporation and the Engineer-in-Charge  of any error, omission, fault and such defect in the design of or specifications for the works which are discovered when reviewing the contract documents or in the 	process of execution of the works.

84.3 	Disputes:

If contractor believes that a decision taken by the Engineer-in-Charge was either outside the authority given to the Engineer-in-Charge by the contract or that the ecision was wrongly taken, the decision shall be referred to the Chief Engineer 	/Technical Expert within 14 days of the notification of the Engineer-in-Charge’s decisions.

84.4	Pending finalisation of disputes, the contractor shall proceed with execution of 	work with all due diligence.

- Security measures:

a)	Security requirements for the work shall be in accordance with the Corporation/Government’s general requirements including provisions of this clause and the Contractor shall conform to such requirements and shall be held responsible for the actions of all his staff, employees and employees of his agents.

b)	All contractors’ employees, representatives and agents shall wear identifications badges provided by the contractor. Badges shall identify the contractor, showing employee’s number and shall be worn at all times while at the site.  Individual labour will not be required to wear identification badges.

c)	All vehicles used by the contractor shall be clearly marked with contractor’s name.

d)	The contractor shall be responsible for the security of the works for the duration of the contract and shall provide and maintain continuously adequate security personnel to fulfil these obligations.  The requirements of security measures shall include, but not limited to maintenance of order on the site, provision of all lighting, fencing, guard flagmen and all other measures necessary for the protection of the works within the colonies, camps and elsewhere on the site, all materials delivered to the site, all persons employed in connection with the works continuously throughout working and non working period including nights, Sundays and holidays for duration of the contract.

e)	Other contractors working on the site concurrently with the contractor will provide security for their own plant and materials.  However, their security provisions shall in no way relieve the contractor of his responsibilities in this respect

f)	Separate payment for provision of security services will not be made and its cost shall   be deemed to have been included in the offer of the bidder.

- Fire fighting measures:

a)	The contractor shall provide and maintain adequate fire fighting equipment and take adequate fire precaution measures for the safety of all personnel in temporary and permanent works and shall take action to prevent damage/destruction by fire of trees, shrubs and grasses.

b)	Separate payment will not be made for the provision of fire prevention measures.

- Provisions of health and sanitation:

The contractor shall implement the sanitary and watch and ward rules and regulations for all forces employed under this contract and if the Contractor fails to enforce these rules, the Engineer-in-Charge may enforce them at the expenses of the Contractor.

The contractor’s special attention is invited to clause 37, 38, 39 and 51 of the preliminary specification to the A.P.S.S. and he is requested to provide at his own expenses the following amenities to the satisfaction of Engineer-in-charge concerned.

87.1	First Aid: At the work site there shall be maintained in a readily accessible place, first aid appliances and medicine including adequate supply of sterilized  dressing and sterilized cotton wool.  The appliance shall be kept in good order.  They shall be placed under the charge of a responsible person, who shall be readily available during working hours.

87.2	Drinking water:

Water of good quality for drinking purpose shall be provided for the worker on a scale of not less than 2 gallons per head per day.

a)	Where drinking water is obtained from an intermittent public water supply each work site shall be provided with a storage tank, where such drinking water shall be stored.

b)	Every water supply storage shall be at a distance of not less than 10 mt from any latrine drain or other source of pollution where water has to be drained.  Any existing well, which is within such proximity of any latrine, drain or other source of pollution, the well shall be properly chlorinated before water is drawn from it for drinking.  All such wells shall be dust and water proof.

c)	A reliable pump shall be fitted to each inner well.  The trap door shall be keep locked and opened only for inspection or cleaning which shall be done at least once a month.

87.3	Washing and bathing place:

Adequate washing and bathing places shall be provided separately for men and women.  Such place shall be keep clean and well drained, bathing or washing should not be allowed in or near any drinking water well.

87.4	Latrine and urinals:

There shall be provided within the area of every work site latrines and urinals in an accessible place to men and women separately. For each of them shall be on the following scales or the scale as directed by Engineer-in-charge in any particular case.

1. Where the No. of persons employed does not exceed 50: 2 Nos

2. Where the No. of persons employed exceeds 50 but does not exceed 100: 3 Nos

3. For every additional 100: 3 Nos

If women are employed, separate latrines and urinals separated from those for men shall be provided on the same scale.

Except in work site provided with water flushed latrines connected with a water borne sewage systems all latrine shall be cleaned at least four times daily and at least twice during working hours and kept in a strict sanitary condition.  The receipt scales shall be tarred inside and outside at least once a year.

The excrete from the latrines shall be disposed off at the contractors expenses in a way approved by the local public health authority.  The contractor shall also employ adequate number of scavengers and conservancy shall to keep the latrines and urinals in a clean condition.

87.5	Shelters during rest:

At he work site there shall be provided free of cost two suitable sheds, one for meals and other for rest for the use of workers.

87.6	Creches:

At every work site at which 50 or more women workers are ordinarily employed there shall be provided two huts of suitable size for use of children under the age of 6 years.  One hut shall be used for infants games and other as a bed room.  The hut shall be constructed on a standard not lower than the following.

    - 1. Thatched roots

    - 2. Mud floors and wall

3. Planks spread over the mud floor and covered with matting.  The use

of huts shall be restricted to children their attendants and mothers

of the children.

87.7 Canteens:

A cook for canteen on a moderate scale shall be provided for the benefit of works if it is considered essential.

87.8	Sheds for the workers:

The contractor should provide at his own expense sheds for housing the workers.  The sheds shall be on a standard not less than the cheap shelter type to have in which the workers in the locality are accustomed.  The sheds are to be in rows with 1.5 Mts., clear space between sheds and 2.5 Mts. clear space between roofs.  If conditions permit, the workers camp shall be laid out in units of 400 persons each unit to have a clear space of 4’ each side.

87.9	Land should be acquired temporarily for storing Contractor’s materials or for 		housing their staff.

The contractor should make his own arrangements for temporary acquisition of 	land required for storing his materials and for the housing of his staff at his own 	expenses.

- Training of personnel:

The contractor, shall, if and as directed by the Engineer-in-Charge provide free of any charge adequate facilities, for vocational training of Government Officers, students, Engineers, supervisors, foremen, skilled workmen etc. not exceeding six in number at any one time on the contractor’s work. The training schemes will be drawn up by the Engineer-in-Charge in consultation with the contractor.

- Ecological balance:

a)	The contractor shall maintain ecological balance by preventing de-forestation, water pollution and defacing of natural landscape.  The contractor shall so conduct his construction operation as to prevent any unnecessary destruction, scarring, or defacing of the natural surrounding in the vicinity of the work.  In respect of the ecological balance, Contractor shall observe the following instructions.

i)	Where unnecessary destruction, scarring, damage or defacing may occur, as result of the operation, the same shall be repaired, replanted or otherwise corrected at the contractor’s expense. The contractor shall adopt precautions when using explosives, which will prevent scattering of rocks or other debris outside the work area. All work area including borrow areas shall be smoothened and graded in a manner to conform to the natural appearances of the landscape as directed by the Engineer-in-Charge.

ii)	All trees and shrubbery which are not specifically required to be cleared or removed for construction purposes shall be preserved and shall be protected from any damage that may be caused by the contractor’s construction operation and equipment. The removal of trees and shrubs will be permitted only after prior approval by the Engineer-in-Charge. Special care shall be exercised where trees or shrubs are exposed to injuries by construction equipment, blasting, excavating, dumping, chemical damage or other operation and the contractor shall adequately protect such trees by use of protective barriers or other methods approved by the Engineer-in-Charge. Trees shall not be used for anchorages.  The contractor shall be responsible for injuries to trees and shrubs caused by his operations. The term “injury” shall include, without limitation bruising, scarring, tearing and breaking of roots, trunks or branches. All injured trees and shrubs be restored as nearly as practicable without delay to their original condition at the contractor’s expense.

(iii)	The contractor’s construction activities shall be performed by methods that will prevent entrance or accidental spillage of solid matter contaminants, debris and other objectionable pollutants and wastage into river. Such pollutant and waste include earth and earth products, garbage, cement concrete, sewage effluent, industrial wastes, radio-active substances, mercury, oil and other petroleum products, aggregate processing, mineral salts and thermal pollution. Pollutants and wastes shall be disposed off in a manner and at sites approved by the Engineer-in-Charge.

(iv)	In conduct of construction activities and operation of equipments the contractor shall utilise such practicable methods and devices as are reasonably available to control, prevent and otherwise minimise the air pollution. The excessive omission of dust in to the atmosphere will not be permitted during the manufacture, handling and storage of concrete aggregates and the contractor shall use such methods and equipment as necessary for collection and disposal or prevention of dust during these operation.  The contractor’s methods of storing and handling cement shall also include means of eliminating atmospheric discharges of dust, equipment and vehicles that give objectionable omission of exhaust gases shall not be operated.  Burning of materials resulting from clearing of trees, bushes, combustible construction materials and rubbish may be permitted only when atmospheric conditions for burning are considered favourable.

b)	Separate payment will not be made for complying with the provisions of this clause and all cost shall be deemed to have been included in the unit rates and prices included in the contract if any provision is not complied with within a reasonable time even after issue of a notice in this respect, the necessary operations would be carried out by the Engineer-in-Charge at the cost of the Contractor, Orders of the Engineer-in-Charge in this respect would be final and binding on the contractor.

- Preservation of existing vegetation:

a)	The contractor will preserve and protect all existing vegetation such as trees, on or adjacent to the site which do not unreasonably interfere with the construction as may be determined by the Engineer-in-Charge. The contractor will be held responsible for all unauthorised cutting or damage of trees, including damage due to careless operation of equipment, stockpiling of materials or trekking of grass areas by equipment. Care shall be taken by the contractor in felling trees authorised for removal to avoid any unnecessary damages to vegetation and trees that are to remain in place and to structures under construction or in existence and to workmen.

b)	All the produce from such cutting of trees by the contractor shall remain the property of Government and shall be properly stacked at site, approved by the Engineer-in-Charge. No payment whatsoever shall be made for such cutting and its stacking by the contractor. If any produce from such cutting is not handed over to the Government by the contractor, he shall be charged for the same at the rates to be decided by the Engineer-in-Charge. The recovery of this amount shall be made in full from the intermediate bill that follows.

c)	The contractor shall also make arrangements of fuel deposits for supply of required fuel for the labourer to be employed for cooking purpose at his own cost in order to prevent destruction of vegetation growth in the surrounding area of the work site.

- Possession prior to completion:

The Engineer-in-Charge shall have the right to take possession of or use any completed part of work or works or any part there of under construction either temporarily or permanently. Such possession or use shall not be deemed as an acceptance of any work either completed or not completed in accordance with the contract with in the interest of Clause 28 of APSS except where expressly otherwise specified by the Engineer-in-Charge.

- Payment upon termination:

If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Engineer-in-Charge shall issue a certificate for the value of the work done less advance payments received upon the date of the issue of the certificate, less other recoveries due in terms of the Contract, less taxes due to be deducted at source as per applicable law and the percentage to apply to the value of the work not completed representing additional cost for completing the works at the rate of 20 percent of balance work. Additional Liquidated Damages shall not apply. If the total amount due to the Department exceeds any payment due to the Contractor the difference shall be a debt payable to the Corporation.  In case of default for payment within 28 days from the date of issue of notice to the above effect, the contractor shall be liable to pay interest at 12% per annum for the period of delay.

- Access to the contractor’s books:

Whenever it is considered necessary by the Engineer-in-Charge to ascertain the actual cost of execution of any particular extra item of work or supply of the plant or material on which advance is to be made or of extra items or claims, he shall direct the contractor to produce the relevant documents such as payrolls, records of personnel, invoices of materials and any or all data relevant to the item or necessary to determine its cost etc. and the contractor shall when so required furnish all information pertaining to the aforesaid items in the mode and manner that may be specified by the Engineer-in-Charge.

- Drawing to be kept at site:

One copy of the drawings furnished to the contractor shall be kept by the contractor on the site and the same shall at all reasonable time be available for inspection and use by the Engineer-in-Charge and the Engineer-in-Charge’s representative and by any other persons authorised by the Engineer-in-Charge in writing.

- b.i.s [i.s.i.] books and apss to be kept at site:

A complete set of Indian Standard specification referred to in “Technical Specifications” and A.P.S.S. shall be kept at site for reference.

- Site order book:

An order book shall be kept at the site of the work. As far as possible, all orders regarding the work are to be entered in this book. All entries shall be signed and dated by the Department Officer in direct charge of the work and by the contractor or by his representative. In important cases, the Executive Engineer or the Superintending Engineer will countersign the entries, which have been made. The order book shall not be removed from the work, except with the written permission of the Executive Engineer.

- Variations by way of modification, omissions or additions:

For all modifications, omissions from or additions to the drawings and specifications, the Engineer-in-Charge will issue revised plans, or written instructions, or both and no modification, omission or addition shall be made unless so authorised and directed by the Executive Engineer in writing.

The Engineer-in-Charge shall have the privilege of ordering modifications, omission or additions at any time before the completion of the work and such orders shall not operate to annul those portions of the specifications with which said changes do not conflict.

Engineer-in-Charge’s decision:

It shall be accepted as inseparable part of the contract that in matters regarding materials, workmanship, removal of improper work, interpretation of the contract drawings and contract specification, mode of the procedure and the carrying out of the work, the decision of the Engineer-in-Charge, which shall be given in writing shall be binding on the contractor.

- Care and diversion of river/stream:

The contractor shall submit details regarding the diversion and care of river or stream during construction of the work along with a separate print-out of the time table showing earliest and latest start and finish dates of various activities.  He should submit a detailed layout plan with drawings for the diversion and care of river during construction of work.  The above arrangements shall be at contractor’s cost.

- Income tax:

a)	During the currency of the contract deduction of Income Tax at 2.24% or amended from time to time shall be made from the gross value of each bill of the contract, the contract value of which is in excess of Rs. 20,000/- for deduction of tax at rates lower than 2.24% procedure stipulated under section 194-C(4) of Income Tax Act, 1961 shall be followed.

b)	Income Tax clearance certificate should be furnished before the payment of final bill.

c)	The contractor’s staff, personnel and labour will be liable to pay personnel income taxes in respect of their salaries and wages as are chargeable under the laws and regulations for the time being in force, and the contractor shall perform such duties in regard to such deductions thereof as may be imposed on him by such laws and regulations.

- Seigniorage charges:

100.1	Seigniorage charges will be added and recovered as per G.O Ms No. 100, 		Industries and commerce (M.I) Department Dated: 31.10.2015 from the work 		bills of the contract based on the theoretical requirement of materials at the 		following rates:

| Sl. No | Material | Seigniorage charges |
| --- | --- | --- |
| 1. 2. 3. 4. 5. 6. 7. 8. 9. | Sand Metal R.R stone for masonry Revetment stone C.R.S. stone Gravel/ Earth Bricks Flooring stone (colour) Marble stone | Rs. 100.00/Cum Rs. 90.00/Cum Rs. 90.00/Cum Rs. 90.00/Cum Rs. 90.00/Cum Rs. 30.00/Cum Rs. 8000/kiln/Annum Rs. 120.00/10 Sqm Rs. 300.00/MT |

100.2	The seigniorage charges are to be added and recovered as provided in the 		agreement. Any escalation in these charges beyond the provisions of the 			agreement is to be borne by the department debiting such escalated amount to 		the works estimate concerned.

- GST :

101.1	The percentage quoted by the contractor is exclusive of GST but inclusive of 		other taxes on all materials that the contractor will have to purchase for 			performance of this contract.

101.2	GST component loaded in Part ‘B’ of the estimate shall be added in each bill of 		the contractors who opt for composition scheme and recovered.

101.3	In respect of those contractors, who do not opt for composition scheme, the GST 	component loaded in the estimate shall not be released to them with their bills. 	However, GST loaded in Part ‘B’ of the estimate shall be recovered and for the 		recovery made a deduction certificate shall be issued, based on which they have 		to claim adjustment through their returns submitted to their respective assessing 		authorities.

101.4	As per A.P GST Act 2017, during the currency of the contract, GST as applicable of the total value of the contract will be deducted from the bills of the contractor.

101.5	The contractor should produce a valid GST Clearance Certificate before the 	payment of the final bill, otherwise payment to the contractor will be withheld.

- a) Supply of construction materials:

i)	The contractor has to make his own arrangements for procurements, 	supply and use of construction materials.

ii)	All materials so procured should confirm to the relevant specifications 	indicated in the bidding documents.

iii)	The contractor shall follow all regulations of the Corporation/Government of India in respect of import licences etc., if the procurement of the materials is through imports and he shall be responsible for the payment of applicable duties and taxes, port clearances, inland transportation etc.

iv)	The contractor shall make his own arrangements for adequate storage of the materials.

b) Cess: DELETED

c) Any other special conditions applicable to the work put to bid:

i)  The contractor will not have any right for claiming any interest for the delays in payments if any that occurs during execution due to administrative reasons.

ii)  The delay or non payment of part bills cannot be a reason or alibi for the contractor to slow down/stop the work. In other words the essence of contract remains the completion of the work within the stipulated time not withstanding anything regarding timing of the payments.

iii)  Sand is to be procured for the work as per Govt G.O.No: 43, Dt: 08.07.2024 of the Industries and Commerce (MINES-III) Department i.e as per free sand policy of the Govt., at the concerned reaches fixed by the District Collector and receipt for procurement shall be accompanied with the bills.

iv)  The entire work is to be completed and handed over to user within 12 Months period only.

- APEWIDC is a nodal agency and execute the works on behalf of the user department and payments are made at intermediate stage/ on completion of the work subject to release of funds by the user department.

TECHNICAL SPECIFICATIONS

[INCORPORATED AS PER REQUIREMENT OF THE WORK PUT TO BID WITH THE RELEVANT SPECIFICATION AND NUMBER OF AP STANDARD SPECIFICATION/SPECIAL SPECIFICATION

STANDARD SPECIFICATION FOR BUILDING WORK (AS PER A.P.S.S)

All the items of work shall be executed as per the Standard Specifications laid down in APSS, the relevant I.S Codes of the Special Specification as indicated in Schedule - 'A' of the tender.

| Sl. No | Name of the specification | Specification No. of APSS |
| --- | --- | --- |
| 1 | 2 | 3 |
| 1. | STANDARD SPECIFICATION FOR MATERIALS |  |
| 1.01 | General | 101 |
| 1.02 | Common Burnt Clay Brick | 102 |
| 1.03 | Broken Brick | 103 |
| 1.04 | Surki | 104 |
| 1.05 | Fly Ash | 105- |
| 1.06 | Rough Stones for dry packed Revetments and aprons | 106 |
| 1.07 | Stone for Masonry | 107 |
| 1.08 | Broken Stone/Coarse Aggregate for Concrete | 108 |
| 1.09 | Marble | 109 |
| 1.10 | Sand | 110 |
| 1.11 | Lime | 111 |
| 1.12 | Portland Cement of not less than '43' glade | 112 |
| 1.13 | Lime Mortar | 113 |
| 1.14 | Surki Mortar | 114 |
| 1.15 | Cement Mortar | 115 |
| 1.16 | Cement Lime Mortar | 116 |
| 1.17 | Sebara Putty (Lime Putty) | 117 |
| 1.18 | Pan Tiles | 118 |
| 1.19 | Burnt Clay Flat Terracing Tiles | 119 |
| 1.20 | Clay Roofing Tiles, Mangalore pattern | 120 |
| 1.21 | Glazed Tiles | 121 |
| 1.22 | Bitumen Felts for Water Proofing and Damp Proofing | 122 |
| 1.23 | Cuddapah/Shahbad Slabs | 123 |
| 1.24 | Galvanized Steel Sheets (Plain and Corrugated) | 124 |
| 1.25 | Un-reinforced Corrugated Asbestos Cement sheets | 125 |
| 1.26 | Steel for Reinforcement | 126 |
| 1.27 | Steel for Structural Work | 127 |
| 1.28 | Asbestos Cement Flat Sheets | 128 |
| 1.29 | Water | 129 |
| 1.30 | Teak Wood | 130 |
| 1.31 | Bamboos | 131 |
| 1.32 | Ballies | 132 |
| 1.33 | Steel Sheets piling Sections | 133 |
| 1.34 | Bitumen Emulsion for Roads (Anionic Type) | 134 |
| 1.35 | Cut back Bitumen | 135 |
| 1.36 | Paving Bitumen | 136 |
| 1.37 | Coal Tar Pitch | 137 |
| 2. | STANDARD SPECIFICATIONS FOR CLEARING SITE, DISMANTLING BUILDING AND OTHER STRUCTURES AND BLASTING |  |
| 2.01 | Clearing Site | 201 |
| 2.02 | Dismantling of Buildings and other Structures | 202 |
| 2.03 | Blasting | 203 |
| 3. | STANDARD SPECIFICATIONS FOR EARTH WORK |  |
| 3.01 | Excavation and Forming un compacted banks | 301 |
| 3.02 | Embankment compacted by other than driven equipment | 302 |
| 3.03 | Embankment compacted by power driven equipment | 303 |
| 3.04 | Clay blankets | 304 |
| 3.05 | Filters | 305 |
| 3.06 | Rock-fill in toe of embankment | 306 |
| 3.07 | Turfing | 307 |
| 3.08 | Excavation of foundation | 308 |
| 3.09 | Filling in foundations | 309 |
| 3.10 | Filling in Basement | 310 |
| 3.11 | Well sinking for foundations | 311 |
| 3.12 | Well sinking for Water Supply | 312 |
| 3.13 | RCC Precast and Cast-in-situ pile foundations | 313 |
| 4. | STANDARD SPECIFICATIONS FOR CONCRETES |  |
| 4.01 | lime Concrete and surki concrete | 401 |
| 4.02 | Cement Concrete for plain and reinforced works. | 402 |
| 4.03 | Reinforced cement concrete work | 403 |
| 4.04 | Repair grouting to aprons and revetments with surki Concrete and pointing with surki mortar | 404 |
| 4.05 | Prestressed concrete work. | 405 |
| 5. | STANDARD SECIFICATIONS FOR BRICK MASONRY |  |
| 5.01 | Brick Masonry-General | 501 |
| 5.02 | Brick in Lime Mortar | 502 |
| 5.03 | Brick in Surki Mortar | 503 |
| 5.04 | Brick in Cement Mortar | 504 |
| 5.05 | Brick in Cement Lime Mortar | 505 |
| 5.06 | Brick in clay | 506 |
| 5.07 | Brick Arch work | 507 |
| 5.08 | Brick in Honey Comb work | 508 |
| 5.09 | Reinforced half-brick partition walls | 509 |
| 5.10 | Boiler Brick works | 510 |
| 5.11 | Honey Comb works with white washed pan tiles | 511 |
| 5.12 | Brick Nogging | 512 |
| 6. | STANDARD SPECIFICATIONS FOR STONE MASONRY |  |
| 6.01 | Stone Masonry-General | 601 |
| 6.02 | Cut stone in Lime Mortar | 602 |
| 6.03 | Cut stone in Surki Mortar | 603 |
| 6.04 | Cut stone in Cement Mortar | 604 |
| 6.05 | Cut stone-Rock Rustic or quarry faced in mortar | 605 |
| 6.06 | Cut stone string course and other cornice etc. in mortar | 606 |
| 6.07 | Cut stone arch work | 607 |
| 6.08 | Rubble arching | 608 |
| 6.09 | Coursed Rubble in Lime Mortar (1 st sort) | 609 |
| 6.10 | Coursed Rubble in Surki Mortar (1 st sort) | 610 |
| 6.11 | Coursed Rubble in Cement Mortar (1 st sort) | 611 |
| 6.12 | Coursed Rubble in Mortar (2nd sort) | 612 |
| 6.13 | Uncoursed Rubble or random rubble in lime mortar | 613 |
| 6.14 | Random Rubble in surki mortar | 614 |
| 6.15 | Random Rubble in Cement Mortar' | 615 |
| 6.16 | Random Rubble in Clay | 616 |
| 6.17 | Dry stone masonry (for retaining wall) | 617 |
| 6.18 | Damp proof (or any proof) course with Shahabad stone/Cuddapah stone 50mm thick in cement mortar 1:3 | 618 |
| 6.19 | Rough stone dry packing for aprons and revetment | 619 |
| 6.20 | Laterite or rough stone pitching for fiver conservancy works | 620 |
| 6.21 | Moorum back to rough stone dry packing and gravelling to top and side slopes of bunds 150 mm thick | 621 |
| 7. | STADARD SPECIFICATIONS FOR FLOORING GENERAL |  |
| 7.01 | Flooring General | 701 |
| 7.02 | Flooring with Shahabad/Cuddapah slabs | 702 |
| 7.03 | Flooring with polished Shahabad/Cuddapah slabs | 703 |
| 7.04 | Flooring with Cement Mortar (1 :3) 12mm thick | 704 |
| 7.05 | Flooring with coloured cement mortar (1 :3),12mm thick | 705 |
| 7.06 | Terraced flooring with brick on edge, 75mm thick broken brick aggregate concrete and 12mm thick cement plastering (1 :3) on top | 706 |
| 7.07 | Flooring with Glazed Tiles | 707 |
| 7.08 | Flooring with in-situ Terrazzo finish | 708 |
| 7.09 | Flooring with Cement Tiles (A) plain or coloured (B) Terrazzo (C) Chequered or embossed | 709 |
| 7.10 | In-situ-Granolithic concrete flooring | 710 |
| 8. | STANDARD SPECIFICATIONS FOR ROOFING AND CEILING |  |
| 8.01 | Roofing with pan tiles set mortar over flat tiles with lime mortar borders including reepers | 801 |
| 8.02 | Roofing with pan tiles and lime mortar borders including reepers | 802 |
| 8.03 | Roofmg with Mangalore tiles set in mortar over flat tiles and including reepers | 803 |
| 8.04 | Roofing with Mangalore tiles including reepers | 804 |
| 8.05 | Roofing with Mangalore tiles over ceiling tiles with air spaces and including reepers | 805 |
| 8.06 | Madras terraced roofing with brick on edge 75mm thick broken brick aggregate concrete three courses flat tiles and three coats of lime plaster to top and bottom | 806 |
| 8.07 | Madras terraced roofing with brick on edge, 75mm thick broken brick aggregate concrete three courses of flat tiles and three coats of lime plaster to top and one coat of 12mm thick cement plaster (1 :3) to bottom | 807 |
| 8.08 | Terraced roofing with brick on edge, 75mm thick broken brick aggregate concrete two courses of flat tiles to top and one coat of cement plaster (1 :3) to bottom | 808 |
| 8.09 | Weather proof course for reinforced cement concrete roofing with Lime broken brick aggregate concrete and two courses of flat tiles | 809 |
| 8.10 | Water proof course for reinforced cement concrete roofing with two courses of flat tiles | 810 |
| 8.11 | Complete surface repair to leaky lime plastered terrace roof | 811 |
| 8.12 | Water proofing of concrete and masonry (flat or sloping) roofs with Bitumen felts Normal treatment | 812 |
| 8.13 | Water proofing of concrete and masonry (flat or sloping) roofs with Bitumen felts Heavy treatment | 813 |
| 8.14 | Roofing with corrugated galvanized steel sheets | 814 |
| 8.15 | Roofing with corrugated asbestos cement sheets | 815 |
| 8.16 | Roofing with semi-corrugated asbestos cement sheets | 816 |
| 8.17 | False ceilings | 817 |
| 9. | STANDARD SPECIFICATION FOR PLASTERING, POINTING, WHITE WASHING, COLOUR WASHING, DISTEMPERING AND WATER PROOF CEMENT PAINING ETC. |  |
| 9.01 | Plastering General | 901 |
| 9.02 | Plastering with time mortar one coat, 12mm thick, including fine Rendering | 902 |
| 9.03 | Plastering with cement mortar, one coat 12mm or 20mm thick including fine rendering | 903 |
| 9.04 | Plastering with cement mortar 2 coats 20mm thick with sponge finish | 904 |
| 9.05 | Plastering with combination mortar, one coat 12mm thick including fine rendering | 905 |
| 9.06 | Pointing to masonry with cement mortar | 906 |
| 9.07 | Pointing to masonry with surki mortar | 907 |
| 9.08 | White-washing | 908 |
| 9.09 | Colour-washing | 909 |
| 9.10 | Dry distempering | 910 |
| 9.11 | Oil bound distempering | 911 |
| 9.12 | Water proof cement painting | 912 |
| 10. | STANDARD SPECIFICATIONS FOR WOOD WORK |  |
| 10.1 | Wood work-General | 1001 |
| 10.2 | Doors, windows, ventilators, ward robes and cup-boards etc., | 1002 |
| 10.3 | Frame work for Roofs | 1003 |
| 10.4 | Wooden Partitions | 1004 |
| 10.5 | Wall Paneling | 1005 |
| 10.6 | Wooden Railing | 1006 |
| 11. | STANDARD SPECIFICATIONS FOR STRUCTURAL STEEL WORK |  |
| 11.01 | Materials | 1101 |
| 11.02 | Steel work in single section of R.S. Joists, Flats, Tees Angles and Channels etc. | 1102 |
| 11.03 | Steel work Riveted and bolted in built-up sections, trusses and framed work | 1103 |
| 11.04 | Steel work (welded) in built-up sections trusses and Framed works | 1104 |
| 11.05 | Miscellaneous Steel work Collapsible steel structures | 1105 |
| 11.06 | M.S.Steel sliding shutters | 1106 |
| 11.07 | M.S. Sheet Doors | 1107 |
| 11.08 | Rolling Shutters | 1108 |
| 11.09 | Clamps for ceiling Fan | 1109 |
| 12. | STANDARD SPECIFICATIONS FOR PAINTING AND VARNISHING |  |
| 12.01 | Painting-General | 1201 |
| 12.02 | Removing old paint with patent paint remover | 1202 |
| 12.03 | Removing old paint with caustic soda solution | 1203 |
| 12.04 | Removing old paint with blow lamp | 1204 |
| 12.05 | Painting with wood preservative | 1205 |
| 12.06 | Coal tarring | 1206 |
| 12.07 | Painting priming coat on wood, iron or plastered surfaces | 1207 |
| 12.08 | Painting with ready mixed paint | 1208 |
| 12.09 | Painting of GI. sheets with ready mixed paint | 1209 |
| 12.10 | Spray painting with flat wall paint on new work including priming coat | 1210 |
| 12.11 | Spray painting with flat wall paint on old work | 1211 |
| 12.12 | Painting with synthetic enamel paint | 1212 |
| 12.13 | Painting with Aluminum paint | 1213 |
| 12.14 | Painting with acid proof paint | 1214 |
| 12.15 | Painting with anti-corrosive bitumanistic paint | 1215 |
| 12.16 | Wall painting with plastic emulsion paint | 1216 |
| 12.17 | Varnishing | 1217 |
| 12.18 | Oiling with raw linseed oil | 1218 |
| 12.19 | Wax polishing with ready made wax polish | 1219 |
| 12.20 | Painting cast iron rain water, soil waste and vent pipes and fittings including priming coal | 1220 |
| 12.21 | Lettering with paint | 1221 |
| 12.22 | French polishing. | 1222 |
| 16. | STANDARD SPECIFICATIONS FOR MISCELLANEOUS |  |
| 16.01 | Bamboo chicks with blue Dungary cloth pulleys, rings, ropes, hools, staples etc., complete including painting two coats. | 1601 |
| 16.02 | Teak wood trellis work for verandahs | 1602 |
| 16.03 | Forming black boards on walls | 1603 |
| 16.04 | Barbed wire for fencing | 1604 |
| 16.05 | Reinforced concrete fence posts | 1605 |
| 16.06 | Fencing with barbed wire or chain link mesh | 1606 |
| 16.07 | Protection of building and altered structures against lighting | 1607 |
| 16.08 | Steel doors, windows and ventilators | 1608 |
| 16.09 | Aluminum doors, windows and ventilators | 1609 |
| 16.10 | Fixing and glazing of metal (steel and aluminum) doors and | 1610 |

SPECIFICATIONS

1.0	PREAMBLE

The technical specifications for various items of work contained herein shall be read in conjunction with the specifications mentioned for each item of work in bill of quantities part-I (Schedule – A) and also plans and drawings in part III.

2.0 	General Technical Specifications

2.1 	The following are the general technical specifications to be adopted for construction of buildings.  Each item of work shall be executed according to the relevant standard specification number as described in the “Andhra Pradesh Standard Specification” (APSS) and Indian Standard (I.S) Specifications, including Water supply, Sanitary and Electrical Installations. In the absence of any definite provisions on any particular item of work in the aforesaid specifications in A.P.S.S., reference may be made to the latest codes and specifications of Indian Standards or Indian Roads congress (IRC in case of Roads). Where even these are silent, the  construction  and  completion  of  works shall conform to sound engineering practice as  approved  by  Engineer-in-charge and in case of dispute  arising  out of the  interpretation of the above, the decision of Engineer-in-charge shall be final and binding on the contractor.

3.0	GENERAL INSTRUCTIONS:

3.1 	Drawings, Instructions, Measurements

All works shall be done according to the detailed drawings and specifications.  Figured dimensions shall be followed.  Measurement shall be taken of the actual work done but shall not exceed those marked on the drawings for payments.

3.2 	Site Clearance and Demolition

The site shall be cleared of all trees, stumps, roots, brush wood, bushes and other objectionable materials.  Useful and saleable material shall be the property of the Owner (A.P.S.F.C.) and shall be stacked properly as directed by the Engineer-in-charge.  The areas to be covered with embankments shall be stripped of top soil to required depths to expose acceptable founding strata.  Top soil unsuitable for use in embankment construction and other fills shall be disposed off as directed.  All combustible materials shall be stacked and burnt in locations sufficiently remote to eliminate all danger of fire hazards.  All old concrete, brick works and drains which interfere with construction works shall be dismantled with the approval of the Engineer-in-charge duly taking all necessary precautions prescribed in safety specification.  Top soil which is suitable for use in construction work shall be stockpiled for later use.  Other objectionable materials such as trash, debris, stones, brick, broken concrete, scrap metal etc., shall be disposed off as directed by the Engineer.  Payment for cutting and removal of trees, stumps, dismantling existing structures and stripping shall be regulated by the description in the Schedule of Items or Section 2 of A.P.S.S.

3.3	Precision: The works shall be set to the highest precision of dimensions, levels, grades and lines as per designs and drawings using precise scientific equipments and measuring instruments.

3.4	Safety Specification:

3.4.1	On every demolition job, danger signs shall be conspicuously posted all-round the structure and all door openings giving access to structure shall be barricaded or marked except during the movement of actual workmen or equipment. However provision shall be made for at least two independent exits for escape of workmen during any emergency.

3.4.2	During night, red lights shall be placed on or about all the barricades.

3.4.3	Where in any work of demolition it is imperative, because of danger existing to ensure that no unauthorized person shall enter the site of demolition outside working hours, a watchman should be employed. In addition to watching the site, he shall also be responsible for maintaining all notices, lights and barricades.

3.4.4	All the necessary safety appliances as per IS: 4130 shall be issued to  the  workers  and  their use explained. It shall be ensured that the workers are using all the safety appliances while at work.

3.4.5	The removal of a member may weaken the side wall of an adjoining structure and to prevent possible damage, these walls shall be supported until such time as permanent protection is provided. In case any danger is anticipated to the adjoining structure the same shall be got vacated to avoid any danger to  human life.

3.4.6	The power on all electrical service lines shall be shut off and all such lines cut or disconnected at or outside the property line, before the demolition work is started.  Prior to cutting of such lines the necessary approval shall be obtained from the electrical authorities concerned for demolition work itself.

3.4.7	All gas, water, steam and other service lines shall be shut off and capped or otherwise controlled at or outside the building line, before demolition work  is started.

3.4.8	All the mains and meters of the building shall be removed or protected from damage.

3.4.9	If a structure to be demolished has been partially wrecked by fire, explosion or other catastrophe, the walls and damaged roofs shall be shored or braced suitably.

3.4.10	Walkways and passageways shall be provided for the use of the workman who shall be instructed to use them and all such walkways and passageways shall be kept adequately lighted, free from debris and other materials.

3.4.11	All nails in any kind of lumber shall be withdrawn, hammered or bent over as soon as such lumber is removed from the structure being demolished, and placed in pipes for future cleaning or burning.

3.4.12	All the roads and open area adjacent to the work site shall either be closed or suitably protected.

3.4.13	No electric cable or apparatus which is liable to be a source  of  danger or a cable or apparatus used by the operator shall remain electricity charged.

3.4.14	All practical steps shall be taken to prevent danger to persons employed from risk of fire or explosion or flooding. No floor, roof or other part of the building shall be so overloaded with debris or materials as to render it unsafe.

3.5	Quality of work:

To be the best quality: All the materials, workmanship, articles, Equipment, tools and plants should be of high and acceptable quality conforming to the standard specifications.

All materials shall be new and of the kinds and qualities described in the contract.

3.6	Testing of works and materials

3.6.1	All materials used and works done shall be subject to approval of the Engineer-in-charge.

3.6.2	The contractor shall arrange sufficiently in advance to test materials and portions of works in order to prove their soundness and efficiency if required, including samples and supporting test results from the approved laboratory and other documentary evidence from the manufacturer, wherever applicable, and indicate the types of materials and their respective sources.  The delivery of materials at site shall commence only after the approval of the quality, grading and sources of the materials by the Engineer-in-charge.

3.6.3	The quality of all materials approved shall be maintained throughout the period of construction and periodical tests shall be carried out to ensure that it is maintained. The contractor shall conduct tests at work site/approved laboratories and shall maintain test reports at site for cement, coarse aggregates, fine aggregates, water, steel, bricks and concrete at the following frequency :-

| Sl. No. |  | Description of material | Frequency of test |  | Allowable limits |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  | Cement : (IS : 8112-1989) a) Fineness | One for each source of supply in a month |  | Shall not be less than 3500 sqcm / gm |  |
|  |  | b) Setting time | -do- |  | Initial setting time shall not be less than 30 minutes and final setting time shall not be more than 60 minutes. |  |
|  |  | c) Soundness | -do- |  | Expansion (unaerated) shall be not more than 10mm by “Le Chatelier” method; if it fails, expansion of aerated sample shall be not more than 5 mm. |  |
|  |  | d) Compressive strength of cement mortar cubes 1:3 (1 cement :3 standard sand) by mass | -do- |  | Compressive strength for 7 days shall not be less than 330 kg/cm2 and compressive strength for 28 days shall not be less than 430 kg/cm2 |  |
| 2. |  | Coarse aggregate : (IS383-1970) a) Gradation b) Aggregate impact value | One test for 15 Cum or at least on the day of concrete if concrete quantity is less than 15 cum. Once for each source of supply or when ever change in texture is noticed. |  | 40mm Metal : a)Seive analysis : -63mm – 100% 40mm-85 to 100% 20mm-0-2-%; 10mm-0.5% b) Flakeness Index : shall be less than 30% by weight 20mm Metal : a)Sieve analysis : -Limits : 40mm – 100%; 20mm-95 to 100%; 10mm-25 to 55%; 4.75-0 to 10% b) Flakiness Index : less than 25% c) Aggregate impact value: 20-40(IS 2386-1963) |  |
| 3. |  | FINE AGGREGATE (IS383 –m1970) a) Gradation for concrete | One test for every 15 cum. |  | Fineness modules : Fine sand limit 2.2 to 2.6 |  |
|  |  | b) Gradation for masonry | At least once on the day of work |  | Medium sand limit 2.6 to 2.9 |  |
|  |  | c) Gradation for finishing | -do- |  | Coarse sand limit 2.9 to 3.2 |  |
|  |  | d) Bulkage | Three for each day of work i.e. morning noon and evening |  | b) Silt Content : shall be less than 4% by weight |  |
|  |  | e) Silt content | At least once on the day of work |  |  |  |
| 4. | WATER : Chemical test |  |  | One test for each source |  | The water quantity shall be as per clause 5.4 of ISI 456-2000. The PH value of water shall not be less than 6. |  |
| 5. | STEEL : (Fe 415/500 (IS1786-1985)) a) 0.2% proof stress |  |  | One for each source of supply and once in six months for fresh supply |  | 4150/5000 kg/cm2 (Minimum) |  |
|  | b) Elongation |  |  | -do- |  | Percentage of elongation 14.5% minimum |  |
|  | c) Tensile strength |  |  | -do- |  | Ultimate tensile strength 4900 kg/cm2 (Minimum) |  |
|  | d) Weight/RM |  |  | As per B.I.S. |  |  |  |
|  | e) Rebend test |  |  | As per B.I.S |  |  |  |
|  | f) Chemical compositin of Steel |  |  | As per B.I.S. |  |  |  |
| 6. | BRICKS : (IS:1077-1976) a) Compressive strength |  |  | One for each source of supply and once in two months when change in texture is noticed |  | Shall not be less than 40 Kg/cm2 |  |
|  | b) Water absorptionl |  |  | -do- |  | i) Shall not be greater than 20% by weight for clay bricks. ii) For fly ash bricks– As per standards iii) For Aerocon bricks- As per standards |  |
| 7. | CONCRETE : (IS456:2000) a) Cube strength |  |  | Frequency of testing as per clause 15.2 of IS 456-2000 for example 6 cube specimens, 3 each for 7 days & 28 days strength for every 15 cum. Cube shall be prepared, cured and tested in accordance with the requirement of IS 516. |  | a) Compressive strength (7 days) M15-100 Kg/cm2 (Minimum) M20-135 KG.cm2 (Minimum) b) Compressive strength (28 days) M15-150 Kg/cm2 (Minimum) M20-200 Kg/cm2 (Minimum) |  |
|  | b) Slump |  |  | Thrice in a day of concrete in morning, noon and evening |  | a) Foundation footing – 10mm to 25mm b) Column beams and slabs – 25mm to 40mm (with normal reinforcement) c) Beams, slabs – 4 to 50mm (with congested reinforcement) |  |

A Register of record of material testing and Register of daily events showing materials received, labour engaged, out turn of work etc. shall be maintained at site and shall be signed by the contractor or his authorised representative and the Engineer

3.7	Rejection of Materials/works

3.7.1	Any material brought to site which in the opinion of the Engineer is  defective,  sub-standard, damaged, contaminated, deteriorated or does not comply with the requirement of the specification shall be rejected. The contractor shall remove from site such materials within 4 hours of notice from site.

3.7.2	If the work or portion of the work which in the opinion of the Engineer is found to be defective or unsound, the contractor shall pull it down and  re-execute the same work at his own cost.

3.8	Measurement Materials

For the Controlled Concrete where site mixing is permitted shall be with concrete mixtures fitted with weigh batching scale. Materials shall be weighed and batched in mechanical weigh batchers as per the specified proportions of the approved design mix.

Materials requiring Volumetric mixing, wherever permitted, should be measured separately in boxes of appropriate size before being mixed in the specified proportions.

3.9	Storage of Materials

3.9.1	Adequate safe, dry storage shall be provided for all materials particularly cement.

3.10	Codes

3.10.1	Unless mentioned otherwise, current versions of all codes, specifications and standards issued by the Indian Standards Institution and Indian Roads Congress shall be fully applicable to these specifications. In the absence of appropriate publications by ISI or IRC, adoptable specification of the International Organization for Standardization shall apply.

3.10.2	In case of any conflict in meaning between the specifications mentioned hear in and those of ISI or IRC, the provisions of these specifications shall prevail.

3.10.3	The following codes shall be applicable for the purpose.  However the latest revision of these codes shall only be used.

LIST OF SPECIFICATIONS FOR THE VARIOUS ITEMS OF WORKS SUPPLEMENTING THOSE DESCRIBED IN SCHEDULE ‘A’ BY S.S. NUMBERS

GENERAL SPECIFICATIONS

| Sl. No |  | Short title/ Description | IS No. and as amended from time to time |
| --- | --- | --- | --- |
| A) LIST OF INDIAN STANDARDS |  |  |  |
| I. | CEMENT |  |  |
|  | 1 | Specifications for 43 Grade ordinary portland cement | IS 8112:1989 |
|  | 2 | Methods of physical tests for hydraulic comments | IS 4031 (part 1 to 15) :1988 |
|  | 3 | 53 Grade cement | IS 12269:1989 |
| II. | AGGREGATES |  |  |
|  | 1 | Specifications for Coarse and Fine aggregates from Natural resources for concrete | IS 383:1970 |
|  | 2 | Specification for Sand for Masonry | IS 2116:1980 |
|  | 3 | Methods of tests for aggregates for concrete. Part-1 Particle seize and shape | IS 2386:1963 (Part I to IV) |
|  |  | Schedule - B Estimation of deleterious materials & Organic impurities |  |
|  |  | Part-III – Soundness |  |
|  | 4 | Specification for test sieves. Part-I Wire cloth test sieves | IS 460:1978 (Part-I) |
| III. | BRICKS |  |  |
|  | 1 | Specifications for Common burnt clay building bricks | IS 1077:1992 |
|  | 2 | Methods of test for burnt clay building bricks | IS 3495:1992 (Part I to IV) |
|  | 3 | Pulverized Fuel Ash-Lime Bricks - Specification | IS 12894:2002 |
|  | 4 | Specification for concrete masonry units Part 3 Autoclaved cellular Aerated concrete blocks | IS 2185:1984 (Part-III) |
| IV | BUILDING STONES: |  |  |
|  | 1 | Method of Tests for determination of strength properties of natural building stones ( compressive strength, Transverse strength, Tensile Strength, Shear Strength. | IS 1121 (Part –1 to Part 4): 1974 |
|  | 2 | Schedule of properties and availability of stones for construction purposes | IS 7779:1975 (Part 1 to Part 5) |
|  | 3 | Quarrying stones for construction purposes, recommended practice | IS 8381:1977 |
|  | 4 | Stone Masonry: Specifications for dressing natural building stones | IS 1129:1972 (Part-IV) |
| V. | STEEL |  |  |
|  | 1 | Specification of Mild steel and medium tensile steel bars and hard drawn steel wires for concrete reinforcement. Part-I Mild Steel & Medium tensile steel bars | IS 432:1982 (Part I & II) |
|  | 2 | Specifications for Cold-worked steel, High strength deformed steel bars and wires for concrete reinforcement. | IS 1786:1985 |
|  | 3 | Specification for steel for General structural purposes | IS 2062:1999 |
|  | 4 | Specification for structural steel (Standard quality) | IS 226:1975 |
|  | 5 | Specification for steel tubes for structural purposes | IS 1161:1998 |
|  | 6 | Hand Drawn Wire | IS 432:1953 |
| VI | CERAMIC TILES |  | IS 13712:2006 |
| VII | STACKING AND STORAGE OF MATERIALS |  |  |
|  | 1 | Recommendation of stacking and storage of construction materials and components at site | IS 4082:1996 |
| VIII | MASONRY |  |  |
|  | 1 | Brick Masonry | IS 2212:1962 |
|  | 2 | Code of practice for construction of Stone Masonry Part-1 (Rubble stone masonry) | IS 1597:1992 |
|  | 3 | Code of practice for permeability test for masonry (during and after construction) | IS 11216:1985 |
|  | 4 | Code of practice for brick work | IS 2212:1991 |
|  | 5 | Construction of hallow and solid concrete block masonry | IS 2572:2005 |
|  | 6 | Code of practice for construction of autovlaved cellular concrete block masonry | IS 6041:1985 |
| IX | CONCRETE |  |  |
|  | 1 | Code of practice for Plain and reinforced concrete | IS 456:2000 |
|  | 2 | Method of Sampling and analysis of concrete | IS 1199:1959 |
|  | 3 | Method of test for strength of concrete | IS 516:1959 |
|  | 4 | Recommended guide lines for Concrete Mix Design | IS 10262:1982 |
|  | 5 | Code of practice for Ready-Mixed Concrete | IS 4926:2003 |
|  | 6 | Specification for Admixtures for concrete | IS 9103:1999 |
|  | 7 | Guidelines for false work for concrete structures. | IS:14687:1999 |
|  | 8 | Code of practice for use of immersion vibrators for consolidating concrete | IS 3558:1983 |
|  | 9 | Specifications for Pre-cast concrete coping blocks | IS 5751:1984 |
|  | 10 | Laying in situ cement concrete flooring | IS 2571:1970 |
|  | 11 | Code of practice for concrete structures for the storage of liquids | IS 3370: 11500 (Part 1 & 2) IS 3370-1967 (Part 3 & 4) |
|  | 12 | Code of practice for concrete roads | IRC: 15-2002 |
| X | REINFORCEMENT/ STRUCTURAL STEELWORK |  |  |
|  | 1 | Code of Practice for Bending and fixing of bars for concrete reinforcement | IS 2502:1963 |
|  | 2 | Recommendations for detailing of reinforcement in reinforced cement concrete works | IS 5525:1969 |
|  | 3 | Mils steel wire for General Engineering purposes | IS 280:2006 |
|  | 4 | Recommendation for welding of cold worked bars for Reinforced concrete construction | IS 9417:1989 |
|  | 5 | Code of practice for general construction in steel | IS 800:1984 |
|  | 6 | Code of practice for use of metal arc welding for general construction in mild steel | IS 816:1969 |
|  | 7 | Safety code for erection of structural steel work | IS 7205:1974 |
|  | 8 | Tolerance for fabrication of steel structures | IS 7215:1974 |
| XI. | JOINERY: |  |  |
|  | 1 | Specifications for timber paneled and glazed door, window and ventilator shutters | IS 1003-Pat 1-2003 and IS1003-Part2-1994 |
|  | 2 | Specifications for cut size timber | IS 1331:1971 |
|  | 3 | Code of practice for Glazing in Buildings | IS 3548:1988 |
|  | 4 | Specification for aluminium doors, windows and ventilators | IS 1948:1961 |
| XII | EARTH WORK: |  |  |
|  | 1 | Code of Safety for excavation works | IS 3764:1966 |
|  | 2 | Safety code for piling and other deep foundations | IS 5121:1969 |
|  | 3 | Code of practice for earth work on canals | IS 4701:1982 |
|  | 4 | Methods of Test for soils | IS 2720 |
| XIII | OTHER SUBJECTS: |  |  |
|  | 1 | Code of practice for design and insulation of joints in buildings. | IS 3414:1968 |
|  | 2 | Code of practice for design and construction of foundations in soils : general requirement | IS 1904:1986 |
|  |  | Colours for Ready mixed paints & enamels | IS5: 2004 |
| XIV. | MACHINERY |  |  |
|  | 1 | Batch type concrete mixer | IS 1791:1968 |
|  | 2 | Concrete Vibrators – Immersible type | IS 2505:1980 |
|  | 3 | Specifications for moulds for use in tests of cement and concrete | IS 10086:1982 |
|  | 4 | Compression testing machine used for testing of concrete and mortar | IS 14858:2000 |
|  | 5 | Sheep foot roller | IS 4616:1968 |
| XV. | SAFETY |  |  |
|  | 1 | Code of practice for fire safety of buildings (general): Details of construction | IS 1642:1989 |
|  | 2 | Criteria for earthquake resistant design of structures. | IS 1893:2002 Part-1 |
|  | 3 | Code of practice for earthquake resistant design and construction of buildings. | IS 4326:1993 |
|  | 4 | Safety code for scaffolds and ladders |  |
|  |  | Part-I – Scaffolds | IS 3696:1987 (Part-I) |
|  |  | Part-I – Ladders | IS 3696:1991 (Part-II) |
| XVI | DRAWINGS: |  |  |
|  | 1 | Code of practice for general engineering drawings | IS 696:1972 |
|  | 2 | Code of practice for architectural and building drawings (First revision). | IS 962: 1989 |
| XVII | MEASUREMENT |  |  |
|  | 1 | Methods of measurement of building and civil engineering works. | IS : 1200 |

Note:-  The above I.S specifications mean latest over and above with amendments if any.

3.11	PERFORMANCE OF WORK

3.11.1	Execution of Works

3.11.1.1	All the works shall be executed in strict conformity with the provisions of the contract documents, explanatory detailed drawings and specifications.

3.11.1.2	The site should be cleared of all obstructions, vegetation, loose stones and materials before start of work.

3.11.1.3	The Engineer in charge, Supervisor will inspect the work on a Day-to-Day basis.

3.11.2	Work in Monsoon

3.11.2.1	The construction may entail working in monsoon also.  The contractor must maintain a minimum labour force and execute the construction according to the prescribed schedule.

3.11.2.2	Contractor is responsible for keeping the construction work site free from water.

3.11.3	Plinth Levels

3.11.3.1	A proper level should be maintained, in terms of horizontal and vertical alignment. A minimum acceptable plinth level above road level shall be maintained. The plinth level shall be agreed with the Engineer’s representative.

4.0	Detailed Specifications of Materials

4.1	Water (APSS No. 129)

4.1.1	Water should be clean, fresh and free from all chemicals, oils, salts and deleterious materials and vegetable growth. Water has to meet the requirements mentioned in Cl. 5.4 of IS: 456-2000.  Storage for water should be sufficient and adequate for the regular consumption of works and for the use of labour on site.

4.2	Earth (APSS No. 309 & 310)

4.2.1	For filling, the soil shall be free from all rubbish, organic or vegetable growth including roots, weeds etc.  Black cotton soil should not be used for basement filling.

4.3	Sand/ fine aggregate (APSS No. 110)

4.3.1	Sand to be used shall be composed of hard silicious material and shall be clean, sharp, hard, strong and angular type.  Sand shall be clean river or pit sand of approved quality and free from salts, earth, dust or other impurities. Sand for plain and reinforced concrete shall confirm to IS: 383-1970. Sand for various purposes shall confirm grading as below.

Sand for Masonry   --- table 110-A of APSS No.110

Sand for Plastering --- table 110-B & 110-C of APSS No. 110

Sand for Plain and	Zone I to III of table 110-D of APSS No.110

Reinforced concrete

| TABLE - II |  |  |  |  |
| --- | --- | --- | --- | --- |
| 4.3 FINE AGGREGATE (SAND) |  |  |  |  |
| Percentage passing by Mass |  |  |  |  |
| L.S. Sieve Designation | Grading Zone - I | Grading Zone – II | Grading Zone - III | Grading Zone - IV |
| 10 mm | 100 | 100 | 100 | 100 |
| 4.75 mm | 90-100 | 90-100 | 90-100 | 95-100 |
| 2.36 mm | 60-95 | 75-100 | 85-100 | 95-100 |
| 1.18 mm | 30-70 | 55-90 | 75-100 | 90-100 |
| 600.00 microns | 15-34 | 35-59 | 60-79 | 80-100 |
| 300.00 microns | 5-20 | 8-30 | 12-40 | 15-50 |
| 150.00 microns | 0-10 | 0-10 | 0-10 | 0-15 |

4.4	Stone for Masonry (APSS No. 107)

4.4.1	Stones used shall be strong, durable, dense, compact, close grained, homogeneous, fire resistant and shall be obtained from sources approved by Engineer.  Stones shall additionally be hard, sound, free from cracks, decay and other flaws or weathering and shall be easily workable.  Stones with round surfaces shall not be made use of.

4.4.2	Stones shall have a crushing strength of not less than 1000 Kg/cm2.  Stones with lesser crushing strength may be used in works with prior approval of the Engineer. Stones shall be non-porous and when tested in accordance with IS: 1124-“Method of Test for Determination of Water Absorption” etc., shall show water absorption of less than 5% of its dry weight when soaked in water for 24 hours. Tests for durability and weathering shall be done in accordance with IS: 1126 and IS: 1125 respectively.  The working of stones to required sizes and their dressing shall be as per IS: 1127 “Recommendations for dimensions and workmanship of natural building stones for Masonry work” and IS: 1129 “Dressing of Natural Building Stones”. Stones especially limestones and sand stones, shall be well seasoned by exposure to air before use in construction works.

4.5	Cement (APSS No. 112)

4.5.1   Cement should comply with the requirements of IS:8112-1989 and should be 43 grade 	ordinary Portland Cement, for making plain and reinforced concrete, mortar etc. The 	quality of cement shall be inconformity to the performance characteristics given in IS : 	8112 - 1989.

4.5.2	The contractor shall procure bulk cement required for the works only from reputed cement factories (main producers) acceptable to the Engineer and should obtain, furnish from suppliers of cement a test certficate for every consignment of cement. The cement bag shall bear the manufacturer's name or their registered trade mark. Cement shall be tested in accordance with IS : 4031-1988 and IS : 4032-1988.

4.5.3	The cement should be delivered to the site in sound dry bags and shall be stored 	properly.  Cement packed in LDPE Bags may be preferred to ensure protection from 	moisture and dampness.

4.5.4	The contractor has to make his own arrangements for the procurement of cement of 	required specification for works subject to the following:

a)	The contractor shall procure bulk cement required for the works, only from cement factories (Main producers) of approved make and brand only as approved by the Engineer-in-charge.  The contractor shall make own arrangements for adequate storage of cement.

b)	The contractor shall procure cement in standard packing (50 Kg per bag) from the authorised manufacturers.  The contractor shall make necessary arrangement at his own cost to the satisfaction of Engineer-in-charge for actual weighment of random sample from the available stock and shall confirm with the specification laid down by the Bureau of Indian standards or other standard institutions as the case may be.  Cement shall be got tested for all the tests as directed by the Engineer-in-charge at least once in a month in advance before the use of cement bags brought and kept at site godown.

c)	Cement bags required for testing shall be supplied by the contractor free of cost.

d)	The contractor should store the cement of 60 days requirement at least one month in advance to ensure the quality of cement so brought to site and shall not remove the same without the written permission of the Engineer-in-charge.

e)     The contractor shall forthwith remove from the works area any cement that the Engineer-in-charge may disallow for use on account of failure to meet with required quality and standard. Damaged or reclaimed or partly set cement will not be permitted to be used and shall be removed from the site.

f)	The contractor will have to construct sheds for storing cement having capacity not less than the cement required for 90 days use at appropriate locations at the work site.  The Engineer-in-charge or the representatives shall have free access to such stores at all times.

g)	The contractor shall further at all times satisfy the Engineer-in-charge on demand by production of records and books or by submission of returns and other proofs as directed that the cement is being used as tested and approved by Engineer-in-charge for the purpose and the contractor shall at all times keep his records up to date to enable the Engineer-in-charge to apply such checks as he may desire.

h)   Cement which has been unduly long in storage with the contractor or alternatively has deteriorated due to inadequate storage and thus become unfit for use on the work shall be rejected by the department and no claims will be entertained.  The contractor shall forthwith remove from the work area any cement the Engineer-in-charge may disallow for use on work and replace it by cement complying with the relevant Indian Standards.

4.5.5	STORAGE OF CEMENT

4.5.5.1	Portland cement readily absorbs moisture not only in the form of free water but also moisture from the atmosphere or from damp material in contact with it and becomes hydrated and loses strength.  It is necessary therefore that it should be protected from absorption of moisture before it is used if it is to fulfill its function.  An absorption of one or two percent of water has not appreciable effect but further amounts of absorption, results in hardening of the cement and reduced the strength.  If the absorption exceeds 5% the cement is for all ordinary purposes ruined.

4.5.5.2	American, Spanish and German experiments have shown that on average the strength of cement stress in bags is reduced.

After 3 months by 15 to 20 percent.

After 6 months by 20 to 30 percent.

After 115 Months by 30 to 50 percent.

After 2 years by 40 to 50 percent.

These figures prove that special attention should be paid to the storage of cement,   even when its strength is equal to or suspense’s the specified normal strength.

4.5.5.3	As a general principle the cement must be protected as far as possible from any form of moisture prior to mixing concrete mortar.

4.5.5.4	The cement should be stored in a well constructed dry godown or shed.  The cement store should be weather tight construction with a sound wooden or ground to ensure that it is damp proof building. The storage place required for a given quantity of cement can be calculated at the rate of 2.50 sqm for a ton of cement. Cement should not be placed directly on cement plaster flooring and other types of flooring commonly meant with which are not damp proof.  A wooden platform or false floor a sheet of water proof paper should be provided.

If none of these is possible, then floor should be covered with straw, hay, cinder or ash or such other material densely and uniformly packed to a thickness of at least one inch and over a laid worth tarpaulin of old cement.  Large windows and ventilators if any should be tightly shut to prevent from circulation of air inside the stores. Drainage should be provided if necessary to prevent accumulation of water in the vicinity of the store.

4.5.5.5	Cement should be stored in piles arranged parallel to the walls.  It is not advisable to pile bags against the walls and an allowance of at least 0.3M all round should be made between the exterior walls and piles. At least 0.6M wide should be left for each access and delivery.

When storing the bags, the floor should be raised 30 cms., above the ground and stacked in rows not exceeding 10 bags high. The cement is to be stored in such a manner that easy access and proper inspection and counting is possible.

Successive consignments covered with some water proof cover as a both  measure of protection and prevent the free circulation of air as each lot of proper fresh air will bring in more moisture.  Once the cement has been properly stored should not be disturbed until it is to be used.  There is no advantage in moving and stacking the bags to reduce where house set as this practice only exposes fresh cement to the air resulting in loss due to the shifting of cement through the cloth mesh and in damage to the stacks.

4.5.5.6	Even during the dry weather and when the relative humidity of the atmosphere even in nights is low (that is to say when there is very little moisture in the air) the cement in its stock shall be protected with a tarpaulin through for the stack.  When the atmosphere is damp at any time of day or night, greater care has to be taken of the cement and proper strength provided it from the damp.

4.5.5.7	Cement required for use immediately after delivery to the site may be stored in the open on a raised damp proof floor so long as it is fully protected by tarpaulin or either weather resisting covers.  Storage under these conditions should be limited to 48 hours.  The tarpaulin should be raised well above the top most Tie of bags and must be sloped for rapid drainage in case of showers.

4.5.5.8	Consignments should be used in the same sequences as they are delivered.  To ensure this the date of arrival of each consignment should be clearly indicated.  This is best done by tying a piece of country twins or cord to the end bags in the bottom most tier of the days pile, tacking the two places of card up the sides and along the top of pile an tying the main the center. The date of receipt in the store being clearly written on a bin card high from the card.  Dead storage where the cement remains in place for a long time which other consignments of cement come in and out should be avoided.

4.5.5.9	 In issuing cement from a store the cement bags should be removed in vertical column of the pile and not horizontal so as to avoid dead stoppage space.

4.5.5.10	As a rule cement should not be stored longer than three months. Cement held in storage for a period of 90 days or longer shall be re-tested. Especially in the rainy season prolonged storage should be avoided.  If stock is likely to be held over for more than three months anticipatory measures should be taken to use it on the works.

4.5.5.11	Cement that has become supply due to storage in damp positions due to exposure to the weather is generally useless for making concrete and should be removed from the site.

4.6	Bricks (APSS No. 102)

4.6.1	Bricks for masonry shall be as specified in the specification and shall have minimum crushing strength and shall conform the relevant specifications.

4.6.2	They shall be sound, hard and thoroughly well burnt, but not over-burnt, with uniform size having rectangular faces with parallel sides and sharp straight right angled edges and be of uniform colour with fine compact uniform texture. Bricks shall be of uniform deep red cherry or copper colour. They shall be free from flaws, cracks and nodules of free lime.

4.6.3	 Water absorption after 24 hours immersion in cold water shall be not more than 20% by weight. They shall not absorb more than 10% by weight of water after immersion for six hours.

4.6.4	They shall emit a clear metallic ringing sound when struck by a mallet and shall not break when dropped on their face, from a height of 60 cm.

4.6.5	Fractured surface shall show homogeneous, fine grained uniform texture, free from cracks, air holes, laminations, grits, lumps of lime, efflorescence or any other defect which may impair their strength, durability, appearance and usefulness for the purpose intended. Under-burnt or vitrified bricks shall not be used.

4.6.6	Samples of bricks brought to the site shall be tested periodically for compression and other tests according to IS:3495, Parts-I, II & III - “Method of Test for Burnt Clay Building Bricks”.

4.7	Coarse Aggregate (APSS No. 108)

The coarse aggregate shall be from hard granite crushed stone conforming to   IS 383: 1970. The pieces of aggregate shall be non porous, hard, strong durable clean and free from clay, rounded in shape and shall have granular or crystalline non powdery surfaces. The aggregate shall be well graded. Tests where required shall be carried out in accordance with IS: 2386 - 1963.

| I.S. 383 / 1970 Table – I |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.7.1 Coarse Aggregate |  |  |  |  |  |  |  |  |  |
| I.S. Sieve designation | Percent passing for single-seized aggregate of metal size |  |  |  | Percentage passing for graded-aggregate of nominal size |  |  |  |  |
| mm | 40 mm |  | 20 mm | 12.50 mm | 10 mm | 40 mm |  | 20 mm |  |
| (1) | (3) |  | (4) | (6) | (7) | (8) |  | (9) |  |
| 80 mm | --- |  | --- | --- | --- | 100 |  | --- |  |
| 63 mm | 100 |  | --- | --- | --- | --- |  | --- |  |
| 40 mm | 85-100 |  | 100 | --- | --- | 95-100 |  | 100 |  |
| 20 mm | 0-20 |  | 85 - 100 | --- | --- | 30-70 |  | 95-100 |  |
| 16 mm | --- |  | --- | 100 | --- | --- |  | --- |  |
| 12.50 mm | --- |  | --- | 85 – 100 | 100 | --- |  | --- |  |
| 10 mm | 0-5 |  | 0-20 | 0-45 | 85 - 100 | 10-35 |  | 25-55 |  |
| 4.75 mm | --- |  | 0-5 | 0-10 | 0-20 | 0-5 |  | 0-10 |  |
| 2.36 mm | --- |  | --- | --- | 0-5 | --- |  | --- |  |

| TABLE – III |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ALL-IN AGGREGATE GRADING |  |  |  |  |  |  |
| L.S. Sieve Designation | 40mm Nominal |  |  |  | 20mm Nominal |  |
| 80.00 mm | 100 |  |  |  | --- |  |
| 40.00 mm | 95-100 |  |  |  | 100 |  |
| 20.00 mm | 45-75 |  |  |  | 95-100 |  |
| 4.75 mm | 25-45 |  |  |  | 30-50 |  |
| 600.00 microns | 8-30 |  |  |  | 10-35 |  |
| 150.00 microns | 0-6 |  |  |  | 0-6 |  |

4.8	Steel Reinforcement (APSS No. 126)

4.8.1 General:

a) This section covers specifications for providing steel reinforcement to Bridges. Under Tunnels,

Aqueducts, Super passages, retaining walls, Canal Side Walls, Inlets, Outlets, Head Walls, Cut off Walls; cross Regulators. Off-take Sluices and other similar Structures.

b) A list of IS code applicable is furnished below:

List of I.S. Codes:

I.S.456-1978		:	Code of pratce for plain and Reinforced Concrete.

I.S. 1786-1985	:	Specification for High Strength deformed steel bars and wires for

concrete reinforcement

I.S.432-1982 		:	Specifications for mild steel and medium tensile steel bars for

(Part.I)				Concrete reinforcement and hard drawn steel wire.

I. S. 818-1968		:	Code of practice for safety and healthy requirement and gas

welding and cutting operations.

I.S. 3016-1986		:	Code of practice for fire precautions in welding and cutting

operations.

I.S.280-1978 		:	Mild steel wire for general Engineering purposes.

I.S.2502-1963		:	Code of practice for bending and fixing of bars for concrete

reinforcement.

I.S. 9417-1989		:	Recommendations for welding cold worked bars for reinforced

concrete construction.

I.S.2751-1979		:	Welding of mild steel plain and deformed bars for reinforced

Construction.

I.S.814-1991		:	Covered electrodes for manual metal arc welding of carbon and

carbon manganese steel.

I.S. 1278-1972		:	Filler rods and wires for gas welding.

In addition to the above Indian Standard specifications, wherever necessary, the specifications prescribed in APSS shall also be followed.

4.8.2 Scope:

Supplying, fabrication and placing gills of M.S./HYSD Reinforcement of different diameter including cost and conveyance of Reinforcement bars, sampling, testing, binding wire, cleaning, cutting, bending, welding, tying the grills and placing them in position with necessary chars and cover blocks in including all leads, lifts, delifts and all other operations necessary to complete the finished item of work, as per drawings, specifications and as directed by the Engineer-in-charge.

4.8.3 Materials:

i) The provisions of schedule 'D’ shall apply.

ii) Cutting, bending and Binding of Reinforcement:

a) Reinforcing Steel shall conform accurately to the dimensions given in the bar bending schedules shown on relevant drawings.

b) Bars shall be bent cold to the specified shape and dimensions by a bar bender by hand or power to attain proper radii of bands as shown in drawings or as directed by the Engineer.

c) Bars shall not be bent or straightened in a manner that will injure the material.

d) bars bent during the transport or handling shall be straightened before being used on work, they shall not be heated to facilitate bending.

e) "U" hooks shall invariably be provided at the end of each bar. If specified in Drawing or ordered by the Engineer. The radius of the bend shall not be less than twice the diameter of round bar and the length of the straight part of the bar beyond the end of the curve shall be at least four times the diameter of the round bar. In a case of bars which are not round and in the case of deformed bars, the diameter shall be taken as the diameter of a circle having an equivalent effective area.

f) The hook shall be suitably encased to prevent any splitting of the concrete

4.8.4 Placing of reinforcement:

a) Before the reinforcement is placed, the surface of the bars and the surfaces of any

metal bar supports be cleaned of the rust, loose mill scale, dirt, grease and other

objectionable foreign substances..

b) All reinforcing bars shall be securely held in position during placing of concrete by annealed binding wire, and by using stays, blocks or metal chairs, spacers, metal hangers, supporting wires or other approved devices at sufficiently close intervals.

c) Wire for binding reinforcement shall be soft and annealed mild steel of 16 SWG and shall conform to IS: 280-1978. Binding wire shall have tensile strength of not less than 5600 Kg/CM2, and an yield point of not less than 3850Kg/CM2.

d) Bars shall not allowed to sag between supports. They shall not be displaced during concreting or any other operation over the work.

e) The contractor shall also ensure that there is no disturbance caused to the reinforcing bas already placed in concrete.

f) All devices used for positioning shall be of non-corrodible material. Metal supports shall not extend to the surface of the concrete, except where shown on the drawing. Pieces of broken stone or brick and wooden blocks shall not be used. Where portions of such supports will be exposed on concrete surface designated to receive F2 or F3 finish, the exposed portion of support shall be galvanized or coated with other corrosion resistant material without which the concreting will not be permitted. Such supports shall not be exposed on surfaces designated to receive F4 finish unless otherwise shown on the drawings.

g) Placing of layers of freshly laid concrete as work progresses for adjusting bar spacing shall not be allowed.

h) Layers of bars shall be separated by space bars, precast blocks or other approved devices.

i) Rein forcemeat after being placed in position shall be maintained in a clean condition until completely embedded in concrete. Special care shall be taken to prevent any displacement of reinforcement in concrete already placed.

j) To protect reinforcement from corrosion, concrete cover shall be provided as indicated on the drawings. All bars protruding from concrete and to which other base are to be splided and which are likely to be exposed for an indefinite period shall be protected by thick coat of neat cement grout.

k) bars crossing each other, where required, shall be secured by binding wire (annealed) of size not less than 1mm media and conforming to IS: 280-1978 in such a manner that they do not slip over each other at the time of fixing and concreting.

l) As far as possible, bars of full length shall be used. In case this is not possible, overlapping of bars shall be done as directed. by Engineer. When practicable, overlapping bars shall not touch each other, but be kept apart by 25mm or11/4 times the maximum size of the coarse aggregate whichever is greater, by concrete between them. Where not feasible overlapping bars shall be bound with annealed steel wire, not less than 1mm thickness twisted tight. The overlaps shall be staggered for different bars and located at points, along the span where neither hear nor bending moment is maximum.

m) The minimum allowable clearance between parallel round bars shall not be less than 11/2 times the diameter of the larger bars and for square bars shall not be less than twice the side dimensions of the larger bars or 11/2 times, the maximum size aggregate whichever is greater.

n) Dissimilar diameter rods should not be jointed together.

4.8.5 Splicing:

a) Where it is necessary to splice reinforcement the splices shall be made by lapping, by welding or by mechanical means.

i) When permitted or specified on the drawings, joints of reinforcement bars shall be butt welded so as to transmit their full strength. Welding of bars shall be done as directed by the Engineer and conforming with requirements of Clause 11.4 of IS. 456-1978.

ii) If it is proposed to use welded splices in reinforcing bars, the equipment, the material and all welding and testing procedures shall be subject to the approval of the Engineer. The Contractor shall also carryout test welds as required by the Engineer. No extra rate will be paid for welding reinforcement test-welds as tender rate in schedule-A is inclusive of this item.

iii) For welded splices for reinforcing bars conforming to IS 1786-1985, welding shall be done in accordance with I : 9417-1979. For reinforcing bars conforming to IS : 432 (part-I) -1982, welding shall be done in accordance with IS: 2715-1979. Electrodes for manual metal arc welding shall conform to IS: 814 ( part.I) - 1974 and IS : 814 (part.II) - 1974. Mild steel filler rods of Oxy-acetylene welding shall conform to IS : 1278-1972 provided they are capable of giving a minimum butt weld tensile strength of 41 kg/mm2.

iv) Only electric arc welding using process which excludes air from the molten metal and conforms to any or all other special provisions for the work shall be accepted. Suitable means shall be provided for holding the bars securely in position during welding. It must be ensured that no voids are left in welding and when welding is done in tow or three steps. Previous surfaces shall be cleaned well. Ends of bars shall be cleaned of all Iron, scale, rust grease, paint and other foreign matter before welding.

b) Reinforcing bars of 28mm is diameter and larger may be connected by butt welding provided that lapped splices will be permitted if found to be more practical than butt welding and if lapping does not encroach on cover limitation or hinder concrete or reinforcement placing.

c) Reinforcing bars 25mm in diameter and less may be either, lapped or Butt welded,	whichever is the most practicable.

i) Butt welding of reinforcing bars shall be performed either by the gas pressure or flash pressure welding process or by the electric arc methods under cover from weather.

ii) Welded pieces of reinforcement shall be tested at the rate of 0.5% of total number of joints welded. Specimen shall be taken from the actual site of work. Strength of the weld provided shall be at least 25% higher than the strength of bar.

d) Welded joints of splices shall preferably be located at points where steel will not be subject to more than 75% of the maximum permissible stresses and welds so staggered that at any section not more than 20% of rods are welded. Approval of such additional splices will generally be restricted to splices not closer than 8 meters in horizontal bars or 4 meters in vertical bars measured between midpoint of laps.

4.8.6 Coupling of Bars:

a) Wherever indicated on the drawings or desired by the Engineer to use mechanical couplings for reinforcing bars, bars shall be joined by couplings which shall have a cross-section sufficient to transmit the full strength of bars. The ends of bars that are joined by couplings shall be for sufficient length, so that the effective cross-section of the base of threads shall be standard whit-worth threads. Steel for couplings shall conform to IS. 226. The contractor shall submit samples of the proposed coupling to the Engineer for approval not less than 60 days prior to their proposed use.

4.8.7 Care of placed Reinforcement and Concrete:

a) Where reinforcement bars are bent aside at construction joints and afterwards bent back into their original position, care shall be taken to ensure that at no time the radius of the bend is less than 6x diameter for deformed bars and 4x diameter for plain mild steel bars. Care shall also be taken, when bending such bars, to ensure that the concrete around the bars is not damaged.

4.8.8 Tolerances:

a) As specified in clause 11.3 of IS : 456-1978 unless otherwise specified by the Engineer reinforcement shall be placed within the following tolerances.

i) For effective depth 200mm or less  = + 10mm.

ii) For effective depth more than 200mm + 15mm

b) The cover shall in no case be reduced by more than one third of specified cover or 5mm which ever is less.

4.8.9 Dowels:

a) The dowels shall be of the same H.Y.S.D bars of grade Fe 415/500 conforming to I.S. 1786-1985 as used for reinforcement.

b) Details for dowel shall be as shown on the drawings or as directed by the Engineer.

c) Dowels shall be placed in the concrete where shown on the drawings or where directed and will be inspected for compliance with requirements as to size, shape, length, position, and amount after they have been placed, but before being covered by concrete.

d) Before the dowels are embedded in concrete, the surfaces of dowels shall be cleaned of all dirt, grease or other foreign substances which in opinion of the Engineer are objectionable.

e) The dowels shall be accurately placed and secured in position so that they will not be displaced during the placing of the concrete.

4.8.10 Measurement and Payment:

a) Measurement: Measurement for payment, for furnishing and placing reinforcing bars will be made only on the calculated weight of the bars placed in concrete, in accordance with the drawings or as directed by the Engineer.

b) The calculated weight for reinforcing bars shall be determined as follows:

i) Reinforcement shall be measured in length separately for different diameters as actually used in the work excluding overlaps. Length shall include hooks at ends.

ii) From the length measured, weight of reinforcing bars shall be calculated on the basis of weights specified in the table in schedule 'D’.

iii) Wastage, overlaps, couplings, welded joints, spacer bars, dowels and annealed steel

wire for binding shall not be measured and the cost of these items shall be deemed

to have been included in the rates for reinforcement.

iv) The unit for payment shall be one metric tonne weight of steel.

c) Payment Rate: The tender rate in the schedule-A for reinforcement shall include cost of steel sampling and testing binding wire or welding material at site of work, its cutting, bending, cleaning, placing, binding or welding and fixing in position as sown on the drawings and as directed by the Engineer. The unit rate shall also include cost of all devices for keeping reinforcement in approved position, cost of jointing as per approved methods and all wastage, overlaps, dowels, binding wire or welding material and spacers of bars and cost of all incidental operations necessary to complete the work as per drawings and as per specifications.

4.8.11	Mild steel bars shall conform to Grade I of IS: 432.

4.8.12	High yield steel strength deformed bars shall conform to IS: 1786-1985.  Binding wire shall conform to IS: 280.  The various types of steel shall conform to the relevant IS specification as provided in A.P.S.S. No.126.

4.8.13  	The contractor has to make his own arrangements for procurement of tested steel required for the work. He shall also make his own arrangements for transportation and storage.

4.8.14  	The contractor shall procure mild steel (MS) reinforcement bars, High yield strength deformed bars (HYSD) bars, rods and structural steel etc., required for the works, only from the reputed main steel manufacturing units i.e SAIL, VSP, TATA  manufacturing the steel to the prescribed specification of Bureau of Indian Standards or equivalent and licensed to affix ISI or other equivalent certifications, marks and acceptable to the Engineer-in-charge.

4.8.15	The contractor should  invariably obtain necessary ISI test certificates from the suppliers of  steel for each and every consignment and furnish them to the   Engineer-in-charge, before use on works. Test certificates conforming to IS 1786-1985  are to be furnished. The HYSD  steel (IS 1786-1985)  bars  should have TOR mark.

The original bills of procurement should be submitted to the Engineer-in-charge for making payment of the item. The contractor shall purchase the steel on the name of the work, number and the name of the contractor and furnish the same to the Engineer-In-Charge. The steel without the above two names will not be accepted on the works. Vendors test certificates and weighment bills are to be furnished to the Engineer-In-Charge and any quantity purchased without test certificates will not be accepted for use on the works.

4.8.16	If any difference is observed on carriage inwards, carriage outwards and theoretical requirement of steel for finished work, the contract will be cancelled and the contractor will be blacklisted.

4.8.17	The diameter and weight of steel should be as per IS 1786-1985 or relevant IS specification with subsequent revisions from time to time:

| S.No. | Diameter of rod | Sectional weight in Kg/ RM both for Plain and HYSD steel |
| --- | --- | --- |
| 1 | 6 MM | 0.22 |
| 2 | 8 MM | 0.39 |
| 3 | 10 MM | 0.62 |
| 4 | 12MM | 0.89 |
| 5 | 14 MM | 1.21 |
| 6 | 16 MM | 1.58 |
| 7 | 18 MM | 2.00 |
| 8 | 20 MM | 2.47 |
| 9 | 22 MM | 2.98 |
| 10 | 25 MM | 3.85 |
| 11 | 28 MM | 4.83 |
| 12 | 32 MM | 6.31 |
| 13 | 33 MM | 6.71 |
| 14 | 36 MM | 7.99 |
| 15 | 40 MM | 9.86 |
| 16 | 42 MM | 10.88 |

Note: If any rods other than those diameters specified above are procured the weights shall be as per standard steel tables.

4.8.18	Quality control:  The contractor shall furnish the samples for testing for each batch and consignment along with the test certificates issued by the vendors to the Engineer-In-Charge immediately after receipt of the steel in the stockyard at site of work for verification and testing.

No steel procured by the contractor shall be used in any work until the Engineer-In-Charge has given notice that the test results are satisfactory.

4.8.19	STEEL STORAGE:

a) 	Reinforcement steel and binding wire shall be stored above ground surface upon   platform, skids or other supports protected as for as possible from surface deterioration by direct contact with undesirable elements or by exposure to conditions producing rust and corrosion.  Bars shall be so supported as to avoid distortion and sagging of long lengths. All the reinforcement of same designation shall be stacked separately and distinctly marked.

b)	Steel shall be stacked and stored in accordance with IS 4082: 1996 as per Recommendations on stacking and storage of construction materials.

c)	If the reinforcing rods have to be stored for a long duration, they shall be coated with cement wash before stacking and/or be kept under cover.

4.8.20	Reinforcement shall be free from pitting due to corrosion and free from loose    rust, dirt, dust, mill scale, paint, oil, grease, adhering earth etc.

4.8.21	Erected and secured reinforcement after fabrication shall be inspected and approved by the Engineer-in-Charge prior to placement of concrete.

4.9.1	TEAK WOOD FOR JOINERY/ DOORS

The wood shall be well seasoned, uniformly coloured and shall be free from knots, cracks, shakes, splits, cross grains etc.

The wood shall be durable and of reasonably straight grains.

Moisture content of wood used shall be as near as possible to the following values:

Recommended values of moisture content in timber at the time of assembly or framing:

| Type of work | Coastal area | Inland area |
| --- | --- | --- |
| Frames for doors and windows | 16 to 18% | 14 to 15% |
| Shutters of doors and windows etc | 15 to 16% | 12 to 14% |

4.9.2	Glazed Tiles (APSS No. 121)

The tiles shall be covered by a glaze on the top and under side. The edges shall be free from glaze in order that the tiles may adhere properly to the base. The glaze shall be uniform in quality and free from welts, ships, craze, specks, crawlings, or other imperfections visible from a distance of one meter. The glazed tiles shall be white or colour and size of 300mm x 200 mm with a thickness of 7mm. The tiles shall be true to shape and conform to the performance requirements of IS 13712:2006 and supplier shall submit a certificate with respect to the quality of tiles and detailed there in.

5.0	Detailed Specification of Works

5.1	Standard

A high standard of workmanship in all trades will be required.  The Contractor shall ensure that only skilled and experienced workmen are employed.

5.2 	Supervision

5.2.1	The Contractor’s supervising staff shall be fully qualified and experienced in the types of work being carried out under the supervision and shall be capable of ensuring that they are done well and efficiently.

5.3	Temporary works

Where required, the Contractor shall furnish such details of his temporary works as may be called for by the Engineer and the Contractor shall satisfy the Engineer as to their safety and efficiency.  The Engineer may direct that temporary works, which he considers unsafe or insufficient, shall be removed and replaced in a satisfactory manner.

5.4	Codes

5.4.1	Unless mentioned otherwise, current versions of all codes, specifications and standards issued by the Indian Standards Institution  and  Indian  Roads  Congress, wherever mentioned, shall be fully applicable to these specifications. Where standards are not yet published by the ISI or IRC, adaptable British Standards or Specifications of the International Organization for standardization shall apply.

5.4.2	In case of any conflict in meaning between the specifications mentioned herein and those of ISI or IRC, the provisions of these specifications shall be prevail.

5.5	Base lines and bench marks

5.5.1	The Contractor shall establish and maintain, to the satisfaction of Engineer, the base lines and bench marks, based on which the works are set out.  Where such base lines and bench marks are provided by the Engineer, the Contractor shall maintain these throughout the period of construction without causing any disturbance to them.

5.6	Setting out

5.6.1	The Contractor shall set out all the works to be executed by him, in line with the standard base lines, position and bench marks and truly as per drawings within the accepted tolerance limits at no extra cost to Owner.  The Contractor shall be solely responsible for the correct setting out of all the works, to be executed by him and the approval of such setting out by the Engineer shall in no way absolve the Contractor of his responsibility for carrying the work to the true lines, levels and positions as per drawings.

5.7	Dewatering

5.7.1	The Contractor shall carryout all the works, in dry and workable condition and maintain the same in dry condition till the final handing over of works at no extra cost to the Owner. For this the Contractor shall make at his cost all the necessary provisions of dewatering, wherever necessary, to the full satisfaction of the Engineer.

5.8	Safety of existing work

5.8.1	Before taking up any construction adjoining other property or existing work, the Contractor shall take all steps necessary for the safety and protection of such property or work.

5.9	Protection of existing services

5.9.1	The Contractor shall take all precautions necessary to prevent damage to or interference with under-ground or over-ground services such as cables,         drains, piping or piles, whether shown on drawings or not.  Equipment etc., mounted in position shall be protected against falling debris etc., by means of tarpaulin or such other material.

5.10	Handing over of work site

5.10.1	On completion of work, the Contractor shall remove all rubbish, debris, surplus materials, temporary work etc., from the site.  The site shall be handed over in a tidy and workmanlike manner.

5.11      	CRS Masonry in CM (1:8) in 1st sort (APSS 107 & APSS 611)

5.11.1	The work shall consist of a facing of selected stones hammer dressed at faces and joints with only a small proportion of smaller stones in the hearting.

5.11.2	The face stones shall be set in regular courses of uniform thickness from bottom to the top throughout.  The height of the course should be uniform throughout by using stones of same height.  The face stones shall be laid in headers and stretchers alternately so as to break joint by atleast 75mm and headers shall project atleast 100mm beyond stretchers.  The stones shall be solidly bedded, set full in mortar with joints not exceeding 12mm in thickness and shall extend well back into the hearting.

5.11.3	Bond stones shall be placed in the wall @ interval of 2m in length and 600mm in height and shall run through the wall if the wall is not more than 600mm thick.  If the wall is more than 600mm thick line of headers shall be laid from face to back each header overlapping the other by atleast 150mm.

5.11.4	The heart portion shall be filled with good flat bedded stones set as close as possible, well set in mortar.

5.11.5	The work on interior face shall be precisely the same as on the exterior face unless the work is to be plastered in which case the side joints need not be vertical.

5.12	Coursed Rubble Masonry in CM (1:8) 2nd sort: (APSS NO. 612)

5.12.1	This work shall be executed similar to the specifications for C.R.S. masonry 1st sort with the exception that the hearting and backing shall conform to the standard specification for random rubble masonry and bond with the face stones being carried up continuously with the face work.

5.13 	RRS Masonry in CM (1:8) (APSS 107 & APSS 615)

5.13.1	The face stone be hammered dressed on the face, side and the beds to enable to come into close proximity with the neighboring stone. Face stone shall be of not less width in plan than 150mm for walls of 400mm thick, 200mm for walls of 450mm thick. The face stone shall be laid in headers and stretchers alternatively so as to break joints by at least 75mm. Care is to be taken to break joints vertically.

5.13.2	Bond stones should built in the wall at intervals of 2m in length and 600mm in height and shall run through the wall if the wall is not more than 600mm thick. The heart portion shall be filled with good flat bedded stone set as close as possible, well set in mortar.

5.14	Brick Work: (APSS 102 APSS 501 & 504)

5.14.1	All bricks to be used in the work shall be thoroughly soaked in water before use to prevent absorption of water from the mortar.

5.14.2	The bricks shall be set in cement mortar of 1:8 proportion by adopting a proper bond (preferably either English bond or a Flemish bond) throughout the wall.

5.14.3	The walls shall be taken up truly plumb. All courses shall be truly horizontal (level) and truly vertical.  Vertical joints of consecutive courses shall not come directly over one another.  Vertical joints, in alternate course shall come directly over one another. Joint’s shall be fully filled with mortar and raked.  Every brick shall be laid with full joints of cement mortar on its bed, ends and side in one operation.  No feeding of mortar by using excess water shall be allowed.

5.15	Reinforced Half Brick Partition Walls (APSS 102, 501, 504, 509)

5.15.1	All bricks to be used in the work shall be thoroughly soaked in water before use to prevent absorption of water from the mortar.

5.15.2	The cement mortar used for reinforced brick work shall be in cm (1:4) and mortar used shall conform APSS No. 113. Reinforcement for half brick walls shall be in the form of MS Bars and shall be of specified qualities. The brick shall be constructed only in stretcher bond. The reinforcement shall be well embedded in cement mortar at every third course and half the joint thickness of mortar shall first be laid and the other half laid after the reinforcement is placed in the position. The free ends of the reinforcement where ever possible shall be pegged into the mortar joints of main brick walls.

5.16	NOTES ON MASONRY

5.16.1	i) 	All stones, bricks etc., used in the masonry work shall be thoroughly soaked in water before use to prevent absorption of water from the mortar.

ii) 	Stones shall be laid on their broadest faces which gives better opportunity to fill the faces between stones.

iii) 	To give sufficient lateral bond a stone in any course shall overlap the stone in the course below i.e. joints parallel to the pressure in two adjoining course shall not lie too closely in the same vertical line.  A minimum overlap of 6" shall be maintained.

iv) 	To give sufficient transverse bond, prescribed no. of headers shall be used.

v) 	The practice of building two thin faces, tying width occasionally through stones and filling up the middle with small stones or dry packing shall be strictly guarded against.

vi) 	Jambs for door and window opening shall be formed with quoins of the full height of the course.  The quoins shall be of breadth atleast one and a half times the depth for the course and in length atleast twice the depth.

vii) 	It is advisable to erect the door and window frames first and build the masonry around.

viii) 	Thickness of the joint should not be more than 12mm.

ix) 	Every course of the masonry shall be truly vertical.  Use of plumb bob to check verticality by the mason shall be encouraged.

x) 	Care should be taken to keep all corners and sides including door and window opening truly vertical.

5.16.2    Theoretical requirement of cement should be as follows: Cement bags of 50 kgs

a.	C.R.S. Masonry in C.M. (1:6)	1.54 bags per Cum

b.	C.R.S. Masonry in C.M. (1:8)	1.15 bags per Cum

c.	Brick Masonry in C.M. (1:4)	1.44 bags per Cum

d.	Brick Masonry in C.M(1:6)	0.96 bags per Cum

e.   	Brick Masonry in C.M. (1:8)	0.72 bags per Cum

5.17	Plain and Reinforced cement concrete (A.P.S.S. 402 & 403)

5.17.1	All R.C.C. work shall be carried out in strict accordance with latest IS specification. No concrete work shall be cast in the absence of the works-in-charge/Engineer. All the materials used should be of good quality as mentioned in Sec. 4.0 above.

5.17.2	Cast-in-place concrete for the structures shall conform to the requirements of the section. The structures shall be built to the lines, grades and dimensions as per the designs and drawings.

5.18	Controlled concrete: Controlled concrete shall be used on all concrete works.  Reinforced cement concrete shall correspond to M20/M25/M30 grade as per IS 456-2000.

5.19	Mix Proportions & Strength requirement of concrete: The proportions of various ingredients to be used in the concrete for different parts of the work shall be established by proper mix through design mix. The contractor shall produce concrete mix design and establish the strength of concrete with this concrete mix design for 3 days, 7 days and 21 days as per IS 456-2000. For controlled concrete, the mix design shall be so designed as to attain in preliminary tests a strength atleast 33 percent higher than that required on work tests. The design mix shall be got approved by the Engineer-in-charge before proceeding with the concreting.  The contractor is required to carryout the mix design and the design mix shall be got approved by the Engineer-in-charge, APSFC within the limitations of parameters and other stipulations laid down in IS-456/2000.

The specified characteristic compressive strength of 150 mm size cube at 28 days attained for M20, M25 and M30 grades of concrete shall be 20 N/sqmm, 25N/sqmm and 30 N/sqmm respectively. The mix shall be designed to produce the grade of concrete having the required workability and a characteristic strength at 28 days not less than the appropriate values mentioned in Table-2 of IS-456:2000. The target mean strength of the concrete mix should be equal to the characteristic strength plus 1.65 times the standard deviation.

### TABLE

MINIMUM COMPRESSIVE STRENGTH OF 15 CM. CUBES

AT 7 AND 28 DAYS AFTER MIXING, CONDUCTED

IN ACCORDANCE WITH IS.516

| Class | Preliminary test N/mm2 |  | Works test N/mm2 |  | Maximum size of aggregate mm |
| --- | --- | --- | --- | --- | --- |
|  | at 7 days | at 28 days | at 7 days | at 28 days |  |
| M40 | 33.50 | 50.00 | 27.00 | 40.00 | 20 |
| M35 | 30.00 | 44.00 | 23.50 | 35.00 | 20 |
| M30 | 25.00 | 38.00 | 20.00 | 30.00 | 40 or 20 |
| M25 | 22.00 | 32.00 | 17.00 | 25.00 | 40 or 20 |
| M20 | 17.50 | 26.00 | 13.50 | 20.00 | 40 or 20 |
| M15 | 13.50 | 20.00 | 10.00 | 15.00 | 40 or 20 |

Whenever the grade of concrete such as M30 etc., is specified it shall be Contractor’s responsibility to ensure the minimum crushing strength stipulated for the respective grade of concrete is obtained at works.

The contractor shall maintain the test results on regular basis as indicated in I.S.456/2000 and subsequent amendments thereon.

In all cases, the 28 days compressive strength specified shall be the criterion for acceptance or rejection of the concrete.

The sample of water taken for testing shall be typical of the water proposed to be used for concreting.

The contractor shall be responsible for production of controlled concrete as per design mix to ensure the required works cube strength is attained and maintained. In the designation of concrete mix, letter ‘M’ refers to the Mix and the number to the specified 28 days works cube compressive strength in Newton per sq.mm.

The concrete where site mixing is permitted shall be with concrete mixtures fitted with weigh batching scale. All measuring equipment shall be maintained in a clean serviceable condition and their accuracy periodically checked.

5.19.1 	The proportions of cement concrete specified in the above schedule are nominal and are indication of approximate proportion of cement, fine aggregate and coarse aggregate which may have to be altered suitably at site to obtain desired strength and workability. However, the quantity of cement shall not be less than specified below.

Nominal Mix	Cement in bags of 50 Kgs per

one Cubic metre (net) of cement concrete

a.	1:1.5 : 3	8.84 bags of 50 Kgs.

b.	1:2:4	6.62 bags of 50 Kgs.

c.	1:2.5:5	5.30 bags of 50 Kgs.

d.	1:3:6	4 42 bags of 50 Kgs.

e.	1:4:8	3.31 bags of 50 Kgs.

f.	1:5:10	2.65 bags of 50 Kgs.

g.	1:6:12	2.21 bags of 50 Kgs.

h.	1:8:16	1.66 bags of 50 kgs.

5.19.2	The quantity of water shall be varied to suit the moisture content of the aggregate and shall be just sufficient in produce a dense concrete with workability. Workability should be checked at frequent intervals as per IS: 1199.  An accurate and strict control shall be kept on the quantity of mixing water.

5.20	Concrete quality control measures and concrete quality Assurance Test   Programme

a)	Concrete quality control measures: The contractor shall be responsible for providing quality concrete to ensure compliance of the bid requirements.

b)	Concrete quality Assurance Programme: The concrete samples will be taken     by the Department and its quality will be tested in any other recognized laboratory per the relevant Indian Standard Specifications IS 516:1959 and IS: 1199-1959.

Samples shall be drawn on each day for each type of concrete.

Tests: The Department will obtain samples and conduct tests as specified in

B.I.S. 456- 2000, I.S. 1199- 1959 and I.S. 416 - 1959

Test Facilities: The contractor shall furnish free of cost samples of all ingredients   of concrete for testing and obtain approval from the Engineer-in-Charge. He should also supply free of cost, the samples of all the ingredients of concrete for conducting the required tests.

Test results: The Engineer-in-charge will pass the concrete if average strength of the specimens tested is not less than the strength specified.  Concrete not meeting requirements of specification in all respects may be rejected by the Engineer-in-charge in which case it shall be removed and reconstructed entirely at the expense of the contractor.

5.21	Preparation for placing: No concrete shall be placed until preparation of    surface  involved, all form work, reinforcement, installation of items to be embedded have been approved by the Engineer-in-charge.

5.21.1	All surfaces, forms, embedded material shall be free from dried mortar,   dirt, foreign substances, waste papers etc.  Temporary openings shall be provided to facilitate inspection, especially of bottoms of columns and wall forms, to permit removal of sawdust, wood shavings, binding wire, dirt etc. Such openings/holes shall be suitably plugged later.

5.21.2	Foundation surface: Rock surfaces shall be free from oil, objectionable   coatings, loose, semi detached and unsound fragments. Immediately prior to placement of concrete, surfaces of rock shall be washed with an air water jet and shall be brought to a uniform surface dry condition.

5.21.3	Concrete shall not be placed in standing water or on a water-covered surface. Any concrete that has been washed away by heavy rains shall be entirely removed, if there is any sign of cement and sand having been washed away from the concrete mixture.

5.21.4	Starters: Before proceeding with erection of form work for RCC columns, Starters shall be cast with 25 mm thick concrete with string lines placed in position as per the layout.

5.21.5	Slots, openings, holes, pockets etc shall be provided in the concrete work in the positions specified or required or as directed by Engineer-in-charge.

5.21.6	Reinforcement and other items to be cast in concrete shall have clean surfaces that will not impair bond.

5.21.7	Approval by the Engineer-in-charge of any materials and work as required herein shall not relieve the contractor from his obligation to produce finished concrete in accordance with the requirements of the specifications.

5.22	Placing of Concrete: The contractor shall notify the Engineer–in-charge before batching begins. Batching, mixing and placing of concrete shall be performed only in the presence of an authorized representative of the Engineer-in-charge.

5.23      Weather: Concrete shall not be placed in rain sufficiently heavy or prolonged to wash mortar from concrete.

The contractor is not entitled for any additional payment over the unit prices bid in the schedule for concrete, by reason of any limitation in placing of concrete under the above paragraphs.

5.24	 PRODUCTION OF CONCRETE:

5.25	 BATCHING OF MATERIALS:

All materials entering into the concrete shall be batched by weight except water

which shall be in liters, when the weight of cement is determined on the basis of weight of cement per bag, a reasonable number of bags should be weighted periodically to check-the net weight. Admixtures if permitted by the Engineer-in-Charge should be added to the concrete by weight.  All measuring equipment and weight batching machinery shall be approved by the Engineer- in- Charge and maintained in a clean serviceable condition and their accuracy shall be periodically checked. The batching and mixing plant for concrete is to be designed to suit the local conditions and output requirements as per IS: 4925 - 1968 specification of batching and mixing plant for concrete.

The aggregates of different sizes should be stocked in separate stock piles, the same shall be blended in right proportions to ensure a uniform grading of aggregate as determined by the Engineer -in- Charge.

In case uniformity in the materials used for concrete making has been established over period of time, the proportioning may be done by volume batching, provided periodic checks are made on weight / volume relationships of materials.

Where weight batching is not practicable, the quantities of fine coarse aggregate (not cement) may be determined by volume.

The amount of the added water to concrete shall be adjusted to compensate for any observed variations in the moisture contents determined by the above tests for both design and nominal mix of concrete making for weight and volume batching.

5.26 	Mixing:

Concrete shall be mixed in a mechanical mixer complying with IS: 1791 - 1968 specification of batch type concrete mixtures. The mixing shall be continued until there is a uniform distribution of the materials and the mass is uniform in colour and consistency. If there is a segregation after unloading from the mixer, the concrete should be remixed.

The Mixing time may be 1.5 to 2 minutes for all normal cements.

In exception circumstances, such as (i) mechanical breakdown, (ii) work in the remote areas, (ii) when the quantity of concrete work is small Hand mixing is permitted subject to adding 10 percent extra cement.

The Hand mixing shall be carried out in a watertight platform and care shall be taken to ensure that mixing is continued until the concrete is uniform in colour and consistency.

All cement concrete shall be machine mixed and machine vibrated.

The mixers with other accessories shall be kept in first class working condition and so maintained throughout the construction.

Any mixer that at any time produces unsatisfactory mix, shall not be used until repaired. If repair attempts are not successful, the defective mixer shall be replaced.

The Cement and aggregates shall be mixed thoroughly in the specified proportion in   a mechanical mixer until the mixture is of uniform colour. Where machine mixing is      done the concrete shall be mixed, until the mixture is of uniform colour and, in no case, for less than two minutes.

5.27	Workability:

Work ability of concrete should be controlled by direct measurement of water content. Workability should be checked is frequent intervals as per the procedure laid down in IS: 1199 - 1959 methods of sampling and analysis of concrete.

SLUMP TEST TO CHECK WORKABILITY:

The Slump test for concrete shall be adopted only for concretes of medium to high work abilities (i.e., slump 25 to 100mm). For very stiff mixes having zero slump, the slump test does not indicate any difference in concrete of different work abilities.

TYPE										SLUMP

1. (A) Structure with exposed inclined 						  25mm

surface requiring low slump concretes,

to allow for proper compaction

(B) Plain cement concrete							  25mm

2. RCC, structures with widely spaced 						40-50mm

reinforcement: e.g.; solid columns, piers

abutments footing, well steining.

3. RCC structures with fair degree of congestion 				50-75mm

of reinforcement e.g. pier, and abutment caps,

box culverts well curbs and caps, walls with

thickness greater than 300mm.	.

4. RCC and PSC structures with highly congested 				75-125mm

reinforcements e; g; deck slab girders, box girders,

walls with thickness less than 300.

5. Under water concreting through tremie					100-200mm

eg : bottom plug, cast in- situ -piling.

VEE -: BEE test method to check workability:

VEE - BEE test shall be done for stiff concrete mixes having ‘ low or very’ workability. The ranges for VEE-BEE -TIME method for some placing conditions are given in clause:6 or IS: 456 - 1978, which shall be followed.

5.28.1 Transportation, placing and compaction of concrete:

Concrete shall be transported from the mixer to the form work as rapidly as possible by methods approved by the Engineer-in-charge, which will prevent the segregation or loss of any of the ingredients and maintaining the required workability.

The concrete shall be transported, laid and compacted in its final position within 30 minutes of its discharge from the mixer unless carried by in properly designed agitators. Where the time of haul exceeds 20 minutes, mixed concrete shall be transported in a suitable agitators or transit mixer as directed and approved by the Engineer-in-charge.

5.28.2 Placing of concrete:

All surfaces upon or against which concrete is to be laid shall be prepared in accordance with the drawings.

No concrete shall be placed until all form works installation of parts to be embedded and preparation of surface involved in the placing have been approved by the Engineer-in-charge. No concrete shall be placed in water except when specifically so permitted. All surfaces of forms and embedded materials have become incrusted with dried mortar from previously placed shall be cleaned before surrounding of adjacent concrete is placed.

If concreting is not started within 24 hours of to approval being given, it shall have to be obtained again. The contractor shall notify the Engineer at least 24 hours before matching begins for placement of concrete.

All absorptive surfaces against which concrete is to be laid shall be moistened thoroughly so that moisture will not be withdrawn from the freshly placed concrete. The concrete shall be deposited as nearly as possible in its final position and compacted before setting commences and should not be subsequently disturbed.

Methods of placing should be such as to preclude segregation.

Care should be taken to avoid displacement of reinforcement or movement of form work.

Placing is allowed with a limitation of free fall of 1.5meter.

All concrete shall be placed in continuous and approximate horizontally layers, the thickness of which shall not more than 450mm for mass concrete and 150mm for RC.C and plain cement concrete works.

Concrete shall not be placed faster than the placing crew can compact it properly.

On sloping surfaces, concrete should be placed at the lower end of the slope first, progressing upwards, and thereby increasing natural compaction of the concrete.

High velocity discharge which may cause segregation of the concrete should be avoided.

Recommended methods of placing concrete in segregation prone locations are:

5.28.3 a) In narrow forms: If very wet concrete is to be placed in narrow, deep form work,   water content in the upper layers should be gradually reduced to compensate for water gain.

b) Placing through side ports in column form work: Concrete shall be dropped vertically into the outside pockets under each form work opening (port) so that concrete stops and then flows easily into the column form work.

c) Placing on sloping surfaces: Concrete shall not be discharged from free end of a chute on to a sloping surface, as the heavier coarse aggregates are separated and carried down the slope. The chute should be fitted with a baffle and a drop at its end, so that concrete remains on slope.

d) Temperature: Concrete when deposited shall have a temperature of not less than 5 degree Celsius, and not more than 40 degrees Celsius.

Weather Conditions:

Concreting operations shall temporarily suspended during excessively hot or rainy weather when conditions are such that. The concrete cannot be placed and cured.

During the hot weather, no concrete shall be deposited when the temperature with in the forms is more than 49 degree Celsius. When ever necessary exposed surface of fresh or green concrete shall be shaded from the direct rays of sun and immediately protected against premature setting or drying by being cured under continuous fine spray of water.

During continued rainy weather or heavy downpour all freshly placed concrete shall be covered and protected against surface wash. Then all badly washed or stressed surface shall be removed and washed before depositing the next course.

e) Preparation of foundation surface: Immediately. before placing concrete all surfaces of foundations upon or against which concrete to be placed shall be free from standing water mud, debris, free from oil objectionable coatings, loose, semi detached or unsound fragments of rock. Surface of rock shall be cleaned with the use of high velocity audit.; wet sand blasting, stiff brooms, picks or by effective means.

f) Preparation of concrete surface: Concrete surface upon which fresh upon which fresh concrete is to be placed shall be chipped and roughened to a depth of not greater than 25mm. The roughing shall be performed by chipping or other satisfactory methods and in

such a manner as not to loosen, crack or shatter, any part of the concrete beyond the roughened surface. After being roughened, the surface of the concrete shall be cleaned thoroughly of all loose, dirt and other objectionable substances and shall be sound and hard and in such conditions as to assure good mechanical bond between old and new concrete. All concrete which is not hard, dense and durable shall be removed to the depth required to secure a satisfactory surface.

g) Cement slurry and mortar layer : After surfaces have been prepared satisfactorily, all surfaces, rock, old concrete and old masonry shall be coated with a thin layer of cement slurry (comprising 1 cement to 23 water by volume) and covered with a layer of mortar not less than 12mm, not more than 20mm thick. The mortar shall be similar to the mortar in the regular concrete mixture having the same cement sand ratio of the mortar used in concrete unless other wise directed. The cement slurry and mortar shall be spread uniformly and shall be worked thoroughly into all irregularities of the surface, concrete shall be placed immediately upon the fresh concrete.

5.28.4 	COMPACTION OF CONCRETE:

Compaction should preferably be achieved by mechanical vibration. But in is located locations. It can also be achieved if approved by the Engineer-in-charge by manual methods, namely, rodding, spading and tamping. The mechanical compaction is achieved by vibration. The methods like spinning mechanical tamping and use of shock are restricted to special situations as approved by the Engineer.

Under-vibration is harmful should be avoided. Over vibration may cause:

(i) Settlement of the coarse aggregate (ii) heavy bleeding of the concrete, (iii) excessive form work deflection and form work damage.

The following vibrators shall be used for compaction as per the directions of the Engineer-in-charge.

5.28.5 Immersion vibrators:

Immersion vibrators per IS: 2505-1980 be used for consolidation of plain as well as reinforced concrete. They shall be of either

a) Flexible shaft type, powered by different types of motors or

b) Motor-in-head type, electrically or pneumatically driven.

While compacting with internal vibrators, concrete should be deposited in layers of 300 to 450mm thick and the vibrator inserted vertically at uniform spacing over the entire area of placement. The vibrator should penetrate rapidly to the bottom of the layer and at least 150mm into the preceding layer, if there is any. It should be held (generally 5 to 15 second) until the compaction is considered adequate and then withdrawn slowly at the rate of about 80mm/second.

Operational frequency: 800 to 1200 per minute.

5.28.6 Screed board type vibrators:

Concrete vibrators of screed board type as per IS : 2506 - 1964 shall be used for compaction of concrete beds, floors, pavements and thing slabs, where the area to be compacted is large or the thickness is too small (less than 200mm) to allow the use of immersion vibrators.

Operational frequency: 3500 per minute (under no load state)

5.28.7 Form work vibrators:

Form work vibrators as per IS: 4656 - 1968 shall be used for compaction of concrete, Pre cast concrete moulds, gullies and deep post - tensioned beams. They shall be used for compaction of in-situ concrete is small and narrow sections of very heavily reinforced section where immersion of vibrators cannot be used. There are two types:

a. The fixed or clamped type, and

b. The manual type.

Operational frequency: 2800 per minute (under no load state)

5.28.8 Vibrating Table:

Vibrating table as per IS: 2514-1963 shall be used for compaction of concrete in moulds for the manufacture of precast products and structural elements. They compact concrete through rapidly alternating horizontal, vertical or circular vibrations which are transmitted to moulds filled with concrete and placed or clamped on the table top.

Operational frequency: 3000 to 6000 cycles per minute.

Immediately after compaction, concrete shall be protected against harmful effects of weather, including rain, running water, shocks, vibration, traffic, rapid temperature changes and drying out.

5.28.9 OTHER REQUIREMENTS OF CONCRETE CONSTRUCTIONS:

All concrete construction shall conform to the permissible tolerances and technical provisions as described in the section. All structures shall be built in a workman like manner, to the lines, grades and dimensions shown in the drawings or as prescribed by the Engineer. The location of all the construction joints shall be subject to the approval of the Engineer. The dimensions of each structure shown on the drawings shall be subject to such changes as may be found necessary by the Engineer to adopt the structure to the conditions disclosed by the excavation.

5.28.10 CURING:

All equipment, material etc needed for curing and protection of concrete shall be at hand and ready for installing before actual concreting begins. Detailed plans, methods and procedures and protection shall be settled and got approved in writing from the Engineer sufficiently in advance of the concreting. The equipment and method proposed to be utilized shall avoid interruption or damage to the work.

The vertical and sloping concrete surfaces shall be kept saturated with a system of perforated pipes mechanical sprinklers/ porous hoses / any other suitable method which will keep all surfaces continuously wet.

5.28.11 Moist curing:

Exposed surfaces of concrete shall be kept continuously in a damp or wet condition (to avoid formation of surface cracking due to alternate wetting and drying) by pounding or by covering with layer of sacking, canvas, Hessian or similar materials and kept constantly wet for at least SEVEN DAYS from the date of placing of concrete, if O.P cement is used in concrete.

It may be reduced to 3 to 4 days when rapid hardening Portland cement is used, but greater care shall be exercised, particularly at early stages when rate of hydration is high.

5.28.12 Membrane curing:

Approved curing compounds shal1 be used in lieu of moist curing with the permission of the Engineer - in charge. These compounds shall be applied to all exposed surface of the concrete as soon as possible after the concrete had set and the free water on the surface has disappeared and no water sheet is seen. But not so late that, the compound will be absorbed into the surface pores of the concrete.

5.28.13 SAMPLING AND STRENGTH OF CONCRETE:

The sampling shal1 be done as per the specifications laid down in IS 1199 - 1959 specification of sampling and analysis of Concrete with IS : 510 - 1959 specification for testing strength of concrete.

For relatively small and unimportant buildings and structure in which quantity of concrete is less than 15 cum, the strength tests may be waived by the Engineer - in - charge.

The sampling scheme given in clause 14 and the acceptance criteria given in clause: 154 of IS: 456 - 1978 are applicable to both design mix and nominal mix concrete. In the case of the later, the preliminary tests for establishing the mix proportions are not necessary.

Concrete of each grade shall be assessed separately.

The concrete under acceptance shall be notionally divided into lots for the purpose of sampling, before commencement of work. The of delimitation of lots shall be determined by the following:

i) No individual lot shall be more than 30 cum. in volume.

ii) At least one cube forming an item of the sample representing the lot shall be taken from concrete of the same grade and mix proportions cast any day.

iii) Different grades of mixes of concrete shall be divided into separate lots.

iv) Concrete of a lot shall be used in the same identifiable component the structure.

5.28.14 SAMPLING AND TESTING:

a) Concrete for making 3 test cubes shall be taken from a batch of concrete at point of delivery into construction according to procedure laid down in IS: 1199.

b) A random sampling procedure to ensure that each of the concrete batches forming the lot under acceptance inspection has equal chance of being chosen for taking cubes shall be adopted.

c) 150 mm cubes shall be made, cured and tested at the age of28 days for compressive strength in accordance with IS: 516. The 28 day test strength result for each cube shall form an item of the sample.

d) Three test specimens shall be made from each sample for testing at 28 days: Additional cubes may be required for various purposes such as to determine the strength of concrete at 7 days or for any other purpose.

e) The test strength of the sample shall be the average of the strength of 3 cubes. The individual variation should not be more than + 15% or - 15% of average.

f) Frequency: The minimum frequency of sampling of concrete of each shall be :

| QUANTITY OF CONCRETE IN WORK, CU.M | No. OF SAMPLES |
| --- | --- |
| 1- 5 | 1 |
| 6-15 | 2 |
| 16 - 30 | 3 |
| 31 - 50 | 4 + one additional sample for |
| 51 and above | each additional 50 cm. part thereof |

At least one sample shall be taken from each shift of work.

5.28.15. Test procedure

In order to get a relatively quicker idea of quality of concrete, optional tests on beams for modulus of rupture at 72 + 2 hours or at 7 days or compressive strength tests at 7 days may be carried out in addition to 28 days compressive strength tests. For this purpose, the values given in Table may be taken for general guidance in the case of concrete made with ordinary port land cement. In all cases, the 28 days compressive strength specified in Table shall be alone be the criterion for acceptance or rejection of the concrete. If however, from tests carried out in a particular job over a reasonably long period, it has been established to the satisfaction of the Engineer that a suitable ratio between 28 days compressive strength and the modules of rupture at 72 + 2 hours or 7 days or compressive strength at 7 days may be accepted, the Engineer may suitably relax the frequency of 28 days compressive strength provided the expected strength values at the specified early age are consistently met.

OPTIONAL TESTS REQUIREMENTS OF CONCRETE

|  | Compressive Strength | Modules of Rupture |  |
| --- | --- | --- | --- |
| Grade of concrete | on 15cm Cubes, Min, at 7 days | By Beam test, Min |  |
| (1) | (2) | at 72 + 2h | at 7 days |
|  |  | (3) | (4) |
| M-I0 M-15 M-20 | N/mm2 7.0 10.0 13.5 | N/mm2 1.2 1.5 1.7 | N/mm2 1.7 2.1 2.4 |

5.28.16. Standard Deviation:

(i) Standard Deviation based on Test results:

a) Number of test results: The total number of test results required to constitute as acceptable record for calculation of standard deviation shall be not less than 30. Attempts should be made to obtain in the 30 test results, as early as possible, when a mix is used for the first time check additional condition of about 5 samples.

b) Standard deviation to be brought up to date: The calculation of the standard deviation shall be brought up to date after every change of mix design and at least once a month.

(ii) Determination of Standard Deviation:

(a) The standard deviation of concrete of given grade shall be calculated using the following formula from the results of individual tests of concrete of that grade.

Estimated standard deviations = Sqrt ( sigma(delta sqr) / ( n-1 ) = √ € Δ2

(n-1)

Where delta = deviation of the individual test strength from the average n = number of sample test results.

c) When significant changes are made in the production of concrete batches (for example" changes in the materials used, mix design, equipment or technica1.dmtrol) the standard deviation value shall be separately calculated for such batches of concrete.

5.28.17 Assumed standard Deviation:

Where sufficient test results for a particular grade of concrete are not available the value of standard deviation given in the following table may be assumed.

ASSUMED STANDARD DEVIATION

| GRADE OF CONCRETE | STANDARD DEVIATION FOR DIFFERENT DEGREE OF CONTROL IN N/mm2 |  |  |
| --- | --- | --- | --- |
|  | Very good | Good | Fair |
| M 10 | 2.0 | 2.3 | 3.3 |
| M 15 | 2.5 | 3.5 | 4.5 |
| M 20 | 3.6 | 4.6 | 5.6 |

However, when adequate past records for a similar grade exist and justify to the designed a value of standard deviation different from that shown in the above Table. At shall be permissible to use that value.

Acceptance criteria:

The concrete shall be deemed to comply with the strength requirements if:

a) every sample has a test strength not less than the characteristic value: or

b) the strength of one or more samples through less than the characteristic value: is in each case not less than the greater of:

1) the characteristic strength minus 1. 35 times the standards deviations: and.

2) 0.80 times the characteristic strength: and the average strength of all the. samples

is not less than the characteristic strength plus

(1. 65-1. 65/sqrt. (number of samples) times the standard deviation.

1.65 -            1.65             .	    X  Standard deviation.

√No. of Samples

The concrete shall be deemed not to comply with the strength requirements if:

a) the strength of any sample is less than the greater of:

1) the characteristic strength minus 1. 35 times the standard deviation; and

2) 0.80 times the characteristic strength: or

b) the average strength of all the samples is less than the characteristic strength plus.

1.65 -          3.00        .   x  Standard deviation

√No. of Samples

(1.65-3.00/sqrt. (number of samples) times the standard deviation.

Concrete which does not meet the strength requirements as specified but has a strength greater than that required may, at the discretion of the designer, be accepted as being structurally adequate without further testing.

If the concrete is deemed not to comply the structural adequacy of the parts affected 	shall be investigated and any consequential action as needed shall be taken.

Concrete of each grade shall be assessed separately.

Concrete shall be assessed daily for compliance.

Concrete is liable to be rejected if it is porous or honeycombed; its placing has been interrupted without providing a proper construction just (or) tolerances have not been met. However, the hardened concrete may be accepted after carrying out suitable remedial measures to the satisfaction of the engineer.

5.28.18 Core and load tests:

Inspection: Immediately after stripping the form work, all concrete shall be carefully inspected any defective work or small defects either removed or made good before concrete has thoroughly hardened.

In case of doubt regarding the grade of concrete used, either due to poor workmanship or based on results of cube strength tests, compressive strength tests of concrete and/or load test may be carried out.

a) Core Test: The points from which cores are to be taken and the number of cores required shall be at the discretion of the engineer and shall be representative of the whole of concrete concerned. In no case, however, shall fewer than three cores be tested.

Cores shall be prepared and tested as described in IS : 516-1959.

Concrete in the member represented by a core test shall be considered acceptable if the average equivalent cube strength of the cores is equal at least 85 percent of the cubes strength of the grade of concrete specified for the corresponding age and no individual core has a strength less than 75 percent.

In case the core test results do not satisfy the requirements of or where such tests have not been done, load test may be resorted to.

b) Load tests on parts of structures: Loading tests should be carried out as soon as	possible after expire of 28 days from the time of placing of concrete.

The structure should be subject to a load equal to full dead load of the structure plus 1.25 times the imposed load for a period of 24 hours' and then the imposed load shall be removed;

NOTE: Dead load includes self weight of the structure members plus weight of finishes and walls or partitions, if any, as considered in the design.

The deflection due to imposed load only shall be recorded. If within 24 hours of removal of the imposed load, the .structure does not recover at least 75 percent of the deflection under superimposed load, the test may be repeated after a lapse of72 hours. If the recovery is less than 80 percent, the structure shall be deemed to be un acceptance.

5.28.19. Acceptance criteria:

Two sets of criteria for demonstrating that the concrete as produced and casted either complies or does not comply with the IS : 456-1978 requirements for concrete quality.

a) requirements of strength, and

b) requirement of workmanship.

Compressive strength: When both the following conditions are met, the concrete complies with the specified compressive strength:

a) The mean strength determined from any group of four consecutive samples should	exceed the specified characteristic compressive strength.

b) Strength of any sample is not less than the specified characteristic compressive strength  minus 3MPa.

5.28.20 Rejection Criteria:

Concrete is liable to be rejected if it is :

a) Porous or honeycombed, (due to incorrect mix proportions or improper compaction 	techniques).

b) Its placing has been interrupted without providing a proper construction joint

c) The reinforcement has been displaced beyond the ta1erance have not been.

d) If the core tests / load test does not yield the results.

e) If the strength of the concrete produced and casted does not yield the strength 		requirements of the code.

(f) If the test results of the test cubes obtained as per IS: 1199 and tested as per IS: 516 	does not yield the strength requirements of the code acceptance criteria, the Engineer-	in-Charge with the consolation of the Designer will consider the technical Consequences 	such as durability, strength, serviceability, economic consequences, .cost replacement, cost of strengthening the weak point etc..., However, the hardened concrete shall be accepted only after carrying out suitable remedial measures to the satisfaction of the Engineer-in-Charge.

5.28.21 Unacceptable work:

All defective concreting work including but not limited to defects arising out of honeycombing, under -sizing, under strength etc. are liable to be demolished and rebuilt by the 'contractor at his cost. In the event of such work being accepted by carrying out repairs as specified by the Engineer the cost of repairs shall be borne by the can tractor. Acceptance of such works will be in accordance with the provisions of IS : 456-1978.

Visible defects noticed in the workman ship and quality which could be rectified through remedial measures, shall be rectified to. the satisfaction of the Engineer.

Deficiency in workmanship which is considered to be attributable to same inadequacy in concrete production or concrete haulage, or concrete placement method, or compaction, should be got remedied from thee-Contractors by the Engineer through additional inputs and up gradation of methodology and work taken subsequently only when the needed augmentation has been done. If the subsequent work is within acceptable level, steps should be taken to remedy the defects noted in the earlier work through appropriate measure.  After the defects have been remedied to the satisfaction of Engineer and provided that the inputs (cement, aggregates, water etc.,) are within the specified quality standards, the concerned work shall be accepted.

In case the Engineer observes basic and serious deficiencies in the quality of inputs and output as well as in the workmanship, revealed through perusal of test records and visual inspection as well including say, examination of cores (taken from insight concrete lining), as also serious in adequacies in construction equipment and job facilities in enforcing the technical specifications, such portions of works shall be rejected and not accepted far any payment. In the absence of any positive measures to strengthen these structures/works, the Engineer may arrange for their demolition and reconstruction.

There could be portions of work/works.  Where some sort of slight transgression of specification / quality levels has taken place and which is not feasible of rectification in full.  In case it is determined that the integrity of such portions of work is not significantly impaired and that the functional capability can be assured consideration may be given by the Engineer (subject to full satisfaction of the Engineer to accept these at reduced payment to the contractor instead of demolishing the concerned portion of work and re constructing it.

5.28.22 CONCRETING UNDER SPECIAL CONDITIONS:

Concrete under water:

When it is necessary to deposit concrete underwater, the methods, equipment, materials and proportions of mix to be used shall be got approved from the Engineer before any work is started. Concrete shall contain 10 percent more cement than, that required for the same mix placed in the dry.

Concrete shall not be placed in water having a temperature below 5 degrees Celsius. The temperature of the concrete, when deposited, shall not be less than 16 degrees Celsius, not more then 40 degrees Celsius.

All under water concreting shall be carried out by tremie method only, using tremie of appropriate diameter. The number and spacing of the tremies should be worked out to ensure proper concreting. The tremie concreting when started should continue without interruption for the full height of member being concreted. The concrete production and placement equipment should sufficient to enable the underwater concrete to be completed uninterrupted within the stipulated time. Necessary stand-by equipment should be available for emergency situation.

The top section of the tremie shall have a hopper large enough to hold one full batch of the mix or the entire contents of the transporting bucket as the case may be. The tremie pipe shall not be less than 200mm in diameter and shall be large enough to allow a free flow of concrete and strong enough to withstand the external pressure of the water in which it is suspended, even if a partial vacuum develops inside the pipe preferable, flanged steel pipe of adequate strength for the job shall be used. A separate lifting device shall be provided for each tremie pipe with its hopper at the upper end. Unless the lower and of the pipe is equipped with an approved automatic check valve, the upper end of the pipe shall be plugged with a wadding of gunny sacking or other approved material before delivering the concrete to the tremie pipe through the hopper, so that when the concrete is forced down from the hopper to the pipe, it will force the plug (and along with it any water the pipe) down the pipe and out of the bottom end, thus establishing a continuous stream of concrete. It will be necessary to raise slowly the tremie in order to allow a uniform flow of concrete, but it shall not be emptied so that water is not allowed to enter above the concrete in the pipe. At all times after placing of concrete is started and until all the required quantity has been placed, the lower end of the tremie pipe shall be kept below the surface of the plastic concrete. This will cause the concrete. to build up from below instead of flowing out over the surface and thus avoid formation of layers of laitance, If the charge in the tremie is lost-while depositing the tremie shall be rapped above the concrete surface and unless sealed by a check value, it shall be re plugged at the top end, as at the beginning, before refilling for depositing further concrete.

5.28.23: Cold Weather Concreting:

Where concrete is to be deposited at or near freezing temperature, precautions shall be taken to ensure that at the time of placing, it has temperature of not less than 5 degrees Celsius and that the temperature of the conception shall be maintained above degree Celsius until it has throughly hardened. When necessary, concrete ingredients shall be heated before mixing but cement not be heated artificially other than by the heat transmitted to it from other ingredients of the concrete. Stockpiled aggregate may beheaded by the use of dry heat or steam. Aggregates shall not be heated directly by gas or on sheet metal over fire. In general the temperature of aggregates or water shall not exceed 65 degrees Celsius. Salt or other chemicals shall not be used for the prevention of freezing. No frozen material or materials containing ice shall be used. All concrete damaged by frost shall be removed. It is recommended that concrete damaged by frost shall be removed, It is recommended that concrete exposed to freezing weather shall have entrained air and the water content of the mix shall not exceed 30 liters per 50 kg of cement.

5.28.24 Hot weather conditions:

When depositing concrete in very hot water precautions shall be taken so that the temperature of wet concrete does not exceed 40 degrees Celsius while placing. This shall be achieved by stacking aggregate under the shade and keeping them. moist, using cold water, reducing the time between mixing and placing to the minimum, cooling form work by sprinkling water, starting curing before concrete dries out and restricting concreting as for as possible to early morning and late evenings. When ice is used to cool mixing water, it will be considered apart of the water in design mix. Under no circumstances shall be mixing operation be considered complete until all ice in the mixing drum has melted.

The contractor will be required to state his methodology for the Engineer's approval when temperatures of concrete are likely to exceed 40 degrees Celsius during the work.

5.28.25 INSPECTION AND TESTING OF STRUCTURES:

Immediately after stripping the form work, all concrete shall be carefully inspected and any defective work or small defects either removed or made good before concrete has throughly hardened. In case of doubt regarding grades of concrete used, either due to poor workmanship or based on results of CUBE STRENGTH TESTS. Compressive strength tests on concrete structural elements shall be done as specified in clause: 16.3 - for core test and as specified in clause 16.5 -for tests on the part of the structures.

5.28.26 FINISHING:

General:

Immediately after removal of forms exposed bars or bolts if any, shall be cut inside the concrete member to a depth at least 50mm below the surface of the concrete and the resulting holes filled with cement mortar. All fins caused by form joints, all cavities produced by the removal of form ties and all other holes and depression honey comb spots, broken edges or corners and other defects, shall be thoroughly cleaned, saturated with water, and carefully pointed and rendered i.e. with mortar of cement and fine aggregate mixed in the proportion used in the grade of concrete that is being finished and of as dry a consistency as is possible to use. Considerable pressure shall be applied in filling and pointing to ensure through filling in all voids. Surfaces which have been pointed shall be kept moist for a period of 24 hours. Special pre-packed proprietary mortars shall be used where appropriate or where specified in the drawing.

All construction and expansion of joints in the complete work shall be left carefully tooled and free from any mortar and concrete. Expansion joint filler shall be left exposed for its full length with clean and true edges.

Immediately on removal of forms the concrete work will be examined by the Engineer before any defects are made good.

a) The work that has sagged or contains honeycombing to a extent detrimental to structural safety or architectural appearance will be rejected. defined as concrete surface irregular

b) Surface defect of a minor nature shall be made good as directed by the Engineer-   in-charge.

5.28.27 Concrete Surface Irregularities:

a) General: Bulges depressions and offsets are ties Concrete surface irregularities are classified as 'abrupt' or 'gradual' and are measured relative to the actual concrete surface.

b) Abrupt surface irregularities: Abrupt surface irregularities are defined here in 	as offsets such as those caused by misplaced or loose forms, loose knots in form

timber, or other similar forming faults. Abrupt surface irregularities are measured using a short straightedge, at least 150 cm long, held firmly against by direct measurement.

c) Gradual surface irregularities are defined herein as, bulges ad depressions resulting in gradual changes on the concrete surface. Gradual surface irregularities are measured using a template conforming to the design profile of the concrete surface being examined. Templates for measuring gradual surface irregularities shall be provided by the contractor. Templates 'shall be at least2.5m. length. The magnitude of gradual surface irregularities is defined herein as a measure of the rate of change in slope of the concrete surface.

d) The magnitude of gradual surface irregularities on concrete surface shall be checked by the contractor to ensure that the surfaces are with in specified tolerances. The Engineer will also make checks of hardened concrete surface as deemed necessary to ensure compliance with these specifications. Templates for these surface shall be furnished by the contractor free of charge and shall be available for use by the contractor free of charge and shall be available for use by the Engineer at all times.

5.28.28 Repair of concrete: General:

a) Repair of concrete shall be performed by skilled workers and in the presence of an Engineer-in-charge. Repairs and correction of all imperfections on formed concrete shall be completed as soon as practicable after removal of forms and within 25 hours after removal of forms. Concrete that is damaged from any cause and concrete that is honey combed, fractured or otherwise defective and concrete, which because of excessive surface depressions, must be excavated and built up to bring the surface to the prescribed lines, shall be removed and replaced by dry pack mortar or concrete as hereinafter specified. Where bulges and abrupt irregularities protrude outside the limits specified the protrusions shall be reduced by bush hammering and grinding so that the surfaces are within the specified limits.

b) Before repair is to commence, the methods proposed for the repair shall be approved by the Engineer. Routine curing should be interrupted only in the area of repair operations.

Methods of Repairs:

For new works four methods are used as under:

a) Dry Pack method: This methods should be used for holes having a depth nearly equal to, or greater than the least surface dimensions; for cone bolt, the bolt and grout insert holes, and narrow bolts cut for the repair of crakes. Dry pack should not be used for relatively shallow depressions where lateral restraint cannot be obtained; for filling in back of considerable lengths of exposed reinforcement; nor for filling holes which extended entirely through the wall, beam etc.

b) i. Concrete Replacement method : Concrete repairs made by bonding concrete to repair area (without use of an epoxy bonding agent or mortar grout applied on the prepared surface) should be made when the depth of the area exceeds 15cm and the repair will ,be of appreciable continuous area, as determined by the Engineer.

Concrete repairs should also be used for holes extending entirely through concrete sections, for holes in which no reinforcement is encountered and which are greater in area than 900Sq.cms, and deeper than 10cms., and in reinforced concrete for holes greater than 1400 Sq.cms. The Engineer may also permit Expoxy bonded concrete repair as an alternative to concrete repair.

ii. Mortar Replacement method: Portland cement mortar may be used for repairing defects on surface not prominently exposed where the defects are too wide for a dry pack filling, the defects are too shallow for concrete filling and where they are not deeper than the far side of the reinforcement, that is nearest the surface.

iii. Epoxy Method: A thermo setting plastic known as epoxy can be used as a bonding medium whenever long time curing of conventional concrete cannot be assured. Epoxies can be used to bond new concrete or mortar to old concrete when ever the depth of repair is between about 3.75cm and 15cm. Also epoxy mortars of fine sand as well as plain epoxy are suitable for concrete repair work and should be used whenever every thin patch is to placed or immediate reuse of the area is require or where moist curing cannot be effectively accomplished. Preparation for epoxy bonded repairs should in general be identical to that for other concrete repairs except that every effort should be made to provide surfaces thoroughly dry. Drying of the immediate surface for at least 24 hours and warming to temperature between 18° to 27°C are essential for proper application of epoxy bonded repairs. Preparation for the use of epoxy mortars should include through cleaning and drying of the areas to be repaired. A wash of dilute (1 : 4) muriatic acid rinsing with clean water and subsequent drying is desirable, where feasible. If acid wash is not feasible, preparation may be accomplished as for other concrete repairs with final cleanup being by means of sandblasts method, followed by air water jet washing and through drying. Epoxy repairs shall be carried out only by trained personnel.

c) 	Removal of Concrete: All concrete of questionable quality should be removed. It is better to remove too much concrete than too little because affected concrete generally continues to disintegrate and while the work is being done it costs but little more to excavate to ample depth. Moistening, cleaning, surface drying and complete curing are of utmost importance when making repairs which must be thoroughly bond, watertight and permanent. Surfaces within trimmed holes should be kept continuously wet for several hours, preferably overnight prior to placing new concrete. Immediately, before placement of the filling, the holes should be

cleaned so as to leave a surface completely free from shipping dust dried growth and all   other foreign materials. Final cleaning of the surfaces to which the new concrete is to be bonded should be done by wet sand blasting followed by washing with air water jet for through cleaning and drying with an air jet. Care should be taken to remove any loose materials embedded in the surface by chisels during the trimming and to eliminate all shiny spots indicating free surface moisture. Cleaning of the steel if necessary should be accomplished by sandblasting. The prepared surface shall be approved by the Engineer.

(d) Dry pack of concrete: For this method of repair, the holes should be sharp and square at the surface edges, but the corners within the holes should be rounded. Especially when water tightness is required. The interior surfaces of holes left by cone bolts, the bolts etc. should be roughened to develop and effective bond. Other holes should be under cut slightly in several places. Holes for dry pack should have a minimum depth of 25mm.

(e) Concrete Replacement: i) Holes should have minimum depth of200mm in new concrete and the minimum area of repair should be 500 Sq.cms for reinforced and 1000 Sq.cms for unreinforced concrete. ii) Reinforcement bars should not be left partially embedded. There should be a clearance of at least 25mm around each exposed bar. iii) The top edge of the face of the structure should be cut to a fairly horizontal line. If the shape of the defect makes it advisable the top of the cut may be stepped down and continued on a horizontal line. The top of the hole should be cut 1 to 3 upward slope from the back towards the face of the wall or beam. It may be necessary to fill the hole from both sides in which case the slope of the top of the cut should be modified accordingly. iv) The bottom and sides of the holes should be cut sharp and approximately square with the face of the wall when the hole goes entirely through concrete section. Spalls or feather edges shall be avoided by having chippers worked from both faces. All interior corners should be rounded to maximum radius of 25mm.

f) 	Mortar Replacement :  When mortar gun is used with this method comparatively shallow holes should be flared outwardly at about 1 to 1 slope to avoid inclusion of rebound.  Corners within the holes should be rounded.  Shallow imperfections in new concrete may be repaired by mortar replacement if the work is done promptly after removal of the forms and while the concrete is still green for instance when it is considered necessary to repair the peeled areas resulting from surface material sticking to steel forms the surfaces may be filled using mortar gun without further trimming or cutting.  Whenever hand placed mortar replacement is used edges of chipped out areas should be squared with the surface leaving no feather edges.

Best results with replacement mortar are obtained when the mortar is pneumatically applied using a small mortar gun.  After the areas to be repaired have been cleaned and surface dried the mortar shall be applied immediately.  No initial application of cement, cement grout etc., is to be made.  The six proportion shall be 1 part cement to 4 parts natural sand by dry volume or weight.  Well graded sand passing No. 16 screen shall give best results.  Cement and sand shall be mixed with water to approximately the same consistency as for dry pack repair.

For repairs of more than (2.5 Cm) depth the mortar shall be applied in layers not more than about 20mm thick to avoid nagging and loss of bond.  After completion of each layer a time of about 30 minutes shall be allowed before the next layer is placed.  This time shall be so adjusted that the mortar of the previous layer does not get dry.

g)   Use of Dry pack Mortar  :  The Surface after preparing should be thoroughly brushed with a stiff mortar or grout barely wet enough to thoroughly wet the surface after which the dry pack material should be immediately packed into place before the bonding grout has dried.  The mix of bonding grout shall be 1 to 1 cement and fine sand mixed to a consistency like thick cream.  Under no circumstances should bonding coat be wet enough or applied heavily enough to make the dry pack material more than very slightly rubbery.  Dry pack is usually a mix (by dry volume or weight) of one part of cement to 11/2 part of sand.

Protection of works: The contractor shall protect all concrete against damage until final acceptance by Engineer-in-Charge. The fresh concrete shall be protected from defacements and damage due to construction operations, rain, sun and winds. The contractor shall provide protection to prevent erosion to fresh concrete whenever precipitation either periodic or sustaining  is imminent or occurring. All fresh concrete surfaces shall be protected from contamination and from foot traffic until the concrete has hardened.

5.29 Replacement of unsatisfactory concrete: Immediately after the shuttering is removed,  the surface of the concrete shall be very carefully gone over and all defective areas called to the attention of Engineer-in-charge. If reinforcement is exposed or the honey combing occurs the work may be rejected. Rejected concrete shall be removed and replaced by the contractor. Superficial honey combed surfaces and rough patches if permitted by the Engineer-in-charge shall be made good and finished neatly as per specifications and as directed.

5.30	Curing of concrete:. Rigid supervision shall be maintained for curing the concrete after laying for complete hydration and hardening to take place. The set concrete shall be cured by ponding with clean water. All exposed faces of concrete shall be kept continuously moist for a minimum period of 28 days by spraying water or by covering  with  gunny bags  which shall be constantly sprinkled with water. The curing operation should be done by using stirrup pump, or by any other methods given code  IS  456-1984. For curing floors, flat roofs, concrete pavements and other level surfaces the ponding method of curing shall be adopted.

5.31	CENTERING (FORM WORK) AND SHUTTERING

5.31.1	Formwork: Form work shall be as specified in the standard specification in BOQ used. Forms with surface dents, bulges, undulations or holes shall not be used on the work and shall be removed from the site.

5.31.2	Form work shall be substantially and rigidly constructed and shall be true to the dimensions described. Form work shall be constructed to confine and shape the concrete to the required shape, lines and dimensions described.  Liners and cores shall be provided where   necessary and shall be due to space and securely fixed.

5.31.3	Shuttering shall be erected true to line and securely braced, cross braced, strutted and supported to prevent deformation under the weight of  pressured wet concrete and constructional loads, wind pressure and other forces.

5.31.4	The surfaces of the forms shall be clean and free encrustation of mortar, grout or other foreign materials.

5.31.5	The variation in thickness of RCC roof slab due to varying spans or special covering materials should not effect the general roof bed which should be uniform, unless otherwise shown in drawing or as instructed.

5.31.6	All joints shall be sufficiently tight to prevent leakage of cement slurry. All faulty joints shall be adequately caulked.

5.32.1	Mould Oil: Before laying the reinforcement, all faces of shuttering and moulds in contact with wet concrete shall be treated with a coat of oil to prevent adherence to concrete. Release agent should be applied so as to provide thin uniform to the forms without coating the reinforcement.

5.32.2	The mould oil (The de-bonding agent)  to be applied shall be standard shuttering oil, engine oil or filtered waste oil (Carbon particles and impurities should not be present).

5.32.3	Plumb and string lines in sufficient numbers shall be installed before and maintained during concrete placement. During concrete placement the contractor shall continuously monitor plumb, string line and form positions.

5.32.4	In case of columns, retaining walls and vertical structural components suitable arrangement shall be made for securing the form to the already poured concrete.

5.33       Reinforcement for RCC works:

5.33.1	Unless shown otherwise in the drawings, the reinforcement to be used shall  be of High Yield Strength Deformed (H.Y.S.D.) bars of grade Fe-415/500 grade  conforming to  IS 1786-1985.

5.33.2	Reinforcement shall be steel and shall be free from corrosion, oil, grease, paint or dirt at the time of fixing in position and subsequent concreting.

5.33.3	Reinforcing steel bars shall conform accurately to the sizes, dimensions and shapes given as per designs and drawings. Bars shall be bent cold to the specified shape and dimensions and the bars shall be hooked or bent accurately and placed in exact position as per designs and drawings. Bars having kinks or bends other than those required by design shall not be used.

5.33.4	Bars of full length shall be used. Reinforcement shall be lap jointed or spliced only if unavoidable. The overlaps shall be staggered for different bars and located at points, along the span where neither shear nor bending moment is maximum. Not  more than 33% of the bars as specified in drawing shall be lapped at one section.

5.33.5	The reinforcement shall  be securely held in position and bound together tight  by annealed binding wire, and by using stays, blocks or metal chairs, spacers, metal hangers, supporting wires or other approved devices at sufficiently close intervals.

5.33.6	Bars shall not be allowed to sag between supports.    Layers of bars shall be separated by spacer bars, pre-cast blocks or other approved devices.  Binders, stirrups, links should be securely wired to the main ring.

5.34.1	Binding Wire: Wire for binding reinforcement shall be  soft and annealed mild steel of 16 SWG and shall conform to IS:280-2006. Binding wire shall have tensile strength of  not less than  5600 Kg/Cm2  and a yield point of less than 3850 Kg/Cm 2.

5.34.2	Proper cover shall be maintained between the reinforcement and the shuttering as per approved drawings and IS codes.

5.34.3	The contractor shall ensure that the bars are not displaced during  concreting or any other operation over the work. The contractor shall also ensure that there is no disturbance is caused to the reinforcing bars in  concrete that has already been placed.

5.34.4	All bars protruding from concrete and to which other bars are to be spliced and which are likely to be exposed for an indefinite period shall be protected by a thick coat of neat cement grout.

5.35	Measurement and payment

a)	Measurement:

Measurement for payment for the reinforcing bars will be made only on the calculated weight of the bars placed in concrete, in accordance with the drawings or as directed by the engineer. The calculated weight for reinforcing bars shall be determined as follows:

- Reinforcement shall be measured in length separately for different diameters as actually used in the work including the lengths of hooks at ends, excluding spacer bars, reinforcement chairs and overlaps.

- From the length measured, weight of reinforcing bars shall be calculated on the basis of weights specified in the table in this section.

- Wastage and annealed steel wire for binding shall not be measured as  the cost of these items were already  included in the unit rate for reinforcement.

Payment rate

The unit rate in the bill of quantities for reinforcement includes all wastages such as overlaps , couplings, welded joints, chairs, spacer bars including cost and conveyance of steel from stock yard etc.

Labour charges for fabrication of steel includes cutting, bending to required sizes and shapes placing in position with cover blocks of approved  size and tying with binding wire of 20 SWG, forming grills for reinforcement work as per approved designs and drawings, lifting charges of steel , placing in position, tying  including cost of binding wire , all tools etc.,

5.36	  Cover Blocks

a) 	Before concreting, cover blocks shall be fixed in all R.C.C works to separate the

reinforcement from the shuttering so that when the concrete is set the

reinforcement is well within the concrete section at a distance from the outer surface, with specified cover to reinforcement.

b) 	Use of stone chips as cover for the reinforcement will not be accepted.    Only cement mortar cover blocks of required thickness to maintain the specified cover shall be used.

c) 	Normally a bottom cover of 12mm to 15mm is sufficient for slabs.  For columns the cover should be about 40mm, and for beams it is 25mm.

d) 	Cover blocks shall be reasonably good for using in appropriate grade of R.C.C. work. The mortar for preparing cover blocks shall at least be of proportion 1:2.  Cover blocks shall be prepared on a clean and level platform by spreading the mortar in the moulds of required size and depth.  When the mortar is still green strands of tying wire shall be inserted into each block. This wire is useful for tying the block to the reinforcement.  After 24 hours the blocks shall be removed from the mould and cured for about seven days.

e) 	A properly made cover block does not get crushed when the reinforcement is tied over it and during the concreting work.

5.37   Reinforcement chairs

a) 	When the reinforcement is tied there is a need to separate bottom steel from the top steel and to maintain correct effective depth.

b) 	For ensuring separation to top and bottom steel and to ensure that the reinforcement work does not get disturbed due to the load or movement of workers when concrete is being laid, reinforcement   spacers or chairs shall be fixed.

c) 	Use of large sized stones or bricks to separate top and bottom steel will not be allowed.

d) 	Reinforcement chairs shall be of slightly lesser size so as to accommodate the chair underneath the top steel and after  allowing for the required covers to the top and bottom steel.

e) 	The chair shall be minimum 450mm long and should have legs bent in opposite directions to ensure stability,

f) 	The chairs shall be placed on a cover block so that the legs do not stick out once the shuttering is removed.

5.38	Form work: The form work shall conform to the shape, lines and dimensions as shown on the plans and be so constructed as to remain sufficient rigid during the placing and compaction of the concrete and shall be sufficiently water tight to prevent loss of cement slurry from the concrete, The form work shall be made leak proof by Providing Kraft paper.

Form work or centering shall be constructed of steel and adequately designed to support the full weight of wet concrete without deflection and retain its form during laying, ramming, vibrating and setting of concrete.

All rubbish, particularly chippings, shavings and sawdust, shall be removed from the interiors of the forms before the concrete is placed and the form work in contact with the concrete shall be cleaned and thoroughly wetted (in case of timber) or treated by coating with non staining mineral oil or other approved by coating with a non staining mineral oil or other approved material. Care shall be taken that such approved composition is kept out of contact with the reinforcement.

The forms shall be removed after expiry of the following periods in the normal circumstances and when O.P.C is used for making concrete.

i) Walls, columns and vertical	 faces of all structural members:	24 to 48 Hrs. or as directed by the Engineer-in-Charge.

ii) in Slabs (props left under)				……			3days

iii) Beam soffits (props left under) 			……			7 days

iv ) Removal of props under slabs

1) spanning up to 4.5 meter 				……			7 days

2) spanning over 4. 5 meter				……			14 days

v) Removal of props under beams and arches.

1) spanning up to 6.0 meter				……			14 days

2) spanning over 6. 0 meter				……			21 days

However the above periods may be increased or decreased at the discretion of the Engineer - in - charge.

All form work shall be removed without shock or vibration and shall be eased off carefully in order to allow the structure to take up load gradually. Forms shall not be disturbed until concrete has adequately hardened to take the superimposed load coming on to it and in no circumstances shall forms be struck until the concrete reaches a strength of at least twice the stress to which the concrete may be subjected to at the time of striking.

After removal of form work, in any case no concrete work shall be finished, plastered or made good in any form unless and until the Engineer-in-charge, inspect and certify the surface for such finishing, plastering or making good.

The number of props left under the concrete element, their sizes and dispositions shall be such that they shall be able to safely carry the full dead load and live load likely to occur during further construction.

The contractor shall be liable for damage and injury caused by removing the forms or props before the concrete has gained sufficient strength.

Cover requirements:

Unless otherwise specified in drawings and directed by the Engineer, the cover requirements for cast - in - situ structural members shall be as follows:

a) At each end of reinforcing bar not less than 25 mm nor less than twice the diameter of such rod or bar.

b) For a longitudinal reinforcing bar in a vertical member or a column not less than 40mm nor less than the diameter of bar. In the less of columns of minimum dimension of200 mm or under whose reinforcing bars do not exceed 12 mm the cover of 25 mm shall be used.

c) For longitudinal reinforcing bar in a beam, not less than 25 mm, nor less than the

diameter of such bar.

d) For RCC. members immersed in sea water, the cover shall be 50mm more than specified in (a), (b) and (c) above.

e) For footing, resting directly on soil the minimum clear cover shall be 50 mm and in the case of concrete in contact with earth faces contaminated with chemicals it shall be 75 mm.

f) Lesser thickness than those specified above shall be permissible for pre cast construction with the permission of the Engineer.

g) For water retaining structures, the cover requirements are

i) for liquid faces  			..           minimum 25 mm or the dia. of bar

which ever is greater.

ii) for the faces away from the liquid        ---	 The cover as specified above in (a) to

(f) with respect to structural member.

All reinforcement shall be placed and maintained in position as shown in the drawings as directed by the Engineer - in - charge adopting chairs and cover blocks within the tolerance limits specified in clause: 11. 3 of IS : 456 - 1978.

The bars shall be supported held in position by suitable means until concrete is poured. Anyone of the following devices shall be used for the purpose. (i) Providing steel reinforcement supports/spacers, (ii) providing of mortar supports/spacers and (iii.) providing plastic supports/spacers.

The steel support/spacers shall be used for slabs except in case of form finished surfaces. The mortar units can be used for slabs, beams and columns as well as plastered or form finished surfaces.

Use of pebbles, broken stone, metal pipe, brick, wooden blocks, etc., as devices for positioning reinforcement will not be permitted.

Suitable shape and size of cement mortar cover block with proportion of (1:1) shall be used on the work as per the drawing and as directed and approved by the Engineer-in-charge.

5.39 Conditions on RCC slabs/Roof Slabs

5.39.1 	The R.C.C. slab laid should be leak proof.  After observing for two rainy seasons as defect liability period if the roof or floor is found to be perfectly leak proof and no moisture or dampness is seen underneath at ceiling of the slab, the contractor can ask for refund of E.M.D. or F.S.D. from the department.  If there are any defects noticed after laying of roof they must be attended to by the contractor at his own cost.  Further the contractor must arrange to get the structure treated as per clause 21 of ISI code No.456/2000 at his own cost on the instructions of the department.

When R.C.C. slab is laid, the contractor shall carry out the following tests at his own cost to prove that the slab is impervious.

a)	After the centering is removed and curing period is over the slabs shall be put to 	test by stagnating  water of 15 cms  depth for one week and watched carefully to 	test the leakages if any.

b)	If there are any leakages, the contractor shall immediately rectify the same at     	his own cost and again test the same to see that there are no leakages. No 	payment will be made to the contractor on this account either for testing or for 	rectifications thus carried out.

c)	The officer observing the leakage test shall issue a certificate to this effect before 	final bill is made.

5.39.2	The variation thickness of R.C.C. roof slab due to varying spans, or special covering materials should not effect the general roof bed which should be uniform unless otherwise shown in drawings or instructed.

5.39.3	For all slabs to be laid MS hooks to be provided as directed by the department for fixing fans and lights etc., G.I. pipes or PVC pipes has to be provided as directed by the department in the masonry walls or concrete at the specified places  for making electrical wiring.

| TABLE – IV |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| For Vibrated Reinforced Concrete Items (V.R.C.C.) |  |  |  |  |  |  |
| Characteristic Strength of Cube at the age of 28 days of curing |  |  |  |  |  |  |
|  | M-25 | 1:1:2 | 25 N/mm2 | = | 250 Kgs / cm2 |  |
|  | M-20 | 1:1½:3 | 20 N/mm2 | = | 200 Kgs / cm2 |  |
|  | M-15 | 1:2:4 | 15 N/mm2 | = | 150 Kgs / cm2 |  |

5.40	Cement plastering in two coats CM 1:6 & CM 1:4 (APSS 901, 903 & 904)

5.40.1	The surface shall be prepared by roughening of the back ground and raking the joints. The surface of the wall shall be kept wet for 2 hours before plastering.

5.40.2	Guides: Patches of 15cm X 15cm of required thickness at not more than 2 meters intervals horizontally and vertically shall be applied over the entire surface truly in the plane and truly plumb to serve as guides.

5.40.3	Plaster shall be started from the top and worked down towards plinth. The work shall be tested frequently with a plumb bob and straight edge.

5.40.4	The Mortar in 1:6 proportion shall be dashed and pressed over the surface and then brought to smooth and uniform surface by means of float and trowel.  The plaster shall be well pressed into the joints.

5.40.5	After the first coat the surface is left rough to receive the second coat.  The final coat shall be applied a day or two after the first coat put on has set, but the first coat shall not be allowed to dry.  The final coat shall consist of 1 part of cement to 4 parts of fine sieved sand and shall be applied as in the first coat and brought to a uniform surface and then finished with a sponge to give granular appearance.

5.40.6	All corners, junctions and arises shall be brought truly to a line, level and plumb.

5.40.7	The finished surface shall be watered for a period of atleast 10 days.

5.40.8	Theoretical requirement of cement for plastering should be as follows:	Cement bags of 50 kgs.

a.	12 mm plastering in C.M. (1:5)& C.M. (1:3)	1.02 bags per 10 Sqm.

b.	12 mm plastering in C.M. (1:6)& C.M. (1:4)	0.82 bags per 10 Sqm.

c.	20 mm plastering in C.M. (1:6)& C.M. (1:4)	1.15 bags per 10 Sqm.

d.	12  mm  plastering  in  C.M.  (1:4)	1.08 bags per 10 Sqm.

e.	  12 mm plastering in C.M. (1:6)		         0.72 bags per 10 Sqm.

5.41	Water proof plaster over the roof

5.41.1	On the clean wet surface of the concrete slab, before it has set, a layer of cement plaster shall be laid to give an average depth of 20mm over the concrete.

5.41.2	The Mortar to be used shall be of CM 1:3 proportion mixed thoroughly with a standard water proofing material with water repelling properties to ensure non-absorption.

5.41.3	Gauges should be put on the floor about ten feet apart to ensure even thickness.

5.41.4	Plastering must be done in squares or strips to avoid cracks.  After the floor has been completed, it shall be covered with two inches of grass; sand or saw-dust and kept wet for three weeks.

5.41.5	Providing Chemical Water proof treatment 100mm thick with Brick bat coba & chemical cement mortars to exposed RCC roof slab surfaces to required slopes mixed with water proofing chemical compound, laid over roof slab and brickbat coba treatment in chemical cement mortar 120/100 mm thick at the centre and 80/60 mm thick at the edges finished smooth with a floating coat of chemical mixed cement mortar as per the manufacturer specification including cost and conveyance of all materials like sand, chemical water proofing compound, water etc., to site, including seigniorage charges and operational, incidental, and labour charges for mixing mortar, laying, lift charges, rendering smooth curing including rounding off junctions of wall and slab etc., complete for finished item of work.

5.42	Pointing: (APSS - 906)

5.42.1	Cement mortar for pointing shall conform to SS: 115 and shall be of 1:3 proportion.

5.42.2	The joints in the masonry shall be raked out to a depth not less than the width of the joint, when the mortar is green. Joints are to be brushed clean of dust and loose particles with a stiff brush. The area shall then be washed and the joints thoroughly wetted before pointing is commenced.

5.42.3	The mortar shall be pressed into the raked out joints according to the type of joint required. The mortar shall not be spread over the corners, edges or surface of the masonry.  The pointing shall then be finished with proper tool.  The superfluous mortar shall be cut off from the edges of the line and the surface of the masonry shall be cleaned of all mortar.

5.42.4	Pointing could be either flush pointing, or groove pointing.

5.43	Notes on pointing:

i) 	Flush pointing with a groove or a line appears neat and does not spoil the look of the stone or brick masonry.

ii) 	As far as possible a minimum amount of mortar shall be used to avoid wastage.

iii) 	The edges shall be neatly trimmed with a trowel and a straight edge.

iv) 	While mortar is green a groove shall be formed by running a tool along the center lines of the joints.  This operation shall be continued till a smooth and hard surface is obtained.

v) 	Even the vertical joints shall be finished in a similar fashion.

vi) 	Even when the job is done carefully, there is always an amount of superfluous mortar sticking to the masonry.  This should be wiped off with a wet cloth.

vii) 	After the work is set and dry i.e., after one or two days the stones shall be cleaned with a strong acid so as to remove the cement stains.

viii) 	After cleaning with acid the stones shall be cleaned with soap water to ensure natural colour of the stones.

ix) 	If care is taken as shown above the pointing work will look attractive and neat, and the natural appearance of the stone masonry is retained.

5.44	Flooring: (APSS 701 & 702)

5.44.1         Granite Flooring:

Flooring shall be with high polished colour granite stone slabs 18 to 20 mm  thick of size not less than 2.40 mts length, laid over existing RCC slab or CC bed.

All the stones in one room shall be preferably of same width and shade. The width of all the slabs in one row must be uniform with longitudinal joints parallel to each other.

The joint width shall be kept minimum and the sides of the slab shall be chisel dressed to ensure a correct joint.

Raw-silk- pink granite			Red-multi colour- granite

Imperial- red- granite		               Kashmir- gold- granite

5.44.2 	Granolithic concrete flooring (APSS No. 701 & 710)

The mix proportions for the Granolithic concrete floor topping shall be (1:2:4) (Cement: F.A.: C.A) by volume. The minimum amount of water which will give necessary workability for adequate compaction shall be added. The grading of the course aggregate for Granolithic concrete shall be from 6mm to 12mm. The finished thickness of flooring shall be 50mm thick or as specified in the approved drawings and the panels into which the floor is divided for laying the Granolithic concrete shall not have any panel dimensions in excess of 5.0m.

5.45	Joinery:

For all wood/iron/ Aluminium work a sample of each item i.e., frame with shutters complete should be prepared and got approved by the Engineer-in-Charge before they are manufactured in full quantities and fixed in position.

The furniture and fixtures and wind appliances for wood work should be of best quality available in the market, and should be got approved by the Engineer-in-Charge before fixing.

5.46	Door Frame:

Wooden Doors & Windows:

The wood shall be of Best Sal wood//1st class teak wood/2nd class Teak wood as specified in Bill of quantities for frames and shutters.

The wood shall be well seasoned, uniformly coloured and shall be free from knots, cracks, shakes, splits, cross grains etc.

The wood shall be durable and of reasonably straight grains.

Moisture content of the wood used shall be as near as possible to the following values:

Recommended values of moisture content in timber at the time of assembly or framing.

Type of work	Coastal area	Inland area

Frames of windows	16 to 18%	14 to 15%

Shutters of windows etc.	15 to 16%	12 to 14%

Construction and fixing

Frames shall have dovetail, tenon or mortise joints.

Before fixing in position, the frames shall be inspected and passed by the Engineer-in-charge. A coat of primer shall be applied before the frames are fixed in position. All portions of untreated timber abutting against masonry or concrete shall be painted with boiling coal tar or approved preservative, before placed in position.

The frames shall be erected in position and held plumb with strong supports from both sides.

Hold fasts shall be embedded in C.C. beds as specified.

Frames shall have dovetail, tenon or mortise joints.

Frames without sills shall be provided with temporary wooden bracings between the styles at sill level which can be withdrawn after the frame is firmly set.

5.47	Steel Door frames:

M.S. Hollow door frames manufactured by cold roll formed process steel sheet 1.25mm thick bright CRCA confirming to IS 4351-1976 with                   105 x 60mm size.

5.48	Fabrication: The steel door frames shall be got fabricated in an approved workshop as approved by the Engineer.

5.49	Mortar Guards: Mortar guards as instructed by the Engineer-in-charge shall be provided. These shall be welded to the frame at the head of the frame for double shutter doors to make provision for bolts.

5.50	Lock-Strike Plate: There shall be an adjustable lock- strike plate of steel complete with mortar guard to make provision for locks or latches complying with the relevant Indian Standards. Lock-strike plate shall be of galvanised mild steel and fixed at 95cm from the head of the frame.

5.51	Shock Absorbers : For side hung door there shall not be less than three buffers or rubber or other suitable material inserted in holes in the rebate and one shall be located on the centre line of the lock strike plate and the other two at least 45cm above and below the centre line of the lock strike plate. For double shutter doors, there shall be two buffers of rubber or similar suitable material inserted in holes in the rebate in the lock jamb only at the head and spaced 15cm at either side of the centre line of the door.

5.52	Finish: The surface of door frame shall be thoroughly cleaned, free of rust, mill-scale dirt, oil etc. either by mechanical means, for example, sand or shot blasting or by chemical means such as picking. After pretreatment of the surface one coat of approved primer i.e. red oxide zinc chrome primer conforming to Ito 2074:79 and two coats of paints as directed by the Engineer-in-charge shall be applied to the exposed surface.

5.53	Fixing: frames shall be fixed up right in plumb. To avoid sag or bow in width during fixing or during construction phase, temporary struts across the width preventing sides bulging inward may be provided.  Wall shall be built solid on each side and grouted at each course to ensure solid contact with frame leaving no voids behind the frame. The Hollow frame section shall be filled with CC (1:2:4) using 20mm grade HBG metal. Three lugs shall be provided on each jamb with spacing not more than 75 cm. The temporary struts should not be removed till the masonry behind the frame is set. In case screwed base tie is provided, this should be left in position till the flooring is laid when it can be removed. After pretreatment of the surface, one coat of steel primer and two coats, of paint, as directed by the Engineer-in-charge shall be applied to the exposed surface.

5.54	Flush shutters for doors:

5.54.1	Flush shutters (Double/Single) : should be factory made ISI marked confirming to IS 2202-1991 (part-I), 35mm thick with bond wood solid block board type core having cross bonds and face veneers hot pressed bonded with water proof phenol formaldehyde synthetic resin, with lipping on all sides.

5.55	Construction: The block board core shall confirm to the requirements specified in clause 7.1.1 of IS 2202 (Part I) : 1991. The frame constructed of stiles and rails shall be provided for holding the core. The width of the frame including internal lipping shall not be less than 45 mm and not more than 75 mm.

5.56.1	Plywood: used in flush door shutter shall confirm to IS 710: 1976 with surface requirements confirming to type AB of IS 303: 1989.

5.56.2	Cross-bands used in flush door shutter shall confirm to the requirements laid down in IS 710:1976.

5.57.1	Face Veneers: used in flush door shutters shall confirm to the requirements laid down for veneer for BWP grade plywood in IS 710:1976.

5.57.2	All Plywood, cross – boards and veneer used shall be treated in accordance with clause 6.1.5.1. of IS 2202 (Part I) : 1991.

5.57.3	Adhesive used for bonding plywood or cross bond and face veneer to core shall be phenol formal dehyde synthetic resin adhesive confirming to BWP grade specified in IS 949:1974.

5.57.4	Internal lipping shall be of Teak wood and shall have a total depth not less than 25mm. It may be provided separately, when it is of species different from that of backing or as one piece with the style, designated as frame-cum-lipping, when internal lipping and backing are of the same species.

5.57.5	External lipping shall be of teak wood and shall be solid and shall measure at least 6mm on the face of the door. It shall be provided all round the shutter in case of single shutter and on three sides in case of double shutter.

5.57.6	In case of double leaved shutters, the sheeting of the stiles shall be rebated by 8mm to 10mm. The rebating shall be either splayed or square type as per clause 7.7 of IS 2202 (Part – I) : 1991. The depth of lipping at the meeting of stiles shall not be less than 30mm.

5.57.7	Shutter shall be shop prepared for taking mortise locks or latches as may be ordered.

5.57.8	Workmanship and the finish of the face panels shall be in confirmity with those specified in IS 303:1989

5.58       Tests: Knife test, glue Adhesion test, End Immersion test, slamming test shall be carried out as per clause 10 of IS 2202 (Part – I) 1991. The sampling and criteria for conformity, making etc. shall also be as per IS 2202 (Part – I) : 1991.

5.59         Windows

5.59.1      Seccolar Systems

- Windows / Ventilator

Windows / Ventilators fabricated from pre painted Steel Sections, made out of cold rolled steel as per ISD 513 of 0.6mm thick ‘D’ quality, galvanized as per IS 277 with sinc of 120 gm/sq.mtr. Primer Coat of Epoxy Primer of 7 microns thick, finish paint with a modified polyster paint of thickness between 13 – 20 microns, and back coat with Alkyd/Polyster of 7-12 microns. The size of profiles is approximately 56 x 46mm for internal shutter frames and 46 x 52mm for External shutter frames. Shutter in fitted with 4mm thick plain/pinheaded glass fixed with EPDM gaskets in the groove provided in the profile.

- Doors

Doors fabricated from Pre-Painted Steel Sections, made out of Cold Rolled Steel as per IS 513 of 0.6mm thick ‘D’ quality, galvanized as per IS 277 with zinc of 120gm/se.mtr. Primer Coat of Epoxy Primer of 7 microns thick, finish paint with a modified polyster paint of thickness between 13-20 microns, and back coat with Alkyd/Polyster of 7-12 microns. The size of profiles is approximately 46 x 46mm for Internal Shutter frames and 46 x 52mm for External Shutter frames, middle and bottom jambs of size 23 x 130mm and panels filled with Glass/Board.

5.60        ALLUMINUM DOORS, WINDOW & VENTILATORS:

(i) 	Aluminium doors, windows and ventilators: All extruded aluminium section to be used for fabrication shall be hollow aluminium alloy extrusions   confirming to designation 63400 of IS: 1285. Aluminium Doors, Windows and Ventilators shall confirm to IS 1948:1961

(ii)   All extruded aluminium sections and fixtures shall be coated with natural   colour      anodic coating in accordance with IS 1868.

(iii)  The mortice locks shall be provided in accordance with IS 2209.

(iv) The floors springs (hydraulically regulated) shall be in accordance with IS 6315:1992.

5.61	Q.C. Clearance: The doors & windows (both frames & shutters) and ventilators should be got cleared by the Engineer / Quality Control agency authorised by the Engineer-in-Chief. The tests will be conducted at the manufacturer’s place and Q.C. clearance certificate will be issued for the lot before supply to site for use in construction. All the arrangements for testing at the manufacturer’s place should be made by the contractor at his cost. No door, window or ventilator should be fixed without clearance of Engineer/ Q.C. agency. The contractor should inform the Engineer/Q.C. agency for testing and clearing at least 7 days in advance.

6.0        	Additional Specifications:

6.1	Anti Termite Treatment

If the site is infected with white ants, all the ant hills shall be dug out completely and queen ants destroyed. Anti-termite treatment, before construction in foundation and basement where required shall be done as per I.S. code 6313 Part II 2001.

Chemicals used, the relevant I.S. specifications for the same and their usual concentrations as water emulsions for soil treatment shall be as given in table 201.9 of S.S. 201 APSS.

6.2	       Structural Glazing:

The structural glazing shall be made up of electro colour anodized (having 15 micron anodic coating) aluminium structural sections of not less than   101.5 x 57 x 2 mm box sections for all mullions and not less than 63 x 57 x 2 mm box section for all transoms of structural glazing system and sub frame of 26.5 x 20 x 1.8 mm size. The members shall be fixed in grid pattern mechanically joined with Aluminium cleats and GI metal screws. The frame shall be fixed to the beam / slab/ soffit with GI brackets and fasteners. Glazed panels shall be made using 5 mm thick heat strengthened reflective glass of St.Gobain / Glaverbel / Equivalent  make fixed to the sub frame with 6 x 12mm spacer tapes of Norton make or equivalent and structural silicone bonding using G.E. SILICONE (SSG 4000)  or DOW CORNING (795). The gaps between glazed panels shall be sealed with suitable Bakor rod and Silicon weather sealant of GE / DOW CORNING are to be applied to provide water tightness of glazing frame. Necessary masking tapes are to be used to prevent spreading of sealant over glass panels.

6.3	ACP Cladding:

a)	Providing, Designing, cutting, bending and fixing aluminium composite cladding 4mm thick of approved make (Alucopanel, alucobonel, Reynobond, Lennox Durabuid) on external facade of size as shown with water tight system either curved or straight on concrete/ masonry surfaces skin  material 0.25 mm thick aluminium sheet (300 5 H6)  cover material natural polyethylene aluminium cladding panel to be of approved colour / shade fixed with extruded aluminium basis frame (50x25x1.5mm) angle cleats, weather sealants, rivets, GI brackets all as approved, using suitable chemical/ anchor bolts on structural steel work including necessary accessories complete in all  respects, where level difference is shown dummy structural steel backup frame shall be provided including the finished surface shall be protected with 80 microns self adhesive peel off film with two layers of white and black tested to withstand at least 6 months exposure to local weather condition, without loosing the original peel off characteristic or causing stains or other damages with silicon sealant of Dow Corning 789 or Wacker EL 305 or GE etc., including all scaffolding and labour charges etc., complete for finished item of work

b)	Providing, Designing, cutting, bending and fixing aluminium composite panel cladding of approved make (Alstrong legame, Reynobond, Alpolic, Alcomat) on external facade of size as shown with water tight system either curved or straight on concrete/ masonry surfaces the panel should be of 4 mm thick with combination of aluminium skin  material of 0.5 mm thick aluminium sheet of alloy grade 3105 H 14  cover material natural polyethylene aluminium cladding panel coated on external side with PVDF (Poly Vinyledene Fluoride) of KYNAR PVDF coating containing 70% KYNAR 500 resins for anti-fungal & anti bacterial properties and the central core should be with opaque/ white polyethylene virgin grade, UV stabilized with a combination of 70% LDPE grade 22 FA 002 and 30% HDPE grade E5201and the core should be bonded to the aluminium skin on both sides with DUPONT adhesive film of 30 to 50 μ  to be of approved colour / shade fixed with extruded aluminium basis frame (50x25x1.5mm) angle cleats, weather sealants, rivets, GI brackets all as approved, using suitable chemical/ anchor bolts on structural steel work including necessary accessories complete in all  respects, the surface protection with 80 microns self adhesive peel off film with two layers of white and black tested to withstand at least 6 months exposure to local weather condition, without loosing the original peel off characteristic or causing stains or other damages with silicon sealant of Sil Proof NB/ Wacker EL 305 or Dow Corning 789 or Wacker EL 305 or GE etc., including all scaffolding and labour charges etc., excluding cost of structural steel backup frame complete for finished item of work

6.4	Aluminium Louvers:

Supply and fixing of powder coated (approved shade) Aluminium Louvers, using 63 x 37 x 1.5mm, Aluminium box section for main frame, the aluminium louver blades of size 103 x 50 x 1.5 mm thick shall be fixed to the main frame using G.I sheet metal screw as shown in the drawing. The spacing between the each louver blade shall be 75 mm.

6.5	Blasting Operations

Blasting operations when considered necessary shall be resorted to only with written permission of the Engineer-in-charge.  Where blasting is resorted to only small charges shall be used. Prior inspection shall be carried out for the safety and stability of the public property.  Blasting operations in the proximity of over head power lines, communication lines,  or  other  structures  shall not be  carried until the operator or the owner of both of such lines have been notified and precautionary measures deemed necessary shall be taken as per the procedure laid down in S.S. No. 203 APSS and code 4081-1986 shall be followed.

Excavation in Hard rock y chiseling:

This includes rock which is easily excavated by blasting, but due to close proximity of structures or any other reason that the Engineer-in-charge may consider, will have to be excavated by chiseling.

The contractor may resort to any of the following methods to excavated rock by chiseling:

(i) Wedging by means of crowbars, pick axes or pneumatic drills

(ii) Heating and quenching

(iii) Controlled blasting with a small charge just sufficient to make a crack in rock which will be subsequently removed by wedging.

No extra payment shall be made for removal of rock by chiseling and controlled blasting.

6.6	a)	Expansion Joints

GENERAL

a)  The expansions joints shall be designed and duly got approved by the Engineer. It shall cater for expected movement and rotation of the structure at the joints and provide smooth riding surface. It shall also be easy for inspection, maintenance and replacement.

b)  Expansion joints shall be robust durable water-tight and replaceable.  Fabricated expansion joints shall be prohibited. Expansion joints shall be obtained by the Engineer either directly or through the Contractor from approved manufacturers and be of proven type.

Structures in which marked changes in plan dimension take place abruptly shall be provided with expansion joint at the section where such changes occur.  Expansion joint shall be so provided that the necessary movement occurs with a minimum resistance at the joint.  The structures adjacent  should preferably supported on separate columns of walls but not necessarily  on separate foundations reinforcement shall not  extend across an expansion joint and the break  between the sections shall be complete.  The  details as to the length of a structure where  expansion joints have to be provided can be determined after taking into consideration various factors such as temperature exposure to weather etc.  For the purpose of general guidance however it is recommended that structure exceeding 45M in level to shall be decided by one or more expansion joints (SS No. 403.8 & IS 456).

This work shall consist of fabrication and placing of expansion joints as indicated on the drawing and conforming to these specifications or as directed by the Engineer.

The expansion joint shall:

a) Withstand the imposed load including the impact load from live load and sources.	.

b) Allow expansion and contraction movement due to temperature. Creep shrinkage, pre stressing and structural deformations.

c) Permit relative rotation in elevation and plan due to the causes as noted above.

d) BE WATER PROOF bridge deck expansion joint seals play critical role in preventing the degradation of the structural components of the bridge system. Without effective joint seals. water passes through the bridge deck and works harmfully to corrode steel components and causes deterioration of the concrete. Rain water gathers various corroding additives from the atmosphere and also from the carriageway.

e)	Construction Joints

Vertical joints in floor and roof slabs shall be provided in the case of long building of more than 30M in length specially when the width or depth of such buildings are less than 15M and when narrow corridors connect blocks of relatively greater width. The most suitable position for such vertical joints are where the corridors take off from inner blocks. On soils such as black cotton, such joints are more essential shall be invariably provided at the places shown in the drawing or as directed by the Engineer-in-charge. Construction joints  when  necessary  shall  be located as follows.

In the main beam over the centre of support. No vertical joint shall be permitted in case of main beams.  In other cases they shall be provided if necessary in the following location.

i)	In subsidiary beams at mid span.

ii)	In the case of slabs the joints wherever possible shall be parallel to main reinforcement. In the case of one way reinforced slabs and over the centre of supporting beams or walls in other cases.  In general the  joints  shall not be provided in locations of considerable shear or under concentrated loads.

Suitable water stops as specified shall be provided in the case of water retain structures (SS No. 403.7).

6.7	Bearings of R.C.C slabs & beams

a) 	Where supports are not monolithic with the beam or slab the bearing surface shall be plastered with cement mortar 1:3 with the craft paper laid over the plaster, before laying the concrete.

b) 	The vertical face of the masonry rebate at bearings shall be plastered smooth with CM 1:3. For beams the craft paper shall be continued to the sides by folding the paper neatly to the plastered vertical face of the masonry opening.

6.8        	Load testing of structures

Load testing of structures shall conform to SS No. 403 APSS.  Load tests on completed structures shall be made of required by the specifications or condition of contract or by the Engineer-in-Charge in the event of reasonable doubt as to the adequacy of the strength of the structure.  Such tests shall be carried out after expiry of 56 days of effective hardening of the concrete test loading of structures, allowable deflections, recovery of deflection etc., shall be as per clause 17.6 of IS: 456-2000.

7.0  	Safety specification:

7.0.1	All the necessary safety appliances as per IS: 4130 shall be issued to  the  workers  and  their use explained. It shall be ensured that the workers are using all the safety appliances while at work.

7.0.2	Walkways and passageways shall be provided for the use of the workman who shall be instructed to use them and all such walkways and passageways shall be kept adequately lighted, free from debris and other materials.

7.0.3	During night, red lights shall be placed on or about all the barricades.

7.0.4	All the roads and open area adjacent to the work site shall either be closed or suitably protected.

7.0.5	All nails in any kind of lumber shall be withdrawn, hammered or bent over as soon as such lumber is removed from the structure and placed in pipes for future cleaning or burning.

7.0.6	No electric cable or apparatus which is liable to be a source  of  danger or a cable or apparatus used by the operator shall remain electricity charged.

7.0.7	Where in any work of demolition it is imperative, because of danger existing to ensure that no unauthorized person shall enter the site of demolition outside working hours, a watchman should be employed. In addition to watching the site, he shall also be responsible for maintaining all notices, lights and barricades.

7.0.8	On every demolition job, danger signs shall be conspicuously posted all-round the structure and all door openings giving access to structure shall be barricaded or marked except during the movement of actual workmen or equipment. However provision shall be made for at least two  independent exits for escape of workmen during any emergency.

7.0.9	The removal of a member may weaken the side wall of an adjoining structure and to prevent possible damage, these walls shall be supported until such time as permanent protection is provided. In case any danger is anticipated to the adjoining structure the same shall be got vacated to avoid any danger to  human life.

7.0.10	The power on all electrical service lines shall be shut off and all such lines cut or disconnected at or outside the property line, before the demolition work is started.  Prior to cutting of such lines the necessary approval shall be obtained from the electrical authorities concerned for demolition work itself.

7.0.11	All gas, water, steam and other service lines shall be shut off and capped or otherwise controlled at or outside the building line, before demolition work  is started.

7.0.12	All the mains and meters of the building shall be removed or protected from damage.

7.0.13	If a structure to be demolished has been partially wrecked by fire, explosion or other catastrophe, the walls and damaged roofs shall be shored or braced suitably.

7.0.14	All practical steps shall be taken to prevent danger to persons employed from risk of fire or explosion or flooding. No floor, roof or other part of the building shall be so overloaded with debris

SCHEDULE – “D”

MATERIALS AND WORKMANSHIP

1.1. GENERAL

1.1.1 a) No Material shall be used for construction in any work until notice has been given by the Executive Engineer that the test results are satisfactory. No oral instruction should be followed.

b) Recommendation of stacking and storage of construction materials at site shall be in 	accordance with IS: 4082 - 1977.

c) To be of the best Quality: All materials, articles, and workmanship shall be the best of their respective kinds for the class of work described in the contract specifications and schedule. The word 'best' as used in the specifications shall mean, that in the opinion of the Executive Engineer there is no superior quality of material or finish of articles on the market and that there is no better class of workmanship available for the nature of the particular item described in the contract schedule. The contractor shall upon the request of the Executive Engineer, furnish him with the vouchers to prove that the materials are such as are specified.

1.1.2 The tenderer has to do his own testing of materials and satisfy himself procure the required construction materials of approved quality including the earth for formation of embankment and water from quarries/sources of his choice. All such quarries / sources of materials required for the work shall be got approved by the Engineer -in - charge in writing well before their use on the work. The materials as per standards of relevant I.S.I. codes only will be accepted.

1.2.   	Samples:

1.2.1 	The representative samples of all materials should be procured by the contractor and arrange to send them to the Engineer - in -charge for conducting preconstruction tests and approval duly informing the source of materials from where he has collected the samples.

1.2.2 	 The raw and processed samples should be supplied at the contractor's expense to the Engineer - in -charge within 14 days after signing of the agreement. For testing of samples maximum of 60 days time will be required. Each sample shall approximately consist of 100 kgs. of materials, or as directed by the Engineer - in - charge.

1.2.3	 If the contractor desires to change the sour of materials, he shall supply the raw and processed representative samples at his own expense to the Engineer - in - charge at least 60 days before its use for pre  construction tests and approval.

1.2.4 In addition to pre - construction tests and approval of quarries, the Engineer may test the aggregate for their suitability during their processing. The contractor shall provide such' facilities as may be necessary for contractor shall provide such facilities as may be necessary for procuring at no extra cost representative samples at the aggregate processing plant and at the batching plant. Final acceptance of the materials will be based on the acceptable test results of samples taken from the construction site only.

1.2.5 	The contractor has to bear the cost of raw and processed representative samples, laboratory tests and filed tests. The contractor has to arrange the required men and material for collecting the samples and bear the cost thereon required for transporting them to the laboratory also. The contractor should quote his rates for finished item of work for the items of works of Schedule 'A' keeping in view the cost of pre and processed samples to be submitted to the Engineer and also the rate of progress and the time required for conducting laboratory tests. No extension of time will be granted for any delay occurred in collecting the samples and conducting pre - construction tests in the laboratory and getting approval.

1.3.  Procurement:

1.3.1 The rates quoted for all items shall include cost and conveyance of all materials with all    leads.

1.3.2 It will be the tenderer's responsibility to satisfy him self that sufficient quantities of construction materials required for the works shall exist in the borrow areas or quarry sites. The Dept. does not accept any responsibility either in handing over the quarries or procuring the materials or any other facilities. The tenderer will not be entitled for any extra rate or claim for the misjudgment on his part for quantity and quality of materials available in the quarries.

1.3.3 Failure by the tenderer to have done all the things, which in accordance with this condition, he is deemed to have done, shall not relieve the successful tenderer of the responsibility for satisfactory completing the works as required at the rates quoted by him.

1.3.4 The contractor shall make his own enquiries degrading the availability of other materials and make his own arrangements for procuring them.

1.3.5 The materials for embankment construction shall be obtained and got approved by the Engineer- in - charge. The responsibility for arranging and obtaining the land for borrowing or exploitation in any other way shall rest with the contractor, who shall ensure smooth and uninterrupted supply of materials for the quantity required in construction during the construction period. No separate cost will be paid.

1.3.6 Similarly, the supply of aggregates' for construction shall be of approved quality approved by the Executive Engineer. Responsibility for arranging uninterrupted supply of materials from the source shall be that of the contractor. No separate cost will be paid.

1.3.7 The contractor has to open and develop the quarry for the stone and aggregate required. All incidentals such as removal of over burden, stripping etc., in the quarry should be done by the contractor. The contractor shall make his arrangements for maintaining the approach roads to quarry for conveying the materials to site of work.

1.3.8 The contractors have to make their own arrangements for storage and conveyance of water and storage at work site for construction purpose, no extra payment will be made to the contractor over and above their tender rates for water lead for storage arrangements.

1.3.9 The tenderer should inspect the site and check-up the possible water source for carrying out the entire work throughout the year in monsoon and non-monsoon seasons irrespective of the quantum of rainfall and quote their rates accordingly. No subsequent claims for extra. water lead will be entertained under any circumstances.

1.3.10 The materials and labour utilized in the execution of work by the contractor shall not be less than that given in the AP.P.W.D. standard data for the relevant item.

1.3.11. Lay-out of material stacks: The contractor shall deposit materials for the purpose of the work on such parts only of the ground as may be approved by the Engineer-in-charge. He shall submit, for the approval of the Executive Engineer, before starting work, a detailed site survey clearly indicating positions and areas where materials shall be stacked and sheds built.

1.4. DEFECTIVE MATERIAL:

1.4.1 All materials which the Executive Engineer/his representative has determined as not conforming to the requirements of the contract will be rejected whether in place or not. They shall be removed immediately from the site as directed. Materials, which have been found defective, and which have been subsequently corrected, shall not be used in the work unless approval accorded in writing by the Engineer-in-charge. Upon failure of the contractor to comply with any order of the Engineer-in-charge, given under this clause, the Engineer -in-charge shall have authority to cause the removal of rejected material and to deduct the removal cost thereof from any money due to the contractor.

1.4.2 The rejected rubble and spoils should be dumped far away from work spot as directed by the Engineer-in-charge. The muck, boulders etc., fallen on the approach roads, ramps, etc. below the place should be removed by the contractor immediately after blasting at the contractor's cost. In case the above materials are not cleared within 24 hours of issue, of departmental instructions, the same will be removed by the Dept. and the cost thereof will be recovered from the Contractor's bills.

1.4.3. The Dept. will not be liable for any compensation due to breakdown in .machinery, water supply or electricity or dealer in supply of materials and for damage due to rains and floods.

1.4.4. The Executive Engineer shall have power to reject at any stage, any work which he considers to be defective in quality of material or workmanship and he shall not be debarred from rejecting wrought materials by reason of his having previously passed them in an unworked condition. Any portion of the work or materials rejected or pronounced to be infer; or not in accordance with the drawings and specifications shall be taken down and removed from the work-site at the contractor's expense, within 24 hours after written instructions to that effect have been given by the Executive Engineer. Replacement shall at once be made in accordance with the specifications and drawings, at the Contractor's expense.

1.4.5. In case of default on the part of the Contractor to carry out such orders the Executive Engineer shall have power to employ and pay other persons to carry out the orders at the contractor's risk and all expenses consequent thereon and incidental thereto shall be borne by the contractor.

1.4.6 Executive Engineer's decision: To prevent dispute and litigation, it shall be accepted as an inseparable part of the contract that in matters regarding materials, workmanship, removal of improper work, interpretation of the contract drawings and contract specifications, mode of procedure and the carrying out of the work, the decision of the Executive Engineer shall be final and binding on the Contractor and in any technical question which may arise touching the

contract, the Executive Engineer's decision shall be final and conclusive. In the case of any difference between Executive Engineer and Contractor on matters regarding materials, workmanship, removal of improper work, interpretation of contract drawings and contract specifications, mode of procedure and the carrying out of the work the contractor shall have a right of appeal to the next higher Authority viz., the Managing Director of the circle, and the decision of the latter shall be final and conclusive.

TEST INSPECTION AND REJECTION OF DEFECTIVE MATERIAL AND WORK:

1.5. LABORATORY SET UP :

1.5.1. For the works costing Rs.50.00 Lakhs and above the contractor shall setup a laboratory and equip the same with adequate equipment and personnel in order to carry out all require tests and Quality Control work as per specification s or as directed by the Engineer. The internal layout of the laboratory shall be as given in the drawing and list of equipment shall be got approved from the Engineer in advance.

1.5.2. “The cost of laboratory building including services, essential supplies like. water, electricity, sanitary and their maintenance and cost of all equipment, tools, materials, labour and incidentals to perform tests and other operations of quality control according to the specifications requirement shall be deemed to be incidental to the work and no extra payment shall be made for the same."

Laboratory Equipment:

The following items of laboratory equipment shall be provided in the field laboratory.

(i) Over - Electrically operated,

thermostatically controlled, range

upto 200° C sensitivity 10C								1 No.

(ii) P1atform balance 300 kg capacity 						1 No.

iii) Balance 20 kg capacity - self indicating type 					1 No.

(iv) Electronic Balance 5 kg capacity accuracy 0.5 gm. 				2 Nos.

v) Water bath-electrically operated and						1 No.

thermostatically controlled with adjustable shelves,

sensitivity 1°C

(vi) Thermometers:									3 Nos.

Mercury-in-glass thermometer range

00 to 2500  C

Mercury-in-steel thermometer with 30 cm stem.

range upto 300° C

(vii) Kerosene or gas stove or electric hot plate					1 No.

(viii) Glass wares spatulas, wire gauzes.					As required

steel scales measuring tape, casseroles.

Karahis enameled trays of assorted sizes.

pestle mortar, porcelain dishes gunny bags.

plastic bags chemicals digging tools like

pickaxes, shovels etc.

(ix) Set of IS sieves with lid and pan :

450 mm diameter:		1 set

63 mm, 53 mm, 37.5 mm, 26.5 mm. 13.2 mm, 9.5mm,

6.7 mm and 4.75 mm size

200 mm diameter:									2 Sets.

2.36 mm, 2.0 mm, 1.18 mm, 600 micron, 425 micron,

300 micron, 150 micron, and 75 micron

(x) Water testing kit									1 Set.

(xi) First aid box 									1 set.

5.3.2 For soils and aggregates

(i) Riffle Box										1 No.

(ii) 	Atterberg Limits (liquid and plastic						1 Set.

limits) determination apparatus

(iii)  	Compaction Test Equipment both 2.5 Kg. and 4.5 Kg

rammers (Light and heavy compactive efforts)				1 Set.

(iv)  	Dry Bulk Density Test apparatus (sand pouring

cylinder, tray, can etc.,) complete						1 Set.

(v)	Speedy Moisture master complete with chemicals				1 Set.

(vi)	Post hole Auger with extensions						1 Set.

(vii)	Core cutter apparatus 10 Cm. dia, 10/15 Cm.

height, complete with dolly, rammer etc.,					1 Set.

(viii)	Aggregate Impact value test apparatus / Los Angeles,			1 Set.

Abrasion Test apparatus.

(ix)	Flakiness and Elongation Test Guages					1 Set.

(x)	Standard measures of 30, 15 and 3 litres capacity				1 Set.

along with standard tamping rod.

(xi)	California Bearing Ratio test apparatus					1 Set.

(xii)	Unconfined compression test apparatus					1 Set.

1.5.3.4. For cement and cement concrete

(i)  Vicat apparatus for testing setting times	1 Set

(ii)  Slump testing apparatus	4 Sets.

(iii)  Compression and Flexural strength testing machine	1 No.

of 200 tonne capacity with additional dial for flexural testing.

(iv)  Needle Vibrator	2 Nos.

(v)  Air meter	1 No.

(vi) Vibrating hammer for vibrating dry mix as for Dry, 	1 No.

Lean Cement concrete sub-base.

Note :-  The items and their numbers listed above in this clause shall be decided by the Engineer as per requirements of the project and modified accordingly.

1.6 STANDARD TESTS AND QUALITY:

1.6.1 The day to day and periodical tests to be carried out on materials, finished or otherwise shall be specified by the Engineer-in-charge from time and the contractor shall allow all facilities and co-operation towards collection of samples and cores etc., The contractor shall however make good at his cost, materials, mixes and cores with similar or other materials as may be directed and the satisfaction of the Engineer-in-charge.

1.6.2 An authorized representative 'of the contractor shall remain present at the time when the samples or cores etc., are taken shall authenticate the fact if so required. Should the contractors agent, fail to be present as aforesaid the samples or cores etc., taken by the Engineer-in.-charge, or his representatives shall be considered to be authentic. The contract or to however will be informed of the details of such samples and cores etc., having been taken.

1.6.3 The material, mixes and cores etc., shall be tested day to day periodically at the laboratory available at the site or at other laboratory or place that the Executive Engineer may direct and the results given thereby shall be considered correct authentic by the contractor. It shall then be the contractor's responsibility to execute work to the standard based on the laboratory designs and tests.

1.6.4 The contractor shall provide proper facilities at all times, for the testing of materials, and inspection of work by the Engineer-in-charge, and the Engineer-in-charge shall accordingly also have access at .all times to the place of storage or manufacture where materials are being made for use under the contract to determine that manufacture is proceeding in according with the drawings and specifications.

1.6.5 The contractor shall, upon demand, also forward for the Executive Engineer's inspection, test certificates supplied by the vendors, when he is purchasing consignments of cement, steel and other materials in respect of which such certificates are usually available.

DRILLING AND GROUTING:

General:

The specifications provide for drilling of "A" and "B" holes and grouting of "A" and "B" holes with cement slurry for foundation treatment.

8.1. A LIST OF IS CODES APPLICABLE IS FURNISHED BELOW:

01	IS 6066-1984	Recommendations of pressure grouting of ROCK

FOUNDATIONS in river valley projects.

02    IS 5441-1986 		Portable pneumatic drilling machine

03    IS 2529-1973 		Code of practice for in-situ permeability tests

8.2 a) Drilling and grouting shall include drilling holes, washing of holes, washing of seams, fixing of grout pipes of packers for stage-wise grouting, grouting with cement grout and back filling of holes.

b) The purpose of grouting is to consolidate the foundations and to reduce seepage through the foundations and uplift pressures under the structure. The Programme of grouting prescribed herein, consists first of a low pressure shallow grouting for consolidating and improving the stability of the upper portion of foundation rock followed by a high pressure curtain grouting to create a tight a tight curtain which will cut off any paths of percolation.

c) Drilling and grouting of foundations is inclusive of washing and testing of permeability. The curtain grout holes for foundations treatment will be drilled to a depth and spacing of holes as shown on the drawings of or as directed to geologist of Geological survey of India and holes shall be drilled and grouted after the completion of excavation and prior to placing masonry or' concrete. But if grouting to be done after construction of masonry or concrete for 3.0 metre height 65 MM/O.M.S. Black Steel Pipes should be left in masonry or concrete. The pipes will be procured by the contractor and the contractor shall fix the pipes vertically in position and see that no damage occurs to them while laying masonry. In case the verticals is maintained for pipes before drilling and grouting operations are taken up, drilling through masonry shall be done by the Contractor.

8.3. EQUIPMENT:

a) Drilling Equipment: Grout holes will be drilled with standard core drilling equipment. Plug or non coring bit may also be used. Where consolidation or blanket grouting is to be done from the foundation surface, in rock which does not produce mud slurries, percussion, drilling in lieu of rotary drilling may be used for shallow holes.

1) Creations pneumatic or electrical driven diamond drill machine and its equipment. 2) Deep hole jack hammer with 80'.0" drill capacity and its equipment.

or pipe of not less than 40mm in diameter and return line not less than 40mm in diameter. Wherever practicable the grout plant shall be placed as near the hole as possible and along pipe lines avoided especially during hot weather. The flow of grout into the holes at a constant speed of the pump shall be controlled by the return valve on the header, by passing and returning to the agitation all grout, not accepted by the hole at the desired pressure. As the grout hole approaches refusal, or when the valves on the holes are closed for any reason, the pump shall continue in full operation, circulation the grout through the line to prevent setting or clogging. Both the pump and the pipe line shall be flushed periodically with clear water during grouting operations,.especial1ywhen using thick grout. Deposits of grout in the pump mixer and agitator not removed by flushing shall be cleaned out, once a week, by scraping and chipping. Upon the completion of any continuous operation or at such time as found necessary, the pump grout lines heads, cap and mechanical expander shall be dismantled, thoroughly cleaned with water and blown out with air.

e) The mixer shall be provided with an accurate meter, for controlling and measuring the amount of mixing water in the grout. Specially equipped pressure gauges shall be provided with diaphrams or by filling a shot gauge tube in the form of a "Pigtail" with semi fluid water proof grease and oil or other devices to prevent the entrance of grout in the gauge. The combined ranges of the high pressure gauge shall be 0.035 Kg/Sq.CM/.500 PSI and for low pressure gauges shall be 0.0175kg/Sq:CM/O.250 P-I one of the pressure gauges shall be

mounted so that it will measure directly the pressure on the hole and shall preferably be mounted directly on the vertical pipe of the head connected to the grout cap or expanding packer the other gauge shall be mounted on the supply line at the pump.

8.4 DRILLING GROUT HOLES AT FOUNDATIONS:

a) Low pressure Grouting: The procedure for grouting of the foundation will be subject to modification as determined in the field, but in general, will consist of.

1. Drilling the holes of diameter 75 MM to 50 MM to the required depth at a time except in the cases where shattered rock on crushed zone is met with in such cases descending stage of drilling and grouting to be done. After completion of drilling, the hole is to be protected by capping till the grouting is completed.

2. Plain washing of holes is to be done using G.I. Pipes or drill rods, with air and water lowering the pipes or rods to full depth

3. Washing of seams is to be done by fixing grout pipes or mechanical expanding packers, in stages starting from bottom zone.

4. The holes are to be washed after seam washing of each zone is to be completed, and then seam washing of next higher zone is to be taken up.

5. After completion of washing of seams, the holes are to be flushed with air and water and grouting to be started for bottom zones first by using expanding packers. First grouting of all bottom zones in a region are to be completed before taking up grouting of next higher zones.

6. During grouting of any hole, If interconnection is found in neighboring holes, the same are to be plugged till the grouting of the hole in operation is completed and then the inter-connected holes are to be drilled again and washed to full depth or required depth with water.

7. Grouting is to be .continued till the zone of the hole refuses to take grout which can be found by measuring at the grout agitator or sump.

8. Once grouting of holes in a region is completed the holes are to be kept plugged for

48 hours and then blown with air and then back filled to the top with some kind of mortar

that .is being using in that, region for construction of masonry.

b) High Pressure Grouting: The holes for the high pressure grouting the foundation of the structure shall and be drilled from the foundation to a depth and spacing of holes as shown on the drawings are approximate and subject to revisions at the time of drilling, testing, and grouting. The diameter of any grout hole shall not be less then 50 MM core recover will not be required. Grout holes shall be drilled to varying depth and at carrying inclination, not to exceed 30 degrees from that vertical. The exact depth direction and interval between holes will be determined in the field from the conditions encountered, and as directed by the geologist of Geological Survey of India, drilling of any grout holes to a total depth greater than 60mm is not anticipated, however holes to greater depths may have to be drilled if found necessary during execution whenever, the drill water is lost or artesian flow encountered, the drilling operations or not to be stopped, hut continued taking precautionary steps. Upon completion of drilling of a hole, it shall be temporarily capped or otherwise protected from entry of foreign material until grouting operations requires it to be opened.

8.5 PIPES FOR FOUNDATION GROUTING:

a) Low pressure grout holes: 65 mm or 75 mm diameter steel pipe of length 0.6m into masonry in the drilled holes to a depth 0.3 m into masonry or concrete from surface by reaming the hole with 80 mm or 100 mm bit to facilitate the easy washing of holes and prevent the drilling from re-entry into the holes; the cost of these pipes and fixing them should be included in the unit rates for drilling and grouting and no separate payment will be made.

b) High pressure grout holes: Standard 65 mm black steel pipe shall be used whenever embedded pipe specified for grout holes and also in foundation work over springs, crevices, seems, and other spots disclosing foundation defects and elsewhere if required. Pipes and fittings that are embedded in masonry or concrete shall be thoroughly cleaned and shall be held firmly in position and protected from damaged while masonry or concrete is being laid around them. The pipes for the high pressure grout holes shall be over 0.9 mts long from the foundation level so that where drilling is done later on, difficulties inclination may be avoided. The above pipe shall be' procured by the contractor at his own cost. The contractor has to embed these pipes without extra cost do the department.

9. PROVIDING WEEP HOLES:

Providing weep holes as shown on the drawings and providing filters and jali as per, the drawings including cost of materials and labour complete.

9.1 General:

a) Rectangular weep holes: Weep holes of the size 75mm wide and 150mm high or of circular pipe size of 10mm diameter as shown on the drawings shall be provided and they shall extend through the full width of the masonry with a slope a about 1 vertical to 20 horizontal towards _e draining face to drain moisture from the back filling. The spacing of holes shall be as per the drawings, 'in either direction staggered. The sides and bottom of weep holes in the interior shall be made up in the stones/concrete having fairly plain surface and channel so formed slab bed over with stones/concrete lintels not less than 150 mm on each side.

In stone masonry, generally the height of weep holes shall be the same as the height of the course in which they are formed as directed by the Engineer.

Filters behind weep holes with jali shall be provided to the dimensions and grades as shown on the drawings.

b) In case of pipes, where the length of pipe falls short of the required length, it shall be joined with necessary collars in CM 1:3 or as directed by the Engineer to form a continuous hole in the body of wall.

c) Defective work shall not be paid. The interior of the weep holes shall be free from. all sand, mortar, stone pieces, dirt and other foreign matter. Care shall be taken to prevent entrance of any foreign matter into the weep holes during progress of the work.

LIST OF APPROVED MAKES /MATERIALS TO BE USED FOR CIVIL WORKS

I here by agree to use materials from the makes specified against each item

TECHNICAL SPECIFICATIONS

SANITARY AND WATER SUPPLY

STANDARD SPECIFICATION FOR BUILDING WORK (AS PER A.P.S.S.)

All the items of work shall be executed as per the Standard Specifications laid down in APSS, the relevant I.S Codes of the Special Specification as indicated in Schedule - 'A' of the tender

| Sl. No. | Name of the specification | Specification No.of.APSS |
| --- | --- | --- |
| 13. | SANITORY WORKS AND ROOF PLUMBING |  |
| 13.01 | Stoneware pipes and fittings | 1301 |
| 13.02 | Cast iron pipes & special castings for water & Sewage | 1302 |
| 13.03 | Galvanised mild Steel Pipes & Fittings | 1303 |
| 13.04 | Concrete & pre-stressed Concrete Pipes & Collars | 1304 |
| 13.05 | Asbestos Cement Pressure Pipes & Fittings | 1305 |
| 13.06 | Unplasticised (Rigid) PVC pipes and fittings for potable water supplies | 1306 |
| 13.07 | Polyethylene pipes and fittings for potable water supplies | 1307 |
| 13.08 | Cast iron manhole covers & frames intended for use in drainage works | 1308 |
| 13.09 | C.I. Surface boxes for sluice valves, fire hydrants and air valves | 1309 |
| 13.10 | C.I. Grating for drainage works | 1310 |
| 13.11 | Sheet metal rain Water Pipes, gutters, fitting & accessories | 1311 |
| 13.12 | C.I. Rain water pipes and fittings | 1312 |
| 13.13 | Asbestos cement rain water pipes, gutters and fittings (spigot and socket type) | 1313 |
| 13.14 | Asbestos cement soil, waste and ventilating pipes and fittings | 1314 |
| 13.15 | C.I. Soil, waste and ventilating pipes & fittings | 1315 |
| 13.16 | Handling, transport and custody of pipes, fittings valves etc. | 1316 |
| 13.17 | Trench work excavation and back filling | 1317 |
| 13.18 | Laying and Jointing of glazed stoneware pipes and fittings | 1318 |
| 13.19 | Laying & Jointing of C.I. pipes, fittings & fixing accessories | 1319 |
| 13.20 | Laying & Jointing of Galvanised mild steel pipes & fittings | 1320 |
| 13.21 | Laying & jointing of cement pipes | 1321 |
| 13.22 | Laying & jointing of AC pressure pipes & fittings | 1322 |
| 13.23 | Laying & jointing of Unplasticised (Rigid) PVC pipes and fittings for potable water supplies | 1323 |
| 13.24 | Disinfection of water mains before commissioning | 1324 |
| 13.25 | Construction of manholes, flush tanks & other masonry works on sewers | 1325 |
| 13.26 | Fixing and Plumbing of sanitary fittings | 1326 |
| 13.27 | House Drains Connection – Construction | 1327 |
| 13.28 | fixing of rain water gutters & down take pipes for roof drainage | 1328 |

DRAINAGE, SEWERAGE,WATER SUPPLY, PLUMBING ETC.

1.0	DRAINAGE, SEWERAGE, WATER SUPPLY, PLUMBING ETC.

1. 1	General

1.2	All water supply, drainage and sanitary work shall be executed by a licenced or 	authorised plumbing supervisor or licenced or authorised plumber and shall be in 	accordance with the requirements of relevant bye-laws of-municipal or other authorities 	in whose jurisdiction the work is being carried out.

1.3	All items such as earthwork excavation, concrete, brick work, stone work, painting, etc., 	relevant specifications for those shall apply unless otherwise specified.

1.4	Unless otherwise specified, all exposed work such as cisterns, brackets etc., shall be 	painted with synthetic enamel paint of approved colour in two coats over a priming coat.

1.5 	The diameter of pipes and fittings wherever mentioned shall mean the internal diameter 	of nominal bore unless otherwise specified.

1.6 	 The job shall include the cost of making necessary chases, grooves, holes etc, in walls, 	floors and in other places and also making good or completion of the works. ANY 	DAMAGE caused to floors, walls etc., during the execution of the sanitary and plumbing 	works shall be made good by the Contractor at his own cost to the satisfaction of the 	Engineer-in-charge.

1.7	All the water supply and sanitary connections are to be tested against leakage and 	satisfactory performance based on standard tests before they are fixed.

Codes and Standards

SCHEDULE -C

LIST OF SPECIFICATIONS FOR THE VARIouS ITEMS OF WORKS SUPPLEMENTING THOSE DESCRIBED IN

SCHEDULE ‘A’ BY S.S. NUMBERS

GENERAL SPECIFICATIONS

| Sl.No. |  | Description | IS.No. and as amended from time to time |
| --- | --- | --- | --- |
| A) LIST OF INDIAN STANDARDS |  |  |  |
| I. | PIPES & FITTINGS FOR SANITARY, PLUMBING, DRAINAGE |  |  |
|  | 1 | Lead Pipe | IS 404:1993 |
|  | 2 | Lead sheet | IS 405:1992 |
|  | 3 | Pre-cast Concrete pipes with or without reinforcement – Specifications | IS 458:2003 |
|  | 4 | Specification for Salt-glazed stone ware pipe and fittings | IS 651:1992 |
|  | 5 | Method of test for concrete pipes. | IS 3597:1998 |
|  | 6 | Specification for Caulking lead. | IS 782:1978 |
|  | 7 | Centrifugally cast (spun) iron pressure pipes for water, gas and sewage. | IS 1536:2001 |
|  | 8 | Vertically cast iron pressure pipes for water, gas and sewage. | IS 1537:1976 |
|  | 9 | Cast iron fittings for pressure pipes for water, gas and sewage | IS 1538:1993 |
|  | 10 | Specifications for Centrifugally Cast (Spun) Ductile Iron Pipes for Water, Gas and Sewage | IS 8329:2000 |
|  | 11 | Specification for high density polyethylene pipes for potable water supplies. | IS 4984:1995 |
|  | 12 | Mild steel tubes and tubulars. | IS 1239 |
|  | 13 | Specification for Chemically resistant salt-glazed stone ware pipe and fittings. | IS 3006:1979 |
| II | WATER SUPPLY FITTINGS |  |  |
|  | 1 | Specification for Pillar taps for water supply purpose | IS 1795:1982 |
|  | 2 | Specification for Plug cocks for water supply | IS 3004:1979 |
|  | 3 | Washers for use with fittings for cold water services. | IS 4346:1982 |
|  | 4 | Specification for Self closing taps for water supply | IS 1711:1984 |
|  | 5 | Specification for cast copper alloy screw down bib taps and stop valves for water services. | IS 781:1984 |
|  | 6 | Water meter boxes domestic type. | IS 2104:1981 |
|  | 7 | Water fittings - Copper alloy float valves (horizontal plunger type) - Specification | IS 1703:2000 |
|  | 8 | Specification for copper alloy gate, globe and check valves for water works purposes . | IS 778-1984 |
| III | SANITARY FITTINGS |  |  |
|  | 1 | Vitreous sanitary appliances (Vitreous china) | IS:2556 |
|  | 2 | Specification for Glazed fire clay sanitary appliances. | IS 771: 1979 |
|  | 3 | Flushing cistern for water closets and urinals. | IS 774:2004 |
|  | 4 | Brackets and supports for wash basins and sinks | IS 775:1970 |
|  | 5 | Wooden water closet seats and covers. | IS 776:1962 |
|  | 6 | Plastic seats and covers for water closets | IS 2548:1996 |
|  | 7 | Waste plug and its accessories for sinks and wash basins. | IS 3311:1979 |
|  | 8 | Non ferrous waste fittings for wash basin and sink. | IS 2963:1979 |
| IV | LAYING OF PIPES |  |  |
|  | 1 | Code of practice for water supply in buildings. | IS 2065:1983 |
|  | 2 | Code of practice for building drainage. | IS 1742:1983 |
|  | 3 | Code of practice for laying of cast iron pipes. | IS 3114:1994 |
|  | 4 | Code of practice for laying of glazed stone-ware pipes. | IS 4127:1983 |
|  | 5 | Laying and jointing of polyethylene pipes and PVC pipes parts- I to III | IS 7634: |
|  | 6 | Laying of D.I pipes | IS 3114: 11500 |
|  | 7 | Code of practice for laying concrete pipes. | IS 783 :1985 |
| V | ROOF DRAINAGE SYSTEM |  |  |
|  | 1 | Cast iron rain water pipes and fittings. | IS:1230:1979 |
|  | 2 | Specification for Asbestos cement building pipes, gutters and fittings (spigot and socket type ) | IS 1626:1994 |
|  | 3 | Cast iron/Ductile iron drainage pipes and fittings | IS 1729:2002 |
|  | 3 | Specification for Centrifugally cast (spun) iron spigot and socket soil, waste and ventilating pipes, fittings and accessories. | IS 3989:1984 |
|  | 4 | Code of practice for fixing rainwater gutters and down pipes for drainage. | IS 2527:1984 |
|  | 5 | Code of practice for building drainage. | IS 1742:1983 |
| VI | TANKS/ MANHOLE COVERS / MISC. |  |  |
|  | 1 | Rectangular pressed steel tanks. | IS 804 :1967 |
|  | 2 | Code of practice for design and construction of septic tank | IS 2470:1985 |
|  | 3 | Specifications for Cast iron manhole covers and frames | IS 1726:1991 |

Note:-  The above I.S specifications mean latest over and above with amendments if  any.

1.2	Materials:  Materials, fittings and appliances for sanitary and plumbing work, used in the 	work shall be as specified in the Bill of quantities. The contractor shall submit to the 	Engineer-in-charge, samples of all materials, fittings and appliances for approval well in 	advance before starting the work. All materials, fittings and appliances used in the work 	shall confirm to the approved samples.

1.2.1	Galvanised pipes and fittings: -Galvanised steel pipe, fittings and accessories shall be 	of tested quality and shall confirm to IS: 1239 - (Part-I) 1968.

1.2.2	Lead Pipe:-  Lead pipes shall confirm to IS:404 Weight and thickness of pipes shall be 	indicated in the drawings or in the Bill of quantities.

1.2.3	Lead sheets: Sheet lead for finishing shall weight at least 30 Kgs. per sq.m. unless 	specified otherwise and shall confirm IS:405.

Bottle trap shall be of approved quality heavy brass chromium plated trap and made particularly smooth on the inside and shall have minimum 50 mm water seal and cleaning screw at bottom.

1.2.4	Lead trap; Lead traps shall be of the same weight and thickness for lead pipes. Lead 	traps wherever provided hall have minimum 50 mm water seal and cleaning screw at 	bottom. Traps shall be connected to wasted pipes with brass cap and lining of required 	sizes and wiped solder joints.

1.2.5	High density polythelene pipes and fittings: High density polythelene pipes and 	fittings shall be of tested quality and shall confirm to IS:4984-1972 and IS: 8008

1.2.6	Cast iron pipes and accessories: Cast iron pipes with sockets spigots ends shall 	confirm to IS:1230 and IS:1729.

1.2.7	IS:8008 : Specification for injection moulded HDPE (Part I to IV) fittings for                                   	potable water supplies.

1.2.8	Manhole covers: Manhole covers shall confirm to IS: 1726.

1.2.9	Concrete pipes: Concrete pipes shall be non-pressure type and shall confirm to IS :458 	and the type of joints shall be as indicated in the drawings.

1.2.10	Salt-glazed stoneware pipe:  Salt glazed pipe shall conform to IS:651 and IS:4006.

1.2.11	Sanitary appliances and non-ferrous fittings: All sanitary appliances and non-ferrous 	fittings shall be of tested quality and shall confirm to the relevant Indian Standards.

1.3	Joints

1.03.1	Cast iron Pipes: The type of jointing for CI pipes confirming to IS: 1729 shall be socket and spigot either with molten lead wool and gasket confirming to IS:782.

If the joints used are spigot and socket types, the spigot shall be careful centered in the socket by one or more pieces of clean white hemp/spun yarn with about 25mm overlap; sufficient yarn only shall be forced into the socket to leave a correct depth for lead caulking. The pipe shall then be examined again for line and level and the proper depth of each joint shall be tested before running the molten lead. For pouring of molten lead of ring of hemp rope shall be wrapped round the pipe at the end of the socket and the joint shall be covered with stiff damp clay. The rope shall then be removed carefully leaving V shaped large hole at the top of the joint to pour the molten lead. Lead shall be poured in one operation only. After a section of convenient length of pipe has been laid, lead shall be caulked sufficiently with caulking tools and hand hammer till the excess lead is removed and the joint shall be made neat and clean.

The type of jointing CI pipes conforming to IS: 1230 shall be socket and spigot with cement and sand. mortar (1 : 1) and gasket yarn.

The spigot shall be carefully inserted and centered in the socket by and or more pieces of thick clean hemp/spun yarn and shall be forced into the socket to leave a correct depth of 30 mm around for cement mortar. The pipe shall then be examined again for line and level and the proper depth of each joint shall be tested before inserting the cement mortar. The joints shall then be adequately carefully filled with stiff cement and sand mortar (1: 1) and the joints shall be levelled to the edge of the socket. Each joint shall be adequately cured by covering with wet clothes and pouring water at frequent intervals.

The parking ring or washer for the flanged joints shall be rubbed for the full diameter of the flange with proper pipe hole and the holes cut out suitably. The packing shall be smeared with graphite paste or a mixture of red lead and white lead and shall be introduced between the flanges of both the pipes and nuts tight in opposite pairs keeping the longitudinal axes adjoining pipe lines in exactly the same straight line. Lead washers shall be provided along with bolt, to prevent any leakage through bolt holes.

1.03.2	Stoneware pipes: The type of jointing for stoneware pipes shall be socket and spigot as indicated on the drawings. The inside of the socket shall be first painted with a layer of cement mortar (1 :2) and a gasket of yarn dipped in cement slurry shall be inserted in the socket of the pipe with in wooden caulking tool and wooden mallet in such a way that the gasket shall fully encircle the spigot with a slight overlap. When the spigot end received the gasket, it shall be wrapped round with two or three turns of treated spun yarn its end before being inserted into the sockets. The rest of the joint shall be then completely filled with cement sand mortar (1 : 1) having very little water and the joint shall be leveled to form a smooth splayed; filled at the angle of 45 degree. All excess of cement mortar left inside the pipe joint shall be neatly cleaned off and the joint shall be adequately cured by covering with gunny bags and pouring water at frequent intervals. In jointing stoneware pipes, care shall be taken that the pipes and kept concentric and the socket especially on the underside, shall be completely filled with cement mortar.    Where settlement of earth is envisaged, the joint shall be made with bitumenastic filler or any other materials as approved by the Engineer-in-charge.

1.03.3	Concrete Pipes: The type of jointing  for  concrete  pipes  shall  be with  loose concrete collars and the joints shall be packed from other side with spun yarn dipped in cement slurry as specified for jointing stoneware pipes; stiff cement mortar (1: 1) shall be filled from both sides and splayed at an angle of 45 degree on both side, the joints shall be adequately cured as specified for joints in stoneware pipes.

1.04.	Laying of pipes :

1.04.1	Cast iron pipes: The laying of cast iron pipe lines shall commence only after the bottom of the trench at various points have been levelled and aligned in accordance with the drawings. The sides of the trenches shall be vertical as far as possible and the width of the bottom shall be 300 mm wider than the diameter of the pipe. Where joints are made, the trench shall be widened suitable to provide room for caulking joints. Shorting and Timbering shall not be used without prior approval of the Engineer. For pipes buried in the ground, the Contractor shall take care to maintain always the minimum cushion of earth over the pipes as indicated in the drawings. All pipes, Water mains, cables etc met within the course of excavation shall be carefully protected and supported. All pipes and fittings shall be sounded with a light hammer and checked properly to detect any crack or blow holes before laying. The excavated materials shall be thrown on one side of the trench and the pipes stacked on the other side.

The inside of the socket and the outside of spigot shall be thoroughly cleaned of all foreign matter before laying. The pipes shall be laid with their socket ends facing the directions of the flow. The pipes shall then be lowered in the trenches by a method as approved by the Engineer. The pipes shall then be jointed by caulking as specified in clause 8.01.15. After each section of the pipeline has been laid it shall be tested for water tightness before back filling the trench. On successful completion of testing, the trench shall be backfilled with the excavated earth in layer of200 mm and shall be watered and rammed. Any subsidence accruing in the line of branches after backfilling shall be repaired by the contractor at his own cost. Where the pipe lines cross roads, the sides of the trenches shall be suitably shored.

1.04.2	Concrete pipes: The laying of concrete pipelines shall conform to clause 9 of IS:783.  Pipes shall be laid true to line and grade. Laying of pipes shall always proceed upgrade of a slope.

1.04.3	Stoneware pipes: The laying of stoneware pipeline shall commence only after the bottom of the trench at various points have been levelled as shown in the drawings. The centre line of the trench shall be first marked out on the ground and shall be excavated correct to depth, slope and width at all points. The pipes shall be carefully laid to the alignment, levels and gradients as shown on the drawings. The trench shall be excavated wide enough under the sockets to allow hands to pass for making joints. The pipes between manholes shall be laid truly in straight lines and without any vertical or horizontal deviations on a bed of concrete as shown in the drawings. While laying pipes, portion of concrete under each socket shall be dug and taken off so that the barrel of the pipe gets full support on the concrete bed. Pipes shall be launched with concrete tangentially up to the crown of the diameter of the pipe as shown on the drawing. When it crosses under a road, the pipes shall be fully encased in concrete as shown on drawings. The contractor shall take precautions to maintain always a minimum cushion of earth over the pipes as indicated in the drawings. All pipes shall be carefully examined with a light hammer for soundness before laying. After each section of the pipeline has been laid, the joints hall be allowed to sit properly and shall be inspected and carried out only after approval of the Engineer. After testing, the trench shall be back filled with selected earth in layers of 200 mm and shall be watered and thoroughly rammed all pipes, water mains, cables etc. met within the course of excavation shall be carefully protected and supported.

When the pipelines cross roads, the trenches shall have vertical sides with suitable shoring. Any subsidence in the line of trenches after backfilling shall be repaired by the contractor at his own cost.

1.04.4	Cast iron rain water pipes:

Cast iron rainwater pipes shall confirm to IS:1230 and IS: 1729 and shall be installed as shown in the drawings.

Cast iron rainwater pipes fixed exposed to external walls shall confirm to IS: 1230 and shall be blocked out at least 20 mm from the plastered surface by means of cast iron bobbing. The rain water pipes at the roof level shall be fitted with a cast iron band with a masonry bell mouth of suitable size fitted with a cast iron grating. The bottom of the down pipe shall be fitted with a shoe fixed 150mm above ground / apron level of the building as shown on the drawings. The sockets spigots of pipes and fittings shall be joined as specified in clause 8.01.15.

Cast iron rainwater pipes embedded in concrete or masonry shall confirm to IS: 1729 and shall be securely fixed to wall with wooden plugs and nails. Joints of the sockets and spigots of pipes and fittings shall be as specified in clause 8.01.15.

1.05	Inspection pits and trap pits:

Construction of pits shall commence only after the pipes have been laid in position to true line and levels as shown on the drawings to the satisfaction of the Engineer.

Inspection Pits:  Inspection pits shall be constructed as indicated in the drawings/bill of quantities. Unless otherwise specified, all inspection pits shall be constructed with rubble masonry in cement mortar (1 :4). Half round channels of size suitable for the inlet and outlet pipe diameter shall be formed on the floor of the pit with M-10. The floor on the pit shall be haunched towards the channel as shown in the drawings. Inside pits shall be finished with cement sand plaster as specified in the specification and finished smooth with cement punning. Care shall be taken to avoid invert level after finishing and shall  be as shown in drawings and/or as directed by the Engineer.

Inspection/master trap pits:   The pits for the glazed stoneware master trap shall be constructed as indicated in the drawings/bill of quantities. The construction and finishing of the pit shall be haunched towards the interception/master trap pits. Gully trap pits shall be constructed as indicated in the drawings/bills of quantities. The construction and finishing of the pit shall be as described in specification for inspection pit. The cast iron grating shall be set flush with the finished ground/ apron level.

1.06	Testing of Cast Iron Soil and Waste Pipelines:

On completion of laying the cast iron soil waste and ventilation pipeline shall be tested by the contractor at his own cost and to detect leakage and any other defects in the pipe line.

Test shall be conducted using proper apparatus with attachments for smoke making machine for applying smoke to the pipelines under pressure, jute cotton waste or brown paper soaked in creosote oil shall be used and fixed to obtain dense and pungent smoke. While conducting smoke test top of soil waste and ventilation pipes shall be kept open till smoke starts coming out of openings. The opening shall then be surely plugged with expanding rubber, traps and other openings for connecting sanitary fixtures shall be sealed with water or other approved plugs. The entire pipeline shall be tested in suitable sections as directed by the Engineer. The entire length of the pipelines including all joints under test shall be closely observed for any sign of smoke leakage. All leakage and defects shall be rectified by the contractor to the satisfaction of the Engineer.

1.07	Testing of underground Sewer lines:

The drainage system shall be tested in accordance with the provisions of IS: 1742. All defects and deficiencies detected during the watch shall be promptly rectified by the contractor to the satisfaction of the Engineer.

2.0	WATER SUPPLY:

2.01	Jointing and laying of galvanised steel water supply pipes:

2.01.1 	Screwed    galvanised steel pipes, conforming is IS: 1239 shall be jointed with screwed socket joints and screwed fittings of the same materials as that of the pipes. Any burrs remaining on the pipes and after the threads are cut shall be removed. An approved jointing compound together with a grumet of a few stands of fine yarn shall be used for jointing pipes and fittings. Any pipe threads exposed after jointing shall be painted with white synthetic enamel paint and in the case of underground piping, thickly coated with approved bituminous compound to prevent corrosion.

2.01.2       The depth at which the underground water supply pipe is to be laid shall be as shown in the drawings. The service pipe passing into or beneath the building shall be laid at least 200mm below the ground floor level and accommodate in a previously laid sleeve in the structure where it enters the building. The space between the sleeve and the pipe as its entry into the exit from the building shall be filled with bituminous materials for a minimum of 150mm at both ends.  Piping shall not be buried in walls or floors as far as possible. However when unavoidable, piping shall be buried for the shortest distance necessary and adequate protection shall be provided against damage.

2.01.3  	Galvanised steel piping shall be secured by iron or steel clamps and hooks when fixed on walls. All pipe work shall be completely water tight and the joints shall be such that there are no projections of jointing materials or the like in the interior of pipes. Before the pipeline is commissioned, all piping and fittings shall be flushed clean

2.01.4	Testing: After the laying and fixing of all galvanised steel water supply pipes and fittings are completed the line shall be slowly and carefully charged with water to a test pressure of 5 Kg. per Sq.cm. or the specified working pressure plus 50% as may be prescribed by the Engineer. Care shall be taken that air in pipelines is completely exhausted while filling the pipelines with water. This pressure shall be maintained for at least one hour, unless otherwise specified. The pipes and fittings shall be inspected for any leakage of water. Defects in pipes and fittings, if detected, shall be remedied by the Contractor at his own cost.

2.02	Jointing and laying of high density polythelene water supply pipes:

All higher density polythelene pipes shall have screwed ends and shall be jointed with screwed fittings of the same materials of the pipes. Any burrs remaining on the pipe ends after cutting threads shall be removed if necessary and approved jointing compound with a few strands of fine yarn may be used for jointing pipes and fittings. All exposed high density polyethelene pipes shall be installed with PVC saddles Screwed on 25mm thick wooden blocks securely fixed on walls, at suitable intervals, not exceeding 1m. Pipes wherever installed on wall, clamps shall be fixed as in the case of galvanised steel pipes.

2.03	Jointing of lead pipes: Jointing in lead pipes shall be wiped solder joints. Joints shall be wiped in a continuous circular motion in one direction so as to leave a neatly formed elliptical shaped joints free from tears, burns, dropping etc. All exposed lead pipes, exceeding 25mm in diameter shall be secured to walls by iron clips or lead ears. The spacing of the clips shall not exceed 900mm.

2.04	Storage water tanks: All tanks for storage of water shall be as indicated in the drawings and bill of quantities and shall be completely and properly covered with dust, light and mosquito proof cover of approved type as shown on the drawings or as described in the bill of quantities. They shall be fitted with a ball valve of approved type, securely fixed to the tank independent of the inlet pipe. A mosquito proof overflow pipe shall be fixed to the tank with the pipe invert about 25mm above the top of water line.

Approved type of stop valve shall be provided for every outlet pipe. All outlet and inlet pipes shall be fixed as shown in the drawings. Support of the tanks shall be 'as indicated in drawings. Inside surface of galvanised steel tanks shall be painted with anti-corrosive drinking water paints as indicated in bill of quantities.

2.05	Cleaning and disinfection: All storage tanks water supply fittings and pipes before being put into commission, shall be disinfected with liquid chlorine by the Contractor as his own cost.

3.0	INSTALLATION OF SANITARY APPLIANCES:

All sanitary appliances shall be fixed in position rigidly on floor and walls as indicated in the drawings/ bill of quantities or as directed by the Engineer.

3.01	Water closet-Squatting type: Squatting type water closet shall be fitted with specified trap and shall be jointed with gasket yarn and cement mortar.  Rim of the pan shall be levelled properly and set flush with the finished floor. The pan shall be connected to flushing cistern of capacity as indicated in the bill of quantities. The flushing cistern shall be supported on pair of CI cantilever brackets firmly embedded in the wall in cement mortar (1:4) or screwed to wall suitable plugs. Heights of the bracket from the top of pan shall be as shown in the drawings. The flush pipe from the cistern shall be 32 mm of specified tested quality and connected to the pan inlet by means of hemp and putty joint.

3.2   	Water closet-pedestal type: Pedestal type water closet shall be rigidly fixed on the finished floor by means of 75mm long brass screw with suitable plugs. The flushing cistern shall be porcelain or PVC or cast iron low level push down cistern of capacity as indicated in the bill of quantities. The cistern shall be supported on pair of cast iron or rolled steel cantilever brackets firmly fixed on wall with brass screws and suitable plugs. The flush pipe from the cistern shall be 40mm dia chromium plated. Brass bend fitted to the closet by means of rubber adopter. The closet shall be provided with double plastic seat cover confirming to IS: 2548 and chromium plated hinges.

3.3   	Urinals: Flat back type urinals shall be firmly fitted. on finished wall by means of 50mm long brass screws and suitable plugs. Height of the lip from the standing point shall be as shown in the drawings. Urinals shall be fitted with specified type of automatic flushing cistern of capacity as described in the bill of quantities and as shown on the drawings. Flushing pipes shall be of galvanised steel pipes of required sizes and connected to the Urinal with 15mm dia. PVC connector fitted with brass cap and lining at one end. The joint to the inlet of urinal shall be neatly finished with putty joints.

SENSOR FITTED URINALS

Flat back urinals shall be fitted with sensors for automatic flushing shall be firmly fitted on finished wall by means of 50mm long brass screws and suitable plugs. height of the lip from the standing point shall be as shown in the drawings.

The arrangement of waste pipes and discharge to the floor trap shall be as shown on the drawings or as directed by Engineer. For single urinal, the discharge may be direct to the floor trap through a 40mm dia waste pipe. For range of urinals the discharge may be collected to the common discharge pipe by 40mm dia pipe shall be led to the 100mm SWG half round channel laid on the floor leading to the floor trap.

3.4	Wash hand basin

Wash hand basin shall be fitted in position to true level on a pair of cast iron brackets rigidly fixed on wall with 50mm long brass screws and suitable plugs. The type of waste pipes and their connection shall be as shown on the drawings or as directed by the Engineer.

3.5       	 Porcelain sink of size as indicated in the bill of quantities shall be levelled properly and fitted   in position on a pair of cast iron cantilever brackets firmly embedded in the wall in cement mortar (1 :4) The sink shall be fitted with chromium plated brass waste fittings of standard size. The type of waste pipes and their connections shall be as shown on drawings. or as directed by the Engineer.

3.6	Other miscellaneous fittings (e.g. Mirror, towel rails, soap cases etc.)

All such fittings shall be of type and sizes prescribed in the bill of quantities and shall be fitted in position true to line, level, and plane as shown on the drawings or as directed by the Engineer.

LIST OF APPROVED MAKES /MATERIALS TO BE USED FOR SANITARY AND WATER SUPPLY ITEMS

| Sl No | ITEM/ MATERIAL | MAKES |
| --- | --- | --- |
| 1 | CI pipes | BPL / INDO / BIC / BIF |
| 2 | GI pipes & Fittings | Jindal / Tata / Zenith/ Oswal |
| 3 | GM Valves | Zoloto / Zenith / Anchor |
| 4 | HDPE Pipes | Finolex/ Superflow / Godavari / Premier Plastics |
| 5 | PVC pipes & fittings | Finolex/ Sudhakar / Ashirvad / Nandi |
| 6 | Wash Basins | Parryware / CERA / HIND WARE |
| 7 | IWC/ EWC | Parryware / CERA / HIND WARE |
| 8 | Porcelain Flush Tanks | Parryware / CERA / HIND WARE |
| 9 | Urinals | Parryware / CERA / HIND WARE |
| 10 | Pillar / Bib / Stop cocks | Seiko / Reico / Jaquar |

I here by agree to use materials from the makes specified against each item

INTERNAL ELECTRIFICATION

(AS PER NUMBERS OF APSS, BIS CODE, MOST, ETC)

1.0  	GENERAL SPECIFICATIONS AND INSTRUCTIONS

I.E. RULE 1956: the installation shall generally be carried out in conformity with Indian electricity rule 1956 as amended from time to time and national electrical code which contains specific regulations to be adhered to in the supply and use of electrical energy in the interest of safety.

PRESURE AND FREQUENCY OF SUPPLY: all current consuming devices shall be suitable for the pressure and frequency of supply stated in the special conditions of contract.

SYSTEM OF WIRING: the wiring shall be carried out on such a system as may be specified in the conditions of contract. Power wiring shall be kept separate and distinct from lighting wiring. All conductors shall be run as far as possible along the walls and ceiling, so as to be easily accessible for inspection. The balancing of circuits in three phase system shall be arranged before hand by the engineer.

CONDUCTORS: The material and size of the conductors shall comply with the bureau of the Indian standards and as per the provision of I.E. rules, 1956. all cables shall have the maker’s name and identifications printed on the insulated surface. In case of dispute regarding make it is the responsibility of the contractor to prove that the material is original of the company.

MATERIALS: All materials, fittings, equipment and their accessories, appliances, etc, used in an electrical insulation shall confirm the bureau of India standard specification wherever they exist. Incase the Indian standard does not exist, the materials and other items shall be those approved by the competent authority. A list of approved materials for use in the electrical works is enclosed.

2.0	TESTS TO BE COMPLIED WITH: Before the installation is permanently put in to service the following test shall be complied with.

a) INSULATION RESISTANCE: the insulation resistance shall be measured by applying between earth and the whole system of conductors or any section there of with all fuses in place and all switches on a direct current pressure of not less than twice the working pressure shall be deemed to be that which is maintained between the phase conductors and the neutral.

b) The insulation resistance of an installation measured as in above shall not be less than 1 mega ohm.

Lighting circuits shall be tested with all lamps in place except in the case of earthed concealed wiring system.

Heating and power circuits may be tested, if desired with the heating and power appliances disconnected from the supply.

3.0 	EARTH RESISTANCE: It is recommended that the value of any earth system shall not be more than 1 ohm unless otherwise specified. Care should be taken select a material which is resistant to corrosion in the soil in which, it will be used. The electrode shall be kept free from paint, enamel and grease. The size of the earth continuity conductor should not be less than 14 S.W.G.(2.8.94sqm). earth resistively test shall be carried out in accordance with Indian standard code of practice for earthing.

4.0 	FANS AND REGULATORS: All ceilings fans shall be wired to a ceiling rose and suspended from hook or shackle and insulated from the same. All joints in the suspension rod shall be screws and all joints or bolts in connection shall be additionally secured by means of split pins.

5.0 	CONDIUT SYSTEM OF WIRING: The conduit shall be electrically continuous front distribution board to out let boxes of lighting switches and other appliances. The lengths of conduits shall be joined by means of screws sockets. Threads shall be free from grease or oil and no material of this nature shall be allowed to come in contact with the conductors. The whole system of the conduits   shall be electrically continuous throughout and shall be permently and efficiently connected to the earthing system.

6.0 	EXCAVATION AND BACKFILL: All excavation and backfill including tempering, shorting and strutting required from the installation of the cable shall be carried out by the contractor in the accordance with the drawing and requirements laid down else where. Trenches will be filled in layer not exceeding 150mm. Each layer shall be properly rammed and consolidated before laying the next layer. The contractor shall restore all surface, road ways, side walks, curbs, wall or other worked out by excavation to their original condition, satisfactory to the departmental officers.

Prior to burying of cables, following tests shall carried out

Insulation test between phases, phase and earth for each length of cable before and after jointing. On completion of cable laying work, the following test shall be conducted in the presence of the departmental engineer.

Insulation resistance test

Continuity test

Earth test

7.0	MEDIUM VOLTAGE  AND LOW VOLTAGE SWITCH GEAR PANEL BOARD:

The main panel board shall be floor mounted and totally enclosed. The design shall include all provisions for safety of operating and maintenance personal. The general construction shall confirm to appropriate Indian standard specifications. Cubical type switch board shall be fabricated out of sheet steel not less than 2.00mm thick. Such sheet steel member shall be stiffened by angle iron frame work. Unless other wise approved, incomer bus section panel or sections shall be separate and independent. The general arrangement for multiplier construction shall be such that the horizontal bar framed present a pleasant and authentic look. The general arrangement shall be got approved before fabrication. All cable entries shall be through gland plates. Cable entry plates shall be sectionalized. The construction shall include necessary cable supports for crimping the cable allay or rear cable chamber. incomer termination shall be suitable for receiving busbar trunking. Busbar shall be firmly fixed on support constructed from a suitable inculting material which confirms to relevant Indian standards. The support shall be sufficiently robust to effectively with stand electromechanical stresses produced in the event of short circuit. The minimum clearance to be maintained for open and closed indoor air insulated busbars/electrically iron exposed and working at system voltage up to 600volts shall be as follows:

BETWEEN				MAINCLERANCE

Phase to earth				26mm

Phase to phase				32mm

8.0	DISTRIBUTION: Distribution boards shall be assembled, aligned and installed as per installation manual of the switch board supplier and relevant Indian standard specifications. Phase sequence for each incomer shall be tested and connections adjusted accordingly. A mechanical endurance test shall be carried out by closing and opening of the circuit breaker.

9.0 	COMPLETION DRAWINGS: At the completion of the work and before issuance of virtual completion contractor shall submit to the departmental officer five sets of layout drawings drawn at approved scale indicating the complete wiring system “as installed”. The drawings shall in particular give the following information.

Run and size of conduits, inspection and junction boxes.

Number and size of conductors in each circuit

Location and rating of sockets and switches controlling the light and power out lets.

Location and details of distribution boards, main switches and others particulars.

A complete wiring diagram as installed and schematic diagram showing all connections in the complete electrical system.

Instructions, maintenance and operation manuals if any for the equipments.

Contractor  should obtain necessary approval, from electrical inspectorate submitting necessary drawings test certificates etc.

10.0 	SPECIAL CONDITIONS FOR THE ELECTRICAL WORKS (GENERAL)

The work shall be carried out strictly in conformity with (1) code of practice for electrical wiring and fittings in Govt. buildings (2) the Indian standard specification (3) the departmental specification, if the work carried out does not comply with the code of practice and departmental specifications and if the workmanship  is unsatisfactory it will be binding the contractor to redo the job without any extra cost and pay penalty as decided by the department.

- The work should be carried out under the direct supervision of persons holding a certificate of competency for the type of work involved.

- After completion of work a plan of building should be prepared indicating the location of various  main and sub-boards and all the fitting together with a circuit diagram duly numbered (in the diagram). The final bill will not be paid till the above and the diagram submitted and approved after verification.

- The contractor will be responsible for any defects noticed for either improper work man ship or defective materials supplied by him for one calendar year from the date of final completion of 	work.

- Lugs should be provided for all earth connections.

- The contractor himself should arrange for the transportation of men and material to their 	work spot.

- All civil works and patch works indicated for providing electrical installations should be well 	finished to the satisfaction of the civil authorities. A certificate from them should be obtained 	to the effect that the civil and patch work done is to the satisfaction civil authorities. It will be 	the responsibility of the electrical contractor to obtain such certificate from the civil engineer. 	Unless such certificate is produced this office will have right to with held the bill.

- Concerting to the pole and providing independent earthing should be done in presence of departmental staff.

- The distribution board with switch controls shall be separate in each floor for normal supply and essential supply.

- The lighting circuits shall be provided with separate conductor to enable to connect the normal lighting and essential lighting with linking to any of the above system to ensure to switch over to essential supply in the order to have minimum to avoid inconvenience to the staff working.

- The control for the luminary to be provided in the hall for both to be connected to the normal 	supply and essential supply shall be separate and away from the each system.

- For the points to be connected to essential supply a separate conduit system is to be laid as 	enumerated in the above conditions includes circuit a main of any system.

- The location for the D.B’s and switch controls for essential supply will be decided during the course of execution where the circuit conduit way have to be terminated.

Conditions for Supply, Erection and Commissioning of Lift.

- GURARANTEE  :-

The equipment offered should be covered by the usual guarantee by which any

part or parts which fail within   24 Months from the date of handing over due to defective 	materials or bad work should be replaced by the firm at free of cost. The period 24 	Months is to be reckoned from the date of handing the lift to this department after testing 	and commissioning in satisfactory operating condition. No extra amount will be paid for 	any reasons what so ever.

- The delivery and erection shall be completed as per the rate of progress as specified in 	the tender conditions under rate of progress.

- Deputation of erector

Before the commencing the erection, the erection engineer should be deputed when 	ever asked from by the department. No separate charges will be paid for such 	deputation.

- (a)  The design and drawings of all civil works have to be furnished by the firm

(b)  The firm shall supply the lay out drawings of lift and its switchgear after the

Completion of the work

(c)   Finial bill shall be paid only after the entire work is completed to the satisfaction

of the department.

(d)   The rate offered by the firm shall be inclusive of all charges such as packing

forwarding and insurance etc. the rate also shall be inclusive of Excise duty,S.T

etc., including all other incidental charges, such as accommodation for erection

crew journeys boarding and lodging inclusive of training to an operator

concerned etc., .The price shall also include any statutory increase in excise

duty, S.T if any during the currency of the contract. However the department

shall help the firm in procuring the materials at concessional sales tax (i.e., the

department shall provide the firm with D-form for obtaining S.T concession )

5)  Servicing : Free servicing will have to be done by the firm for a period of twenty           four months from the date of commissioning the lift i.e., during the guarantee period.

- Terms of payment :  80% of the contract value will be paid on receipt of the all lift material at site. The balance 20% will be released after handing over the lift in satisfactory working condition, inclusive of erection, commissioning and testing.

- Specification :  The supply and erection of lift should be inconformity of standards as per I.S.I specifications.

- Scaffolding :  Scaffolding to the required extent has to be erected by the firm at their cost.

- Steel : The rate quoted should also include necessary steel required for still support angles, hitch beams, buffer supports channels and bearing plates etc., . The  department will not be responsible for any mishaps during execution of equipment.

- Minor civil works : Doing all minor works comprising of cutting holes and making good, quide rail brackets and landing batton fixtures, frames for collapsible gates and civil works, associated with the laying of the stills at each entrances and on the landing buffer supports channels and other works ancillary to the erection work in lift making and all other civil works will have to be carried out by the firm only to the satisfaction of the departmental officer and the company will responsible for any defects in the said works that might be noticed at later dates.

- Transport & Storage : The materials will have to be delivered at site and stored at the cost of the firm. The safety of the material will be firms responsibility till the equipment is handed over duly commissioned. Any damage or loss of the material stored will be to the account of tenderer. Any repairs or replacement etc., needed to the materials so stored should be done at the cost of tenderer till the lift is handed over in satisfactory operation condition after testing and commissioning. All the expenses should be borne by the company.

- Earthing : Necessary earthing is to be provided by the firm in confirmation to the relevant  I.S.I specifications.

- Other conditions will be as per APSS ( Manual AP detailed standard specifications)

# CONDITIONS Exclusively for Transformers

# RATES: The rates should be inclusive of all taxes and other charges for packing forwarding, insurance, transportation of the material to the site.

# DEPUTATION OF ERECTION ENGINEER & STAFF: The erection Engineer and staff should be deputed at the time of erection. No. Separate charges will be paid for such deputation.

# DELIVERY & ERECTION: The transformers should be supplied to erecting, commissioning and handing over in satisfactory working condition within (2) months from the date of agreement. All the H.T and L.T switchgear transformers etc., should be erected as per latest Electrical Inspectorate rules and for any deviations from rules, the contractor will be held responsible.

# GUARANTEE; All the equipment supplied should be guaranteed for two year from the date of handing over or from the date or charging of installation whichever is later in satisfactory working condition. Any part or parts, which fail during the guarantee period due to defective manufacturing or bad workmanship, should be replaced repaired by the firm free of cost.

# TEST REPORTS: The contractor should furnish test reports for transformers, oil breather, OCB’s etc., issued by the competent authority.

# The contractor should hand over all the required manuals of transformers supplied by him.

# CONDITIONS FOR SUPPLY, ERRECTION AND COMMISSIONING DIESEL GENERATOR SETS

# GUARANTEE: The Generator set and its connected switch gear, offered shall be covered by the usual guarantee period during which if any part / parts fall either due to defective materials bad workmanship shall be repaired / replaced by the firm at free of cost. This guarantee period of 24 Months will be reckoned from landing over the generator set after testing and commissioning in satisfactory working condition.

# DELVERY & ERRECTION: The delivery and errection shall be complete as per the rate of progress as specified in the tender conditions under rate of progress.

# A) The design and drawings of all civil works have to be furnished by the firm.

# B) The firm shall supply the layout drawings of generator set and its switch gear after completion of the work.

# C) Final bill shall be paid only after the entire work is completed to the satisfaction of the department.

# D) The rate offered by the firm shall be inclusive of all charges such as packing forwarding and insurance etc., S.T etc., including all other incidental charges such as accommodation for erection crew, journeys bearing and lodging inclusive of training to an operator concerned etc. The price shall also include statutory increase in Excise Duly, S.T. if any during the currency of the contract. However the Department shall help the firm in procuring the materials of concessional sales Tax (i.e. the Department shall provide the firm with ‘D’ form for obtaining S.T concession)

# SERVICING: Free monthly servicing and maintenance shall be done by the firm for a period of 24 Months from the date of handing over the plant and also the firm shall depute servicing Engineer as and when required by the Department without claiming any extra charges duly replacing the parts defective due to manufacture, free of cost and without any obligations.

# TERMS OF PAYMENT :  80% of the contract value on delivery of all materials at site based on payment schedule and balance after handing over the set in satisfactory working condition inclusive of errection, commissioning and testing.

# The current transformers which are proposed to be used shall be resin coated power cables shall be of fibre glass which can withstand  a temperature of 130 and Fuses, ACBs shall be English / Electric / Sermers LT & LK/ISI approved make.

# CIVIL WORKS: All the Civil works contingent to installation of generator set shall be done to the satisfaction of the Departmental officers concerned. The firm shall be responsible for any defects in the said works that might to be noticed at a later dated.

# TRANSPORT & STORAGE: The materials should be stored at the firms cost and responsibility. The storage accommodation will be provided by the Department subjects availability of the accommodation. This department will not defray of reimburse the cost of any materials / materials lost damaged or otherwise in the transit or storage of the materials or for any reason including thefts cyclone fire burglary or any other causes.

# TESTING CERTIFICATES: Test Certificate shall be furnished.

# EXPERIENCE: Only previous experience in supply and errection of generator sets and commissioning only need to apply.

# EARTHING: Necessary earthing is to be provided by the firm in confirmation to the   relevant I.S.I Specifications.

# Necessary exhaust piping from engine exhaust to outside the room by means of   MS / Gl pipe of suitable size and supporting it properly by means of clamps. Silencer should be mounted at the end of the exhaust pipe.

# The D.G set should be tested on load for at least 4 hrs out of which 2 hrs

# shall be 100% load and remaining 2 hrs shall not be less than 75% of full load.

GENERAL SPECIFICATIONS

LIST OF INDIAN STANDARDS FOR ELECTRICAL WORKS

Relevant Indian standards for the various materials to be used in electrical works as per specification condition No.______

| S//l.No. |  | Description | IS.No. and as amended from time to time |
| --- | --- | --- | --- |
| A) LIST OF INDIAN STANDARDS |  |  |  |
| I | CABLES |  |  |
|  | 1 | PVC insulated cables for working Voltage upto and including 1100 V | IS 694:1990 |
|  | 2 | PVC Insulated (heavy duty) electrical cables | IS 1554:1988 |
|  | 3 | 11 KV XLPE cables | I S 7089-part-II |
|  | 4 | Recommended current ratings for cables | IS 3961-1967 |
|  | 5 | PVC insulations and sheath of electric cables | IS 5831:1984 |
|  | 6 | Conductors for insulated electric cables & flexible cords (superceding IS 1753: 1967) | IS 8130:1984 |
| II | CONDUITS & ACCESSORIES AND JUNCTION BOXES |  |  |
|  | 1 | Flexible steel conduits for electrical wiring | IS 3480:1966 |
|  | 2 | Conduits for electrical installation: Part 1 General requirements | IS 9537-PI-1981 |
|  | 3 | Conduits for electrical installation: Part 2 Rigid steel conduits | IS 9537-PII-1989 |
|  | 4 | Recommended practice for hot dip galvanizing of Iron and steel | IS 2629:1985 |
|  | 5 | Fittings for rigid steel conduits for electrical wiring | IS 2667-1988 |
|  | 6 | Accessories for rigid steel conduits for electrical wiring | IS 3837-1976 |
|  | 7 | Adopters for flexible steel conduits | IS 4649:1968 |
|  | 8 | Boxes for enclosure of electrical accessories – Steel and cast iron boxes | IS 5133:1969 |
| III | DOMESTIC SWITCHES SOCKETS |  |  |
|  |  | Plugs and socket outlets (250V; 16A) : Specifications | IS 1293:2005 |
|  |  | Ceiling Roses – Specification | IS 371:1999 |
|  |  | Switches for domestic and similar purposes | IS 3854:1997 |
| IV | ELECTRICAL INSTALLATION |  |  |
|  |  | code of practice for electrical wiring installation | IS 732:1989 |
|  |  | code of practice for earthing | IS 3043:1987 |
|  |  | Recommendations on safety procedures and practices in electrical work | IS 5216:1982 |
|  |  | Code of practice for Selection, installation and maintenance of fuses (Voltages not exceeding 650 V) | IS 3106-1996 |
|  |  | code for practice for interior illumination Part2 | IS 3646:1966 |
|  |  | code of practice for lighting of public thoroughfares | IS 1944:1970 |
|  |  | Installation and maintenance of paper insulated power cables | IS 1155-1967 |
|  |  | Code of practice for use of structural steel in General building construction | IS:800 |
|  |  | Methods of testing uniformity of coating on zinc coated articles | IS:2633 |
|  |  | Code of practice for phosphate iron and steel | IS:6005 |
| V | LT PANEL BOARDS / LIGHTING PANELS |  |  |
|  |  | Enclosed distribution fuse board and cutouts for voltage not exceeding 1000 V AC / 1200 V DC | IS 2675-1983 |
|  |  | Specifications for Low voltage switchgear and control gear for voltages not exceeding 1000 V. Part-1 General Rules (supercedes IS 4237 & IS 2147) Part-2 Circuit Breakers (supercedes IS 2516) Part-3 Switches, disconnectors (supercedes IS 4064) Part-4 Contractors, starters (supercedes IS 2959) | IS 13947:1993 |
|  |  | Part-5 Control circuit devises & switching elements ( supercedes IS 6875 switches/ push button) | IS 13947:2004 |
|  |  | Code of practice for climate for climate proofing of electrical equipment | IS 3202: 11500 |
|  |  | Electrical accessories- Circuit breaker for over current protection for house hold & similar installations ( Miniature Air-bread circuit breakers for voltage not exceeding 1000V) | IS 8828:1996 |
|  |  | Current transformers | IS 2705:1992 |
|  |  | Low voltage fuses (upto 1000V) Supercedes IS 2208 & IS 9224 | IS 13703:1993 |
|  |  | Wrought aluminium and aluminium alloy bars, rods, tubes and sections for electrical purposes | IS 5082: 1998 |
|  |  | Specifications for low voltage switch gear and control gear assemblies (i.e. Factory build assemblies of switchgear and control gear for voltages up to 1000 V) | IS 8623:1993 |
|  |  | Electrical measuring Instruments (Direct acting indicating analog instruments) & accessories | IS 1248:2003 |
|  |  | Danger notice plates | IS 2551:1982 |
|  |  | Guide for Marking insulated conductors (supercedes IS 375) | IS 5578-1984 |
|  |  | Guide for uniform system of marking & identification of conductors and apparatus terminals | IS 11353:1985 |
|  |  | Electrical relays for power systems protections | IS 3231:1986 |
|  |  | Voltage Transformers (part 1 to part 4) | IS 3156:1992 |
|  |  | Electricity meters induction type (for alternating current) | IS 722:1986 |
|  |  | Inter connecting Bus-bars for Voltage above 1KV | IS 8084-1976 |
| VI | LIGHTNING |  |  |
|  |  | Code of practice for the Protection of buildings and allied structures against lightning | S 2309-1989 |
| VII | FIRE SAFETY |  |  |
|  |  | Code of practice for Fire safety of buildings (General) Electrical Installation | IS 1646-1997 |
| VIII | LIGHTING FIXTURES AND ACCESSORIES |  |  |
|  |  | General and safety requirements for electric Lighting fittings | IS 1913-1969 |
|  |  | Interior Illumination | IS 3636-1966 |
|  |  | tubular florescent lamps | IS: 2418:1977 |
|  |  | Bal lazes for use in florcent lighting fittings (part 1) | IS: 1534 |
|  |  | bi-pin lamp holders for tubular florcent lamps | IS: 3323 |
|  |  | capacitors for use in florcent lighting fittings | IS: 1569 |
|  |  | starters for florcent lamps | IS: 1522 |
|  |  | holders for starters for tubular florcent lamps | IS: 3324:1982 |
|  |  | specifications for decorative lighting out fits | IS: 5077 |
|  |  | high-pressure mercury vapour lamps | IS: 2183 |
|  |  | GLS lamps | IS: 416 |
|  |  | Bayonet lamp holders | IS 1258:2005 |
|  |  | dust proof electric lighting fittings | IS :4012 |
|  |  | dust tight electric lighting fittings | IS:4013 |
|  |  | specification for floodlights | IS: 1947 |
|  |  | Lighting public thorough fares | IS 1944-1970 |
|  |  | Luminaries for street lighting | IS 2149-1970 |
|  |  | Water tight electric lighting fittings | IS 3553-1966 |
|  |  | Waterproof electric lighting fitting | IS 3528-1966 |
|  |  | industrial lighting fittings | IS: 1777 |
|  |  | industrial lighting fitting with plastic reflectors | IS:3287 |
| IX |  | Ceiling fans |  |
|  |  | Electrical ceiling type fans & regulators | IS 374-1979 |
| X |  | Transformers | IS 2026-1962 |
|  |  | Installation and commissioning of transformers | IS 1886-1967 |
| XI |  | Onload change over switches | IS 4064-1978 |
|  |  | Tubular steel poles for overhead power lines | IS 2713:1980 |
|  |  | Mild Steel wire for General Engineering purpose | IS 280:2006 |

11.0	Standards for Electrical Equipment

11.1	Unless otherwise stipulated in this specification, all equipment or material covered under this specifications shall be designed, manufactured and tested in accordance with the latest standards of Indian Standard's specifications.

11.2	All equipment shall conform to latest Indian electricity Rules, Indian electricity act and Indian Insurance rules as regard safety, earthing and other essential provisions specified in for installation and operation of electrical equipments.

11.3	Extreme care shall be taken to make enclosures for switch gears proof against rodents, lizards and other creeping vermin.

11.4	Continuity of power supply is to be given maximum consideration and the design of the equipment shall be such as to simplify inspection maintenance and testing at site. The design shall include all reasonable precautions and provisions for safety of operating personnel and maintenance personnel.

1.0 	WIRING INSTALATION

SCOPE

The scope under this section covers wiring installation comprising of

a) 	Lighting/Fan/Exhaust Fan/Circuit bell points.

b)	Power circuits and Air Condition circuits.

c) 	Circuit wiring.

RECESSED CONDUIT WIRING SYSTEM WITH RIGID STEELCONDUIT

a)	Type and size of conduit: All rigid non-metallic conduits shall conform to accepted standards and shall be used to corresponding accessories. Conduits shall provide adequate mechanical protection for the enclosed cables and the interior of the conduit shall be free from obstructions. No non-metallic conduit less than 20 mm in dia shall be used. The No. of insulated cables that can be drawn into rigid non-metallic conduits are given in the following table (Ref: Table-2)

| Size of table |  | SIZE OF CONDUITS, MM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Normal cross Sectional area mm2 | No, &nd diameter of wires Mm | 16 |  | 20 |  | 25 |  | 32 |  | 40 |  | 50 |  | 63 |  |
|  |  | Number of Cables, Max |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | S | B | S | B | S | B | S | B | S | B | S | B | S | B |
| 1.0 | 1/1.12* | 5 | 4 | 7 | 5 | 13 | 10 | 20 | 14 | - | - | - | - | - | - |
| 1.5 | 1/1.40 | 4 | 3 | 7 | 5 | 12 | 10 | 20 | 14 | - | - | - | - | - | - |
| 2.5 | 1/1.80 3/1.06 | 3 | 2 | 0 | 5 | 10 | 8 | 18 | 12 | - | - | - | - | - | - |
| 4.0 | 1/ 2.24 7/0.35 | 3 | 2 | 4 | 3 | 7 | 8 | 12 | 10 | - | - | - | - | - | - |
| 6.0 | 1/ 2.80 7/1.06* | 2 | - | 3 | 2 | 6 | 5 | 10 | 3 | - | - | - | - | - | - |
| 10.0 | 11/3.55+ 7/1.40* | - - | 2 - | - 2 | 5 - | 4 4 | 3 3 | 7 6 | - 5 | - 8 | - - | - - | - - | - - | - - |
| 16.0 | 7/1.70 | - | - | - | - | 2 | - | 4 | 3 | 7 | 6 | - | - | - | - |
| 25.0 | 7/2.24 | - | - | - | - | - | - | 3 | 2 | 5 | 4 | 8 | 6 | 9 | 7 |
| 35.0 | 7/2.50 | - | - | - | - | - | - | 2 | - | 4 | 3 | 7 | 5 | 8 | 6 |
| 50.0 | 7/3.00+ 19/1.80 | - | - | - | - | - | - | - | - | 2 | - | 5 | 4 | 6 | 5 |

“*” for copper conductors only.

“+” for aluminum conductors only.

MS Conduits: Conduit pipe shall be finished with stove enamel surface. all conduit accessories shall be treaded type only and under no circumstances pin grip type or clamp type accessories be used. No steel conduits less than 16mm diameter shall be used.  The No. of insulated conductors that can be     drawn into rigid steel conduits are given in separate enclosure.

(Ref.Table-2)

b)	Bunching of cables: Unless otherwise specified, insulated conductors of AC supply shall be bunched in separate conduits.  For lighting and small power outlet circuits,  phase segregation in separate conduits is recommended.

c)	Conduit Joints:  Conduits (metallic) shall be joined by means of screwed couplers and screwed accessories only.  In long distance straight runs of conduit, inspection type boxes at reasonable intervals shall be provided.  Cut ends of conduit pipes shall have no sharp edges nor any burrs left to avoid damage to the insulation of conductors while pulling them through such conduits.

d) 	Inspection type conduit fittings such as inspection boxes, deep boxes, bends, elbows and tees shall be so installed that they remain accessible for such purposes as withdrawal of existing cables or installation of additional cables.

e) 	Metallic switch board boxes shall be fabricated from 1.6mm thick sheet metal of 16 gauge GI sheet and wooden switch board boxes shall be of Teakwood. The switch boards should be flush mounting type.  The MS switch boards should be painted with two coats of red oxide and two coats of synthetic enamel paint of approved grade and make before fixing in position.

The switch boxes should be covered with 3 mm thick Decolum Hylum cover.

f)	The chase in the wall shall be neatly made and be of ample dimensions to permit the conduit to be fixed in the manner desired.  In the case of building under construction chases shall be provided in the walls, ceiling etc., at the time of their construction and shall be filled up neatly after erection of conduit and brought to original finish of the walls.

g)	The conduits shall be fixed in chases by means of staples or saddles not more than 60 cms  apart.  Fixing of standard bends or elbows shall be avoided as far as practicable and all curves maintained by bending the conduit pipe itself with a long radius which will permit easy drawing in of conductors.  All threaded joints of rigid steel conduit shall be treated with some approved preservative compound to secure protection against rust.

h)	Suitable inspection boxes shall be provided to permit periodical inspection and to facilitate removal of wires if necessary.  Minimum size of inspection boxes shall be 75 x 75 mm.

i)	The M.S. switch board boxes, junction boxes etc., should be efficiently earthed with conduit by a suitable means of earth attachment.

j)	When crossing through expansion joints in Buildings, the conduit section across the joint may be through flexible conduits of same size as the rigid conduit.

k)	Wires: Wires shall comply with the following features.

- 	Annealed copper conductor, multi strand, PVC insulated,   1100 volts grade cables.

-	The following colour coding shall be followed :-

Phase		-R	-	Red

Phase		-Y	-	Yellow

Phase		-B	-	Blue

Neutral			-	Black

Earth			-	Green

l) 	On each (lighting/Ceiling Fan/Exhaust Fan) circuit not more than 6 points or 800-1000 watts load should be connected. Example:-  If on one of the switch boards there are only 4 switches to control  4 lights, other switch board another 3 switches to control lights etc,  then for arriving at the circuit length, the shortest distance from circuit breaker in the MCB distribution board to the nearest switch board shall be considered.  Inter connections between such switch boards shall be allowed by providing same wires as are used for light points and no measurement in circuit wiring is allowed for such inter connections.  A separate conduit pipe has to be provided for running circuit mains and the conduits for light points shall never be used for the same.

For 5 Amps 3 pin on separate board the circuit measurement to first nearest 5 Amps 3 pin socket is considered.  No measurement will be separately considered for looping of switch boards in circuit wiring.

m)	The mounting height of switch boards (bottom of MS Box) shall be 4'6" from finished floor level.

The 5 Amps/15 Amps 3 pin sockets with shutter protection shall be at 1 mtr. Level (or skirting level).

Wiring for power circuits i.e., 15 Amps 3 pin and AC points shall be provided in separate conduit pipes.

n)	Neat holes shall be punched on MS Switch Board Boxes for conduit pipe entries. Rough, burred holes with chisel shall be avoided. Conduit pipes to be fixed to MS Switch Board Boxes, MCB Distribution Boards etc., by providing (double chack) check nut arrangement.  Before drawing of PVC insulated cables inside the conduits, ebonite/ nylon bushes to be provided at conduit ends in order to avoid damage to cables during drawing.

o)	3mm thick Hylum / Decolum covers provided on Switch Boards should be fixed to switch boards by providing brass coated screws and plated cup washers.

p)	Any loose holes on Switch Board boxes and Distribution Boards shall be properly closed,  so as to prevent entry of lizards etc.

q)	Whenever cables of size 2.5 sq.mm /6.0 Sq.m and above are connected inside switch, socket or MCB, metallic plug point etc., proper type and size of lugs to be crimped to cable leads before making the permanent connection in switches etc.

r)	Telephone/intercom cables shall not be laid in the same conduit where electric lighting/power cables are drawn. Separate conduit pipes to be used for drawing of telephone/intercom cables.

s)	Loose joints with PVC insulation shall be avoided. Wherever possible joints of cables shall be avoided.  If found necessary proper type and size of connectors shall be used.

t)	The drop of voltage between the main switch/distant. Terminals and the farthest current consuming apparatus shall not exceed 2% with all devices switched on.

Testing

The entire installation shall be tested for

a) 	Insulation Resistance

b)	Earth continuity

c) 	Polarity of single pole switches

Tests shall be conducted in the presence of Site Engineer. Test results to be tabulated and submitted to the site engineer.

2.0 MCB DISTRIBUTION BOARDS, MCB’S AND ELCB’S

Scope

The scope under this section covers installation comprising.

a) 	Low voltage distribution boards

Details

a)	The Distribution Boards shall have vermin, dust, rust proof painting done by powder coating process.

b)	The cables entering the D. Board should be properly bunched and  dressed before making connection in MCB’s.

c)	Cable glands shall be provided wherever armoured cables are connected to switches.

d)	Cable leads shall be provided with proper type and size of lugs crimped to leads before making permanent connection inside MCB’s, RCCB’s etc.

e) 	Permanent circuit identification shall be provided on the distribution boards.

f) 	The mounting height of MCB distribution boards etc., (bottom line) shall be 6'-6" from finished floor level.

3.   CABLES

3.1 Scope: 	The scope under this section covers Power cables

3.2	Standards

| A a | Specification for conductors for insulated electric cables | IS:8130 - |
| --- | --- | --- |
| B | Specification for Armoured/ unarmoured power cables | IS:1554-Part I - |
| C | Recommended current ratings for cables | IS:3961 - |
| D | Specifications for PVC insulation and sheathing of electric cables | IS:5831-1984 |

3.3	General requirements for cables

a)	Cables should be stranded aluminium conductors for 6mm and above.

b) 	L.V. cables shall be 1100 Volts grade.

c) 	Cables shall have colour coded insulation.

d) 	PVC inner and outer sheathing shall be applied by extrusion.

e) 	Steel armouring between inner and outer sheathing.

f) 	The PVC insulation and sheathing shall confirm to IS: 5831-1984.

g) 	The armouring for cables up to 16mm² shall be of round steel wire and that above 16mm² shall be of galvanized steel strings.

3.4	Laying of Cables

a) 	Cables if laid underground shall be at a depth of not less than 60 Cms., in a trench. Sand filling shall be provided at the bottom of trench before laying the cable.  Bricks shall be provided on either side of the laid cable.  Sand filling shall be done to cover the cable laid. Bricks shall be provided on the top.  Earth filling shall be done.

M.S. cable identification tags, route indicators embedded in C.C. are to be provided at every 8 meters length of cable laid.

b) 	Hume pipe, trenches/tunnels with proper pre-cast slabs to withstand wear and tear of vehicular traffic shall be provided at road crossings.

c) 	Cables if laid in the air shall be laid on cable trays and shall be properly clamped to the trays by plated MS. Saddles at proper intervals.  Cables shall be properly dressed before fixing on the cable trays.

d)	Extra cable loops of minimum 500 mm shall be provided at each end of cables laid.

e) 	Cables shall be bent to a radius of 20 times the diameter of the cable with a minimum of 10 times diameter at restricted space.

f) 	Control/Telephone cables shall be laid away from power cables on separate cable trays.

3.5	Testing:

Manufacturers test report shall be submitted for tests on cables in accordance with Indian standards specifications.

Cables shall be tested after installation before commissioning by using 1000 Volts Megger and the following readings shall be obtained and tabulated.

- 	Continuity on all conductors

- 	Insulation Resistance    a) 	between conductors

b) 	all conductors and ground

The tests shall be conducted in the presence of Site Engineer and results submitted.

4	CABLE TRAYS AND ACCESSORIES:

4.1	Scope

The scope covers MS cable trays and cable tray accessories.

4.2	Standards

(IS. specifications shall be adhered to)

4.3	Specifications

Material: Hot rolled plain sheets of tested quality “O” grade as per IS 1079.

Thickness of material: 2.0 mm

Cable loading on tray: 50 Kg/MTR

Span between cable tray supports: 1.5 meters to 2.0  Mtrs.

Surface finish: Hot dip galvanising iron as per IS 2629, minimum 70 microns thickness

Length of cable trays: 2.5 Meters

Width of Cable trays: (outside to outside width to be taken)

a)	Ladder type - Bolted/welded construction 300 mm/450mm/600mm (depending on number of cables to be laid)

b)	Perforated cable trays (Same as above)

4.4	Sizes of Cable Trays:

a)	Ladder type - Bolted/welded construction

Side rail

* Flange width   15 mm

* Depth 70 mm

* Two coupler holes of 10mm diameter required on each side of side rail

* Rungs

* Channel section: 20 x 40 x 20 mm

* Slot size on rungs: 20 x 10 mm (oblong holes)

* Interval between rungs not more than 250mm

b)	Perforated type construction

* Flange width : 30mm

* Slot size : 20 x 10 mm (oblong)

4.5	Sizes of Coupler Plates:

a)	Ladder type - Bolted/welded construction

Size: 90 x 45 mm

Thickness of material: 2/2.5 mm

Slot size: 20 x 10mm oblong holes - Two numbers

Round holes 10mm diameter Two numbers

Finish: Hot dip galvanised as per IS:2629

b) 	Perforated type construction:

Size: 210mm x 25mm

Thickness of material: 3mm

Slot size: Oblong holes 20 x 10 mm - 2 numbers

Round holes 10mm diameter - Two numbers

Finish: Hot dip galvanised as per IS:2629

4.6	Hardware for coupler plate: (Electro galvanised)

a)	Hexagonal Head Bolts - 3 Nos.

b) 	Plain washers - 6 Nos.

c) 	Hexagonal nuts - 3 Nos.

Number of coupler plates per cable tray - Two numbers.

4.7	Cable tray Accessories:

Material: Hot rolled plain sheets of tested quality “O” grade as per IS: 1079

Finish: Hot dip galvanised as per IS:2629

Minimum bending Radius - 450mm

Tees, Horizontal/vertical elbows, cross and reducers for both ladder type - welded/bolted and perforated construction shall be as per standard manufacturers drawings.

4.8	Erection

Cable trays shall be erected on walls, trenches (if necessary) by drilling holes in the wall by power drilling machine.  Cable Tray shall be fixed to wall by providing proper size Anchor expandable type bolt and nut arrangement.

Proper type of cable tray accessories shall be selected depending on the site condition.

5.0	CABLE TERMINATION:

Cable gland body shall be made of brass castings and machined to final size.  The general construction of the glands should be as per standard manufacturer’s drawings.  It mainly consists

a)	Compression Nut - Brass - 1 No.

b) 	Gland body with Hexagonal head - Brass - 1 No.

c) 	Rubber Ring - Rubber - 1 No.

d) 	Brass washers - Brass - 3 Nos.

e) 	Check nuts - Brass - 1 No.

Metal parts of the gland shall be free from blow holes and surface shall be machined smoothly.

All edges shall be debarred and then nickel plated wherever necessary.  The cable glands shall be of single compression type.

6.0	L.T. PANEL BOARDS

6.1	Scope

The Scope covers the requirement of designs, construction, assembly, testing, Supply and installation of Panel Boards.

6.2	Standards:

IS: 13947  - Specification for low-voltage switch gear and control gear

Part -1 General rules     ( supercedes IS 4237 & IS 2147)

Part -2  Circuit breaker   ( supercedes IS 2516)

Part-3   Switches, disconnectors  (supercedes  IS 4064)

Part-4  Contractors, motor-starters ( Supercedes IS 2959)

Part-5   Control circuit devises & switching elements (supercedes IS   6875)

IS: 13703  - Low Voltage fuses (supercedes IS:9224 & IS 2208)

IS: 2705 - 	Current Transformers

IS: 1248 – Indicating Instruments

IS:  5578 -  Guide for Marking insulated conductors ( superceding IS 375)

IS: 11353 - Guide for uniform system of marking & identification of conductors and apparatus terminals

IS: 3156 - 	Voltage Transformers

IS: 3231 - 	Relays

IS: 722  - 	Integrating Information

IS: 8623 - 	Factory Built Assemblies of switch gear and control gear.

6.2.1	 The contractor can strictly follow the drawings and specifications for preparation of panels and he can get clarification from consultants or site Engineer-in-charge in case of any doubt.  The contractor shall submit the three copies of panel drawings for approval and get manufacture by only CPRI approval manufacturers.

6.3	CONSTRUCTION:

The panel board shall be:

i) 	of the metal enclosed, indoor, floor mounted, free standing type.

ii) 	be made up of the requisite vertical sections, which, when coupled together shall form continuous dead front switchboards.

iii) 	provide dust and damp protection, the degree of protection being no less than IP, 51 to IS. 2147.

iv) 	be readily extensible on both sides by the addition of vertical sections after removal of the end covers.

6.3.1	The panel boards shall be constructed only of materials capable of withstanding the mechanical, electrical and thermal stresses, as well as the effects of humidity, which are likely to be encountered in normal service.

6.3.2	Each vertical section shall comprise:

i) 	A front framed structure of rolled/folded sheet steel channel section, of minimum 2 mm thickness, rigidly bolted together. This structure shall house the components contributing on the major weight of the equipment, such as circuit breaker fuse switch units, main horizontal busbars, vertical risers and other front mounted accessories.

The structure shall be mounted on a rigid base frame of folded sheet steel of minimum 2mm thickness and 100 mm height.  The design shall ensure that the weight of the components is adequately supported without deformation or loss of alignment during transit or during operation.

ii) 	A cable chamber housing the cable and connections, and power/control cable terminations.  The design shall ensure generous availability of space for ease of installation and maintenance of cabling, and adequate safety for working in one vertical section without coming into accidental contact with live parts in an adjacent section.

iii) 	Front and rear doors fitted with dust excluding neoprene gaskets with fasteners designed to ensure proper compression of the gaskets.  When covers are provided in place of doors, generous overlap shall be assured between sheet steel surface with closely spaced fasteners to prelude the entry of dust.

6.3.3	The height of the panel should not be more than 2400 mm. The total depth of the panel should be adequate to cater for proper cabling space.

6.3.4	Doors and covers shall be minimum 2.0/ 1.5mm thick sheet steel. Sheet steel shrouds and partitions shall be of minimum 1.5mm thickness. All sheet steel work forming the exterior of switch boards shall be smoothly finished, levelled and free from flaws. The corners should be rounded.

6.3.5	The apparatus and circuits in the panel boards shall be so arranged as to facilitate their operation and maintenance and at the same time to ensure the necessary degree of safety.

6.3.6	Apparatus forming part of the panel boards shall have the following minimum clearances:

i)	Between phases - 25 mm

ii) 	Between phases and earth - 25 mm

iii) Between phases and earth - 25 mm

iv) 	Between neutral and earth - 19 mm

When, for any reason, the above clearances are not available, suitable insulation shall be provided.  Clearances shall be maintained during normal service conditions.

Creepage distances shall comply to those specified in  relevant standards.

6.3.7	All insulating material used in the construction of the equipment shall be of non-hygroscopic material, duly treated to withstand the effects of high humidity, high temperature tropical ambient service conditions.

6.3.8	Functional units such as circuit breakers and fuse switches shall be arranged in multi-tier formation, except that not more than two air circuit breakers shall be housed in a single vertical section.

6.3.9	Metallic/insulated barriers shall be provided within vertical sections and between adjacent sections to ensure prevention of accidental contact with:

i)	Main busbars and vertical risers during operation, inspection or maintenance of functional units and front mounted accessories.

ii)	Cable terminations of one functional unit, when working on those of adjacent unit/units.

6.3.10	All doors/covers providing access to live power equipment/circuits shall be provided with tool operated fasteners to prevent unauthorised access.

6.3.11	Provision shall be made for permanently earthing the frames and other metal parts of the switch gears by two independent connections.

6.4	METAL TREATMENT AND FINISH:

6.4.1	All steelwork used in the construction of the switchboards, should have undergone a rigorous metal treatment process as follows: (Seven tank process.)

i) 	Effective cleaning by hot alkaline degreasing solution followed by cold water rinsing to remove traces of alkaline solution.

ii) 	Pickling in dilute sulphuric acid to remove oxide scales and rust formation, if any, followed by cold water rinsing to remove traces of acidic solution.

iii) 	A recognised phosphating process to facilitate durable coating of the paint on the metal surface and also to prevent the spread of rusting in the event of the paint film being mechanically damaged.  This again, shall be followed by hot water rinsing to remove traces of phosphate solution.

iv) 	Passivating in de-oxalite solution to retain and augment the effects of phosphating.

v) 	Drying with compressed air in a dust free atmosphere.

vi) 	Primer coating with two coats of a highly corrosion resistant primer, applied wet on wet & stove dried under strictly controlled conditions of temperature and time.

vii) 	A finishing coat of stoving synthetic enamel paint to the specified shade of IS.5.  The total thickness of paint should not be less than 15 to 20 microns.

6.5	BUS BARS:

6.5.1	The busbars shall be air insulated and made of high conductivity, high strength aluminium alloy complying with the requirements of grade E91 of IS 5082.

6.5.2	The busbars shall be suitably braced with non-hygroscopic SMC supports to provide as through fault withstand capacity of 50 KA RMS symmetrical for one second and a peak short circuit withstand of  105  KA minimum.  The neutral as well as the earth bar should also be capable of withstanding the above fault level.  Ridges shall be provided on the SMC supports to prevent trackling between adjacent bus bars.

6.5.3	Large clearances and creepage distance shall be provided on the busbars system to minimise the possibility of a fault.

6.5.4	High tensile bolts and spring washers shall be provided at all busbar joints.

6.5.5	The cross sections of the busbars risers for various ratings shall have been decided on the basis of temperature raise tests carried out under conditions closely similar to actual service conditions.  For a total operating temperature of 110 deg. C. at an ambient of 40 deg. at the standard current ratings and corresponding cross sections of the main busbars should be such that the bus bar shall carry 1 Amp. per Sq.mm.

6.5.6	The main phase busbars shall have continuous current rating throughout the length and the neutral busbars shall have a continuous rating of atleast 50% of the phase busbars.

6.5.7	Connections from the main busbars to functional circuit shall be arranged and supported so as to withstand without any damage or deformation the thermal and dynamic stresses due to short circuit currents.

6.5.8	Busbars shall be colour coded for easy identification of individual phases and neutral.

6.5.9	The busbars shall be suitably supported with epoxy resin mould insulators.

6.6	Tests:

The panel Board shall be inspected as per relevant standards in presence of the Site Engineer and shall include.

a)	High voltage test

b)	Insulation test

c)	Constructional and safety features

6.7	Name Plates:

Main name plates shall be fixed at the top centre.  Name plate giving feeder detail shall be provided and are to be fixed by screws.

7.0 	EARTH ELETRODES

7.1	Scope:

The scope included both pipe earth electrodes and plate earth electrodes.

7..2	Standards:

IS:3043 - Code of practice for earthing

7.3	Construction:

Pipe Earth Electrode: G.I pipe shall not be less than 38mm diameter and 2½meter long. It shall be buried vertically into the earth pit with the top not less than 1.25 meters below ground level. The G.I pipe should be “C” / "B" class type.

Plate Earth Electrode: Copper plate of 600 x 600 x 3.15 mm. (or GI plate) shall be burried in the earth with faces vertical and top shall not be less than 1.5 meters below ground level.

The electrodes shall be surmounted by alternate layers of charcoal or coke and salt. Watering arrangement with ½” G.I pipe with a funnel shall be provided, the later being housed with chamber (masonry) of inner size 300 x 300 mm CI hinged cover with CI frame to be provided on the top.

7.4	Tests:

The resistance of earth electrode shall be less than 5 Ohms.

8.0	EXTERNAL ELECTRIFICATIONS WORKS

8.1.1 	Underground Cables:

i)	Medium and low pressure:

Cables should be double steel tape armoured over lead covering and paper insulated or PVC insulated as specified in the schedule of work.  All repair joints of cables should be in joint boxes and filling in of the compound shall be done as per IS specifications using best quality materials.  All accessories and other materials should conform to I.S. Specification.  The jointing work should be carried out by a competent authorized cable jointer. The cables shall be 1100 V grade.

ii)	Trench:

Trenches shall not be less than 45 cm wide and 60cm below ground level.  Wherever necessary, suitable propping and storing may be done to avoid caving in of the adjoining trench walls.  Where the cables cross other services lines adequate protection should be taken to prevent accidental exposure and/or damage to the cables.

iii)	Spacing between cables:

Where more than one cable is laid in the same trench the actual space between the cables should normally be 23 cm apart leaving a clear distance of 15cm from the cable and the trench walls.

iv)	Laying of cables:

Before the cables are laid, a layer of 3" sand base is to be provided for purposes of cushioning.  The cables after being uncoiled and laid into the trench from the rollers should be drawn in straight length.  After the cable is laid, it is to be covered with another layer of sand of about 15cm in depth, and the top surface is to be suitably levelled to received the cable covers which may be of second class bricks or tiles and laid in such manner as to overlap the cables on either sides by at least 5cm.  Cable markers of aluminium or G.I. shall be provided at concrete blocks of 3/20cm x 20cm x 5cm and spaced at distance of about 30cm from center to center and at every change in direction.  Cables may also be laid in tier formation in the same trench in this case also after the 1st 3 inches of sand cushion, the first tier of cable is laid and sand filled in the trench to form a bed of 23cm above this tier.  After this the second cable is laid and the process repeated, the top most tier being at least 45cm below the Ground level.  The top cable shall be suitably covered with bricks or tiles.  When laying cables, care should be taken to see that the paper insulated cables are bent/straightened slowly, sharp radii being avoided.  The minimum safe bending radius for single core cables is 20 diameters and for multicore cables 10 dia meters and for armoured cables 12 diameters, the diameter being the overall diameter of the cable. Where the cables are required to cross roads they should be normally taken through sleeve pipes at least 10cm in diameter which may be either stone ware, steel or spun reinforced concrete.   For more than one cable the diameter should not be less then 15cm.  Steel pipes shall be used where it is not possible to obtain sufficient depth to withstand impact from traffic.

v) 	Cable inside building:

Cables laid inside the building should be properly protected and be carried either in ducts with suitable covers with slabs or chequred plates or fixed to walls by clamps, brackets or cable trays.

vi)  	Hume Pipes

Wherever cables crossing roads, passages Hume pipes of suitable diameter shall be provided across the road includ ing Civil works of digging, laying of Hume pipes upto a depth of 1 metre and refilling the trench.  This shall be properly laid to cover the entire road so as to protect the  cables against damage of passing Heavy Vehicles.

vii)	Testing the cables:

High voltage tests should be undertaken to ensure that no damage has occurred during the laying operation and that the joints are in order.  Cables of 1.1 KV suitable for low and medium voltage should with stand for 15 minutes, 300 volts D.C. current applied between the conductors and between each conductor and sheath.  In absence of high pressure testing equipment it is sufficient to test for 1 minute with 1000 volts.  If the test results are found to be not satisfactory the contractors shall arrange to replace without any extra cost including removal of rejected materials, Re-laying etc.

viii) 	Cable laying & termination shall confirm to IS 1255

ix) 	Earthing of cables and cable glands shall confirm to IS 3043

x)	The cable length given in bill of quantities are approximate and the contractor has to measure exact length of cables to be laid before commencement of work in presence of engineer in charge and give the sizes and quantities  required to the engineer in charge to take further action by  the engineer in charge. The measurements after laying cables are also to be taken jointly by contractor.

8.1.2 	Over head lines

This specification of over head line covers installation, testing and commissioning of over head lines distribution lines upto including 11 KV lines, service connections and street lighting works.

1)	Materials: Supports for over head lines and for street lights shall be any of the following types or as specified by Engineer in charge and shall be of adequate strength confirming in all respects to Rule 76 of Indian electricity rules.

Steel tubular poles: This shall conform IS 2713-1964. This shall be seamless/sawaged and welded type as specified and shall be in time stepped sections. Unless other wire specified 1/6th from the base length of the pole plus 15cm be coated with black bitumen paint both internally and externally. The remaining portion of the pole shall be painted with one coat of red oxide on its external surface. The pole shall be complete with cap and base plate.

Steel poles (RSJ Joists): These shall be 1 section steel rolled poles confirming to IS standards and Medium weight. The height of the pole shall not be less than 9mts and the pole shall be fixed below ground level not less than 1.5 mts. The size of overhead line steel RS Joist pole shall be concreted in 1:3:6 cement concrete and painted as per steel tubular poles given above.

Prestressed Cement Concrete Poles (PSCC): PSCC poles shall be of 8.0 Mts./ 9.0 Mts. Height and shall confirm to standards of APTRANSCo. / APDISCo.

‘D’ Iron Clamps: Where so specified in the contract conductors shall be spaced vertically supported on shackle which are attached to the pole by means of ‘D’shapped clamps made of M.S. flats of size not less than 50x6mm and galvanized set the dimensions of ‘D’ shall be such as to hold 75 mm high and 90 mm dia (minimum size) shackle insulators. The ‘D’ iron clamp shall be complete with pole clamp with necessary bolts nuts and washers and bolts holes. Clamps shall also provided for pin insulators as in case of vertical formation.

G.I. Strap: Where ‘D’ iron clamps are not specified, a pair of strap plates of galvanized iron of size 40mm x 3mm and length of 23 cms shall be used with shackle insulators. The pole clamp shall be treated with one coat of red oxide primer before erection and finished with two coats of approved paint after erection along with other hardware as specified. The nuts, bolts, for pole clamp shall be of G.I./Cadmium passicated/ galvanized.

Stay/Strut Set: A stay set shall consist of stay rod, anchor plate, bow tightener or turn buckle, thimble, stay wire, and strain insulator. The stay rod shall be with stay grip in case of turn buckle is used instead of bow tightener. The stay wire shall be either 7/4.00mm dia or 7.3.15mm dia. G.I. as specified in the contract confirming to IS 2141 – 1968 grade. The anchor plate shall be of M.S. galvanized and not less than 30cms x 30cms x 6.4mm thick and size of stay rod shall be not less than 1.8 m (6 feet) long and 19mm dia.

Insulator: Porcelain insulator shall conform to IS 1445 –1966 suitable for over head lines for power lines below 1000 V and IS 731-1971 for overhead power lines greater than 1000V. This shall be vitreous throughout and non absorbent. The exposed surface shall be glazed. Insulator shall have adequate mechanical strength high degree of resistance to electrical puncture and resistance to climatic and atmospheric attack. The insulator shall be of the following types as specified.

a) Pin and shackle insulators for L.T. and MV lines.

b) Pin and disc type for HV lines.

The minimum size of shackle insulators shall be 65mm dia 100mm high. The pin insulators shall be suitable for 12mm cordeam thread and shall be complete with GI. Pin, nuts, and washers.

Binding Materials: Binding of conductors with the insulators shall be done with 12 SWG soft/ aluminum conductor.

Guard wire: Guard wire shall be G.I. It shall have minimum breaking strength of 635 kg in accordance with Rule 38 of I.E. Rule. It shall also be sufficient current carrying capacity to ensure rendering of guard line.

Earth wire: The size of the continuous earth wire shall not be less than SSWG.G.I.

Section Stay: A stay shall be provided at all angle or terminal poles. The stay rod with the anchor plate shall be embedded in cement concrete 1:3:6(1 Cement:3 coarse:6 graded stone) and not less than 0.1508 Cum content in such away to prevent uprooting of the stay rod. The stay wire shall also be connected and bounded properly to the continuous earth wire. Double stays shall be provided at the all dead ends of the pole.

Jumpers: While stringing conductors as sufficient length be kept at shackle termination for making jumpers.

Guarding: All road crossing, crossings, of overhead lines, and between HV & LV lines carried on the same support guared shall be provided. The guard wires shall be bonded to earth wire Cage guard shall be provided for distribution lines of vertical configuration.

8.1.3	Lighting Arrestors

Lightening arrestors shall confirm to IS 3070 -  11500 part I and IS - 3070 - 1966 part-II as applicable. The lightening arrestors system shall confirm to Rule 92 of IE Rule.

8.1.4	Service Connection by Underground Cables:

The service cables from an overhead distribution live shall be fixed to the support with 2 No’s of clamp of M.S. flat size 50mm x 6mm.  This shall be protected upto a height of 3m from ground level by a G.I. pipe of adequate size clamped to the support with 2 No’s of flats of size 50mm x 6mm.  The cable shall be laid through pipes while crossing roads, pavements, masonry etc.

8.1.5	ACSR Conductors

Conductors shall be of the following types.

Aluminium conductor steel reinforced (ACSR). This shall   comply with the requirements of I.S. 398 - 1961.

The physical and electrical properties of the above conductors shall be in accordance with the specifications as per IS.  These conductors shall have a breaking strength of not less than 350kg.

Necessary precautions during storage and handling shall be taken to avoid damage to the conductors.

8.1.6	Transformers

The transformers required are intended for use in distribution of power and lighting.  The 11 KV / 433 volts Transformer required for feeding lighting, pumps, Air conditioning, lifts etc.

The transformers shall be distribution type out door used complete with oil filled H.T brushing, L.T. cable end box receive suitable size confirming to IS2026

The transformers shall be designed and manufactured and tested as per IS 2026.

The transformers winding shall be of copper/aluminium winding as specified.

The transformer shall be adequately designed and effectively cooled to ensure its working on full load conditions continuously under short time over load conditions.

The design of core should ensure stability and reduce to a minimum the transformer excitation current and eddy current losses.

The core shall be provided with lugs suitable for lifting the complete core and coil assembly of the transformer.

The transformer coils shall be made of high conductivity copper and insulated with paper of dielectric strength and allow ageing characteristics. The Insulation of the coils shall be treated with suitable insulating material like varnish is to develop full electrical strength of the windings.

The tap changing arrangement shall be provided on the H.T side.  The tap changer shall be ON/OFF load type.  The tap changing switch shall be mechanically coupled to the external operating handle and the operating handle shall be carried through

on oil tight gland on the tank side. A register plate clearly indicating the tapping in use shall be fixed to the external operating mechanism and provision shall be made for securing and padlocking the switch in any of the working position and to ensure that contacts are fully engaged before the transformer is energised.  The range of ON/OFF Load tap change shall be +2 ½ % to + 5%.

i)	Bushing

The Bushing Insulators of the transformers shall be of sufficient creepage length and shall be unaffected by atmospheric conditions due to weather, fumes, alkalies at site.

ii)	Insulating oil

Sufficient oil shall be supplied for first filling. The oil shall comply in all respects with pro  IS.335.

All accessories like drain valve, oil filling valve, filter valve, oil sampling valve, pressure relief device, oil level indicator, indicating  thermometer (dial type) earthing terminal, bi-directional rollers .  Exhaust vent, eye bolts, lugs, Diagram and rating plate.

9.0	       Testing

All panel boards, switch boards, transformers, over head lines, cables, switches, main switch boards, shall be properly tested with meggar, test lamps for voltage, Insulation, and values shall be submitted to site electrical  Engineer before commissioning pressure test of approximate  standard shall be carried out on equipment, on overhead  lines, cable panel boards etc.

The H.T. side of transformers shall be tested with 1000V meggar and L.T. side of equipment, overhead lines, cables with 500V meggar.  The earth pits shall be tested with earth meggar.  All results shall be carried out at site in presence of electrical Engineer and report shall be submitted to him in triplicate and also to the consultant.

All test certificates Transformers, main panel boards, main switch boards, cables, overhead lines, sub distribution boards shall be supplied in triplicate to the site electri cal Engineer as well as to consultant. All meters shall be properly working without damages/strucking.

10.0	Commissioning

All the equipment, transformers, cables, panel boards, overhead lines can be commissioned only after the pressure/meggar tests are found satisfactory.   The equipment, cables, overhead lines, panel boards, transformer etc shall be energised in presence of Engineer and consultant after satisfactory presence/meggar tests.

11.0	       Contractor:

The contractor for electrical works executing substations, earthing, transformers, lighting shall hold valid class ‘A’  licence issued by Andhra Pradesh electrical licensing board and he should submit his license copy and his previous experiences along with the tenders and also before commencement of work  The contractor shall quote and employ the number of electrical engineers, supervisors, wiremen in his position for such type of works, who are possessing necessary permits/certificates/licences.

Liquidated damages will be levied in case of failure to complete the job in time as per standard clauses.

The contractor shall be able to read the drawings and prepare the drawings as per site conditions and any modifications necessary for submissions to  the electrical inspector.

The contractor shall have laison with APSEB officials and electrical inspectors, get the drawings and installations approved and also getting power supply released from APTRANSCO.

It is complete responsibility of the contractor to get the   electrical inspector's approval, including and getting power supply. He should have good laison with APTRANSCO.

The contractor can strictly follow the drawings and specifications for carrying out the works and he can get clarifications from site Engineer or Consultant in case of doubt.  The contractor shall submit three copies of drawings for conduit routing inside the building, which he is going to carry out and submit one copy to consultant and two copies to client.  This also includes the point wiring, telephone point conduit and power plug wiring conduit for each building before starting of the civil works at least one week in advance for verification by client and consultant.  The contractor shall also give the total quantity of various conduit to be used in each building before starting work as well the quantity of various wires to be used for each building.

The contractor should plan properly for all electrical material and works entrusted to him 15 days in advance and in form the Engineer-in-Charge and consultant about his work progress.  He should co- ordinate with civil persons for recessed conduit laying and also switch boards recessed fixing and any other electrical work associated with civil works as well as electrical Engineer at site and electrical consultant for his works.

12.0	Standards for Electrical Equipment

12.1	Unless otherwise stipulated in this specification, all equipment or material covered under this specifications shall be designed, manufactured and tested in accordance with the latest standards of Indian Standard's specifications.

12.2	All equipment shall conform to latest Indian electricity Rules, Indian electricity act and Indian Insurance rules as regard safety, earthing and other essential provisions specified in for installation and operation of electrical equipments.

12.3	Extreme care shall be taken to make enclosures for switch gears proof against rodents, lizards and other creeping vermin.

12.4	Continuity of power supply is to be given maximum consideration and the design of the equipment shall be such as to simplify inspection maintenance and testing at site. The design shall include all reasonable precautions and provisions for safety of operating personnel and maintenance personnel.

13	Completetion Certificate:

13.1	After completion of the work the contractor should submit completion certificate in the following format:

I/We certify that the installation detailed below has been installed by me/us and tested and that to the best of my/our knowledge and belief, it complies with Indian Electricity Rules 1956.

Electrical installation at...................................................................................

Voltage and system of supply.........................................................................

Particulars of Works:

a)	Internal Electrical Installation.

No.	Total Load	Type of system of wiring

i)	Light point

ii)	Fan point

iii)	Plug point

3-pin 5 A

3-pin 15 A

b)	Others                 Description	      hp/kW	Type of starting

1)	Motors:

i)

ii)

iii)

2)	Other plants:

c)	If the work involves installations of over head line and/or underground

cable:

1)	i)	Type and description of overhead line

ii)	Total length and No. of spans

iii)	No. of street lights and its description.

2)	i)	Total length of underground cable and its size

ii)	No. of joints:

End joint:

Tee Joint:

Straight through joint:

Earthing:

i)	Description of earthing electrode

ii)	No. of earth electrodes

iii)	Size of main earth lead

Test Results:

a)	Insulation Resistance

i)	Insulation resistance of the whole system of conductors to earth ........................ Megohms.

ii)	Insulation resistance between the phase conductor and neutral.

Between phase R and neutral ........................ Megohms.

Between phase Y and neutral ........................ Megohms.

Between phase B and neutral ........................ Megohms.

iii)	Insulation resistance between the phase conductors

Between phase R and neutral ........................ Megohms.

Between phase Y and neutral ........................ Megohms.

Between phase B and neutral ........................ Megohms.

b)	Polarity test:

Polarity of non-linked single pole branch switches.

c)	Earth continuity test:

Maximum resistance between any point in the earth continuity conductor including metal conduits and main earthing lead .............................. Ohms.

d)	Earth electrode resistance:

Resistance of each earth electrode.

i)	.............................. Ohms.

ii)	.............................. Ohms.

iii)	.............................. Ohms.

iv)	.............................. Ohms.

e)	Lightning protective system.

Resistance of the whole of lightning protective system of earth before any bonding is effected with earth electrode and metal in/on the structure .............................. Ohms.

Signature of the Supervisor	         Signature of Contractor

Name and Address	Name and Address

...............................................	...............................................

...............................................	...............................................

...............................................	...............................................

*    *    *

LIST OF APPROVED MAKES /MATERIALS TO BE USED FOR

ELECTRICAL WORKS

I here by a agree to use material only from the makes specified against each item.

Note : The contractor shall be invariable used the materials specified in BOQ

Special conditions for Fire Protection & Fire FiGHting System

- It is the complete responsibility of the agency to obtain the approval to drawings pertaining to the fire fitting and protection system from the concerned fire services authorities as per section 13(1) of A.P Services Act 1999

- The agency should be aware of the rules and regulations of A.P Services Act 1999

- It is the complete responsibility of the agency to comply with the Municipal corporation Building Bye Laws 1981 provision No 12 in pursuance of Sub section (1) of section 455 of the act and to should intimate the DG Fire Services on completion of the building and before Occupation and arrange for inspection for issue of No-Objection certificate.

- It is the complete responsibility of the agency to comply with the clause 13.1 of part-II of National Building Code under which the agency has to carry out the work based on the approved Drawings and specifications of the work.

- It is the complete responsibility of the agency to comply with the provisions under clause 9.3 of part-II of NBC and to engage Licenses fire Engineer/Sub agency for supervision of the work right from commencement to till completion of the work.

- It is the complete responsibility of the agency to comply with regulation No 06 of Multi Storied Regulations 1981 and to maintain the specifications standard and code of Practice recommended in the NBC

- It is the complete responsibility of the agency to comply with regulation No 5(2) of Multi Storied Building Regulations 1981 and to arrange the inspection of CE/HUDA and DFO/HYD to ensure that the construction of multi Storied Building is undertaken as per approved plans and fire precautionary and fire protection measures as suggested by the authorities are implemented.

- It is the complete responsibility of the agency to comply with regulations of NBC and to maintain open space at least 13mts around the complex.

- It is the complete responsibility of the agency to comply with regulations of NBC and to maintain means of Escape as NBC in the complex.

- It is the complete responsibility of the agency to provide basement ventilations as per 12.9 of part-III and C.1.6 of NBC part-IV of India

- It is the complete responsibility of the agency to comply with regulations of NBC and to provide smoking venting facilities for space use of exists as per clause 3.4.12 of NBC

- It is the complete responsibility of the agency to comply with regulations of NBC and to provide illumination of means of exit in stair case and corridors as per C.4 of NBC part IV

- It is the complete responsibility of the agency to comply with regulations of NBC and to maintain compartmentation in cellar as per C.9 of NBC Part-IV.

- It is the complete responsibility of the agency to comply with regulations of NBC and to maintain compartmentation to the building so that fire/smoke remain confined to the area where fire accident has occurred and does not spread to the remaining part of the building as per clause 9 of the NBC 2005 Part-IV, Annexure-C

- It is the complete responsibility of the agency to comply with regulations of NBC and to maintain openings in separating walls and floors attention to limit the fire spreading with fire resisting assemble as per clause 3.4.8 of NBC 2005 part-IV.

- It is the complete responsibility of the agency to comply with regulations of NBC and to provide a passage/escape path of the occupants

- It is the complete responsibility of the agency to comply with regulations of NBC and to maintain the limitations of the damaged to the buildings and its contents as per (Clause 3.4.11.1)

- It is the complete responsibility of the agency to comply with regulations of NBC and to maintain pressurization of stair cases as per clause 4.10 Part-IV of NBC

- It is the complete responsibility of the agency to comply with regulations of NBC and to provide fire doors with 2 hours resistance at appropriate places along with escape route and particularly at the entrance to the lift lobby and stair case to prevent spread of fire and smoke (Clause 4.29) part-IV of NBC 2005

- It is the complete responsibility of the agency to comply with regulations of NBC and to maintain smoke venting facilities for safe use of exists as per clause 4.29 of NBC Part-IV of 2005

- It is the complete responsibility of the agency to comply with regulations of NBC and to maintain  flame retardant materials for all interior decoration and upholstery to prevent generation of toxic smoke/flames and the surface shall comply clause 3.4.15 Part-IV of NBC 2005.

- It is the complete responsibility of the agency to comply with regulations of NBC and to maintain 2 Nos fire lift complying clause C1.5Q of annexure-IV of NBC 2005.

- It is the complete responsibility of the agency to comply with regulations of NBC and to maintain basement ventilation as per clause C1.6 of annexure-C of NBC 2005.

- It is the complete responsibility of the agency to comply with regulations of NBC and to maintain illumination means of exit in stair case and corridors as per clause C.1.4 of Annexure –C of part-IV of NBC 2005.

LIST OF APPROVED MAKES OF THE MATERIALS TO BE USED FOR FIRE PROTECTION SYSTEM

| S.No. | Materials | I.S. No | Brand |
| --- | --- | --- | --- |
| 1 | M.S.Pipes | 1239/3589 | TATA JINDAL |
| 2 | Gunmetal Valves (Full way check and globe Valves) | 778 | LEADER ZOLOTO SANT |
| 3 | C.I. double flanged sluice valves & Check Valves | 780 | UPADIAYA KARTAR AUDCO DEEPAK |
| 4 | Slim Seal Butterfly | ISI | KARTAR AUDCO ADVANCE |
| 5 | Slim Seal flap type Non Return Valves | 5312 | AUDCO KARTAR |
| 6 | Fire Hydrant Valves | 5290 | WIMCO ESSEL |
| 7 | Fire Hose Pipes C.P. Hose R.R.L Hose | 8423 636(Type A) | CRC NEW AGE |
| 8 | Fire Aid Fire Hose Reels (Drum & bracket ) | 884 | EVER SAFE FCE |
| 9 | Sprinkler Heads |  | VIKING/H.D. |
| 10 | Horizontal Centrifugal | 1520 | KIRLOSKAR, MATHER PLATT |
| 11 | Electrical Motors | 325 | KIRLOSKAR, CROMPTION/GRUNFOS |
| 12 | Electrical Switch Gear & Starter M. CCB |  | Siemens, L & T |
| 13 | Cables |  | Skytone/CCI/Polycab Asian (RPG) Gloster/ Universal/Nicco |
| 14 | Flow meter |  |  |
| 15 | Suction Strainer |  | ADCO SANT ZOLOTO |
| 16 | Vibration Eliminator Connectors |  | Resistoflex/ Kanwal/D. Wren |
| 17 | Single Phasing Preventor (Pipe protection) |  | L&T Siemens Minilec |
| 18 | Pipe Coat material(Protection) |  | PYPKOTE |
| 19 | Flow Switches |  | Plotter |
| 20 | Diesel Engine | 75,000/ TAC Approved | Ashok Leyland/ Kirloskar/ Cummins |
| 21 | Main Control Panel (Powder Coated) |  | Enron |
| 22 | Fire Bridge Inlet | 904 | FCE |
| 23 | Rubber Hose Inlet | 5132 | Padmini etc |
| 24 | Hose Coupling branch Pipe and nozzle | 903 | Wimco/ Arihant |
| 25 | Pressure Switches | TAC | INDFOSS SWITZER |
| 26 | Pressure Guage | 3624(CL-I) | H.GURU/FIEBIG |
| 27 | Battery |  | EXIDE/ PRESTOLITE/PANSONIC/AMARRAJA |
| 28 | Fire Extinguishers |  | Life Guard/ NAAZ |
| 29 | Paint |  | J & N/ASIAN/ NEROLAC/BERGER |
| 30 | AnnunciaterPanel for Sprinkler system | 2189 | PCD/SAFEWAY/AGNI(INDIA) Pinnacle |
| 31 | Alarm Valve & Hydraulic Alarm motor with covering |  | MATHER & PLATT/HD |
| 32 | Contactor |  | L&T/ SIEMENS/ MG Schinder |
| 33 | Thimbles/Ferrules (tinned Copper) |  | Dowel |
| 34 | Cable Glands |  | Commex/Power/Gripwell |
| 35 | Power Capacitor |  | L&T/ Cromption/ Asian |
| 36 | Measuring Meter( Digital) |  | L&T/ SIEMENS/ Enercon/Conserve |
| 37 | M.S.Conduit |  | Steel Craft/ BEC/ AKG |
| 38 | Dash Fastner |  | Hilti/ Fisher |
| 39 | Paint Primer |  | Asian/ Jenson Nicholson |
| 40 | Weld Electrodes |  | Advani/ Esab/ Victor |
| 41 | Pipe Supports |  | Chilly/ GMGR |
| 42 | Indication Lamps(LED) |  | L.T.SIEMENS Varshano |

I hereby agree to use materials from the makes specified against each item

DRAWINGS

DRAWINGS

1.0	DRAWINGS:

1.1	The plans enclosed with the bid are only for tender purpose and liable to be altered during execution of work as per necessity of site conditions.  The premium quoted by the contractor for various items shall hold good for execution of work even with altered plans.

1.2	One set of drawings, on the basis of which actual execution of the work is to proceed shall be furnished free of cost to the contractor by the APEWIDC /Executive Engineer progressively according to the work program submitted by the contractor and accepted 	by the APEWIDC /Executive Engineer.  Drawings for any particular activity shall be 	issued to the contractor at least 30 days in advance of the scheduled date of the start of he activity.  However, no extra claims by the contractor towards any delay in issue 	of drawing or issue of any revision / change to the drawings issued earlier shall be 	admissible. The Chief Engineer  shall intimate the contractor 7 days in advance	regarding any delay to issue of drawings, for any particular stage of work.  If work gets effected due to delay in issue of drawings, for any particular stage of work the contractor shall be granted extension of time in terms of Clause 28 of General Conditions of 	Contract.

1.3	Signed drawings above shall not be deemed to be an order for work unless they entered in the agreement and schedule of drawings under proper alterations has been sent to the contractor by the Engineer-in-Charge with a covering letter confirming that the drawing is authority for work in contract.

2.0	DISCREPANCIES:

2.1	In case of discrepancies between documents the following order of procedure shall apply:-

2.1.1	Between the written description of written dimensions in the drawings and the corresponding one in the specifications, the latter shall apply.

2.1.2	Figured dimensions shall supersede scaled dimensions.  The drawings on a larger scale 	shall take precedence over those on a smaller scale.

2.1.3	Drawings issued as construction drawings from time to time shall supersede bid drawings and also the correspondence drawings previously issued.

Note:	The contractor should not execute any component of work without obtaining the

working drawings.  Any work done without drawings shall be at the contractor’s responsibility only in the absence of any written order from the Engineer-in-Charge.

3.0	SECRACY CLAUSE:

The drawings and specifications made available to the bidder shall exclusively be used on the work and they are retained from passing on each plan to any unauthorised hand either in parts or in full under the provisions of Section-3 and 5 of the official secrets Act 1923.  Any violation in this regard will entail suitable action under appropriate clause or official secret Act 1923.

BILL OF QUANTITIES

AND

PRICE BID

(Schedule – A)

# Name of work:	Construction of 208 Houses along with infrastructure and amenities at R.Ganapavaram Village (Colony), Buttaigudem Mandal, Eluru District for Rehabilitaton of the PDFs of Chinturu ITDA.

# BILL OF QUANTITIESf

### PREAMBLE

- The Bill of Quantities shall be read in conjunction with the instructions to Bidders, General and Special conditions of Contract, Technical Specifications and Drawings.

- The quantities given in the Bill of Quantities are estimated and provisional and are given to provide common basis for biding. The quantities here given are those upon which the lumpsum bid cost of the work is based but they are subject to alterations, omissions, deductions or additions as provided for in the conditions of this contract and do not necessarily show the actual quantities of work to be done.  The basis of payment will be actual quantities of work ordered and carried out as measured by the Contractor and verified by the Engineer and valued at the estimate rate plus or minus bid percentage quoted in the Bill of Quantities where applicable, and otherwise at such rates and prices as the Engineer-in-Charge may fix within the terms of Contract.

- The estimate rates in the Bill of Quantities shall, except in so-far as it is otherwise provided under the Contract include cost of all constructional material, labour, machinery, transportation, erection, maintenance, profit, taxes and duties together with all general risks, liabilities and obligations set out or implied in the Contract.

- The plans enclosed with the bid are liable to be altered during execution of work as per necessity of site conditions.  The Bid percentage quoted by the bidder shall hold good for execution of work even with altered plans.

- The whole cost of complying with the provisions of the Contract shall be included in the estimated rates for items provided in the Bill of Quantities and where no items are provided in the Bill of Quantities, their cost shall be deemed to be distributed among the estimate rates entered for the related items of work.

- General directions and descriptions of work and materials are not necessarily repeated nor summarised in the Bill of Quantities.  References to the relevant sections of the Contract documentation shall be made before entering estimate rate against each item in the Bill of Quantities.

- The method of measurements of completed work for payment shall be in accordance with the relevant B.I.S. Codes & A. P. S. Specifications.

- All items of work are to be executed as per the drawings / specifications supplied with the contract documents.

If there is any contradiction between the drawings and the text of the specifications, the later shall prevail.

- The Bidder should inspect and select the quarries of his choice before he quotes the bid percentage in the Schedule of Bill of Quantities and satisfy himself about the availability of required quantum of materials.

- Diversion drains should be excavated before completion of the embankments and the useful soils should be used in the nearby embankments.

- The actual mix proportion by weigh batching to be adopted during execution will be got designed in the laboratories to suit the grade of concrete and mortar to be used.  It will be the responsibility of the contractor to manufacture concrete and mortar of required strength.

- The quantum of measurement for all items of earthwork involving conveyance manually or by machinery shall be as assessed by level measurement.  The measurements for the embankment will be for the consolidated banks only.

- Wherever bailing out of water is involved either for excavation or for foundations or for constructions, the percentage quoted shall take into account the dewatering charges necessary.  No separate payment will be made for dewatering.

- Wherever embankment work is involved, useful soils approved by the Engineer-in-Charge from the cutting reaches and diversion drains shall be taken and used for forming nearby embankments soils used for constructions will be at free of cost.

- The quoted bid percentage shall also include the work of any kind necessary for the due and satisfactory construction, completion and maintenance of the works according to the drawings and these specifications and further drawings and orders that may be issued by the Engineer-in-Charge from time to time.  The quoted bid percentage shall include compliance by the Contractor with all the general conditions of contract, whether specifically mentioned or not in the various clauses of these specifications, all materials, machinery, plant, equipment, tools, fuel, water, strutting, timbering, transport, offices, stores, workshop staff, labour and the provision of proper and sufficient protective works, diversions, temporary fencing and lighting.  It shall also include safety of workers, first aid equipments suitable accommodation for the staff and workmen, with adequate sanitary arrangements, the effecting and maintenance of all insurances, the payment of all wages, salaries, fees, royalties / Taxes, duties or other charges arising out of the execution of works and the regular clearance of rubbish, reinstatement and clearing-up of the site as may be required on completion of works safety of the public and protection of the works and adjoining land. The work of Building in quality control / assurance shall be deemed to be covered in the quoted percentage.

- The Contractor shall ensure that, the quoted bid percentage shall cover all stages of work such as setting out, selection of materials, selection of construction methods, selection of equipment and plant, deployment of personnel and supervisory staff, quality control testing etc.  The work quality assurance shall be deemed to be covered in the bid percentage.

- a) 	The special attention of the bidder is drawn to the conditions in the bid document/Schedule ‘A’ wherein reference has been made to the Andhra Pradesh Standard Specifications [APSS] and the Standard preliminary specifications containing therein. These preliminary specifications shall apply to the agreement to be entered into between the contractor and the Government of Andhra Pradesh and shall form an in-separable condition of the contract along with the estimate. All these documents taken together shall be deemed to form one contract and shall be complimentary to another.

b)	The bidder shall carefully study the drawings and additional specifications and all the documents, which form part of the agreement to be entered into by the successful bidder. The APSS and other documents connected with contract such as estimate plans, specifications, can be seen on all working days in the office of the Managing Director, APEWIDC

- The bidders attention is directed to requirements for materials under the clause ‘materials and workmanship’ in the preliminary specifications of APSS. Materials conforming to the Bureau of Indian Standards specifications, APSS etc., shall be used on the work and the bidders shall quote his overall bid percentage accordingly.

- The bidder has to do his own testing of materials and satisfy himself that they conform to the specifications of respective I.S.I Codes before biding.

- The contractor shall himself procure the required construction materials of approved quality including the earth for formation of embankment and water from quarries/sources of his choice.  All such quarries/sources of materials required for the work shall be got approved by the Engineer-in-Charge in writing well before their use of the work.

- The contractor shall himself procure at his own cost the steel, cement, Bitumen, Blasting materials, sand, metal, soils, etc., and such other materials required for the work well in advance. The contractor has to bear the cost of materials and their conveyance. The department will not take any responsibility for fluctuations in market in cost of the materials, transportation and for loss of materials etc.

- Inspection of site and quarries by the bidder: Every bidder is expected before quoting his overall bid percentage, to inspect the site of proposed work.  He should also inspect the quarries and satisfy himself about the quality, and availability of materials. The best class of materials to be obtained from quarries, or other sources shall be used on the work.  In every case the materials must comply with the relevant standard specifications.  Samples of materials as called for in the standard specifications or in this bid document or as required by the Engineer-in-Charge, in any case, shall be submitted for the Engineer-in-Charge’s approval before the supply to site of work is begun.

- The bidder’s particular attention is drawn to the sections and clauses in the A.P. standard specification dealing with

- Test, inspection and rejection of defective materials and work.

- Carriage

- Construction plant

- Water and lighting

- Cleaning up during the progress and for delivery.

- Accidents

- Delays

- Particulars of payments.

The contractor should closely peruse all the specification clauses, which govern the overall bid percentage he is biding.

- The defect liability period of contract in terms of G.O Ms No. 8, T(R&B) (R.I) Department  Dated: 8/1/2003 is twenty four months.

- The estimate rates for items shown in the Schedule “A” include all construction materials.  No escalation in rates will be paid unless specified in the bid document. The bidder has to quote an overall bid percentage considering all the aspects of the bid to complete the finished item of work as per the APSS/MORTH/B.I.S specifications, the special specifications appended, Drawings etc.

- If there is any contradiction between APSS/MORTH and B.I.S. specifications, listed and detailed technical specifications, the latter shall prevail.

- In case of a job for which specifications are not available with the Schedule or in APSS/MORTH or B.I.S code and are required to be prescribed, such work shall be carried out in accordance with the written instructions of the Engineer-in-charge.

- The contractor should use the excavated useful soils and stone for construction purpose.  Soils used for construction either for homogeneous section in hearting or in casing zone based on the suitability will be at free of cost and the cost of stone used for construction purpose will be recovered from the contractor’s bill.

The contractor should quote his bid percentage keeping in view of the above aspects.

- Additions and alternations by the Bidder in the Schedule of quantities will disqualify the bid.

- In the case of discrepancies between the written description of the item in the Schedule “A” and the detailed description in the specification of the same item, the latter shall be adopted.

- The Unit rates noted below are those governing payment of extras or deductions for omissions according to the conditions of the contract as set-forth in the preliminary specifications of the A.P standard specifications and other conditions of specification of this contract.

- It is to be expressly understood that the measured work is to be taken according to the actual quantities when in place and finished according to the drawings or as may be ordered from time to time by the Executive Engineer and the cost calculated by measurement or weight at their respective rates without any additional charge for any necessary or contingent works connected works connected herewith. The Percentage Excess or less on ECV quoted are for works in situ and complete in every respect.

- For all items of work in excess of the quantities indicated the rates payable for such excess quantities will be bided rates i.e., estimate rates plus or minus bid percentage.

- For all items of work, intermediate payment will be made provisionally as per relevant clause.  Full-accepted agreement rates will be paid only after all the items of works are completed.

- The contractor is bound to execute all supplemental works that are found essential incidental and inevitable during execution of main work.

- The payment of rates for supplement items of work will be regulated as under.

a)	Supplemental items directly deduceable from similar items in the original agreement

b)	The rates shall be derived by adding to or subtracting from the agreement rate of such similar item the cost of the difference in the quantity of materials labour between the new items and similar items in the agreement worked out with reference to the schedule of rates adopted in the sanctioned estimate with which the tenders are accepted plus or minus overall tender percentage.

c)	Similar items but the rates of which cannot be directly deducted from the original agreement.

d)	Purely new items which do not correspond to any item in the agreement.

The rate of all such items shall be estimated rates plus or minus overall bid percentage.

- EXTRA  ITEMS:

i)	Extra items of work shall not vitiate the contract.  The contractor shall be bound to execute extra items of work as directed by the Engineer-in-Charge.  The rates for extra items shall be worked out by the Engineer-in-Charge as per the conditions of the Contract and the same are binding on the Contractor.

ii)	The contractor shall invariably before 15th of every month, submit in writing to the Engineer-in-Charge a statement of extra items if any that they have executed during the preceding month failing which, the decision of allowing such items will be solely at the discretion of the competent authority.

- ENTRUSTMENT OF ADDITIOANAL ITEMS:

a)	Where ever additional items not contingent on the main work and outside the scope of original agreement are to be entrusted to the original contractor dispensing with bids and if the value of such items exceeds the limits up to which the officer is empowered to entrust works initially to contractor without calling for bids approval of next higher authority shall be obtained. Entrustment of all such items on nomination shall be rates not exceeding the estimate rates.

b)	Entrustment of supplement items contingent on the main work will be authorised by the officers up to the monetary limits up to which they themselves are competent to accept items in the original agreement so long as the total amounts up to which they are competent to accept in an original agreement rates for such items shall be worked in accordance with the existing procedure prescribed by the Government.

c)	Entrustment of the additional supplemental items shall be further subject to the provisions under para 176(b) of APWD Code Viz., the items shall not be ordered by an officer on his own responsibility if the revised estimate or deviation statement providing for the same requires the sanction of competent higher authority i.e. Government.

Note:	It may be noted that the term estimate rate used above means the rate in the sanctioned estimate with which the bid’s compared or if no such rate is available in the estimate the rate derived will be with reference to the schedule of rates adopted in the sanctioned estimate with which bids are compared.

SCHEDULE –A

BILL OF QUANTITIES

(PART – I)

# NAME OF WORK: 	Construction of 208 Houses along with infrastructure and amenities at R.Ganapavaram Village (Colony), Buttaigudem Mandal, Eluru District for Rehabilitaton of the PDFs of Chinturu ITDA.

# .

| Sl. No | Approximate quantity in figures/words | Description of work | Unit in figures/words | Estimate rate in figures/words | Amount in Rs. |
| --- | --- | --- | --- | --- | --- |
|  |  | Schedule - A ( PART- I ) enclosed separately |  |  |  |

SCHEDULE –A

BILL OF QUANTITIES

(Part-II)

(Details of Maximum amount reimbursable to the Contractor)

# NAME OF WORK:	 Construction of 208 Houses along with infrastructure and amenities at R.Ganapavaram Village (Colony), Buttaigudem Mandal, Eluru District for Rehabilitaton of the PDFs of Chinturu ITDA.

# *************

1)	GST as applicable on Value of work.

2)	Seigniorage charges @ 1% will be added and recovered from the work bills as per the theoretical requirement of materials.

NOTE:

1) The rates mentioned in Bill of Quantities (Part-I) are including overhead charges and contractors profit but excluding GST. The items covered under overhead charges are as per the Revised Standard Data communicated by the Government of Andhra Pradesh vide G.O Ms No.  49, I & CAD (PW-REFORMS) Dept., Dated : 02.03.2009.

3)   As the overhead charges includes engaging technical persons by the contractor and Work insurance, no reimbursement for these will be made separately.

4)  DELETED

5)	If the contractor fails to employ required technical personnel as specified in the agreement, work will be suspended or department will engage required technical personnel and recover the cost from the contractor at penal rate of two times thereof as per the respective SSR rates.

SCHEDULE-B

LIST OF DRAWINGS

# NAME OF WORK:  Construction of 208 Houses along with infrastructure and amenities at R.Ganapavaram Village (Colony), Buttaigudem Mandal, Eluru District for Rehabilitaton of the PDFs of Chinturu ITDA.

Sl. No.	                Drawing No.	                   Description

- Enclosed -

DECLARATION

I/We hereby declare that  I/We have inspected and satisfied myself/ourselves thoroughly and I/We am/are conversant with the local conditions, regarding all materials and about required for the work on which I/We have based my/our rates for the work. The Specifications, Plans, Designs and conditions of contract on which the offer has been based completely studied by me/us before submitting the bid.

SIGNATURE OF THE BIDDER

PRICE BID

[To be placed in the cover -‘B’]

# NAME OF WORK:	Construction of 208 Houses along with infrastructure and amenities at R.Ganapavaram Village (Colony), Buttaigudem Mandal, Eluru District for Rehabilitaton of the PDFs of Chinturu ITDA.

Estimated contract value (in figures & words):	Rs. 17,95,41,544/-

(Rupees Seventeen Crores Ninety Five Lakhs Forty One Thousand Five Hundred Forty Four Only)

I, Sri / Smt./ M/s. ………………………………………………………. do hereby express my willingness to execute the aforesaid work as per the conditions, standards, specifications, rules, regulations, etc., stipulated in the Bid Documents.

at an overall  tender percentage of -------------------(in figures) ……………………………………….(in words) excess/less over estimate contract value.

(OR)

at estimate contract value.

SIGNATURE, NAME OF THE BIDDER/AUTHORISED SIGNATORY

FORMATS OF SECURITIES

Annexure-I (a)

PROFORMA

BANK GUARANTEE FOR  EARNEST MONEY DEPOSIT

(At the time of Agreement)

To:

The Managing Director,

APEWIDC, Vaddeswaram

WHEREAS ……………………………….. (Name of the Contractor) (here in after called “the Bidder”) has submitted his bid response to NIT No…………………. dated:…………………… for the work “ ………………………………………………………………………………………………..” (Name of work) (hereinafter called “the bid”).

KNOWN ALL MEN by these present that we …………………………………………….……………. (Name and Address of Bank) ………………………………. (hereinafter called “the Bank” are bound unto ……………………… / (name of the designated MD) in the sum of  * …………………………………………………………………………………………………….. for which payment will and truly to be made to the said Department, the Bank binds itself, his successors and assigns by these presents.

SEALED with the Common Seal of the Bank this …………….. day of ……………..20….

THE CONDITIONS of this obligation are:-

- If after Bid opening the bidder withdraws or modifies his Bid during the period of bid validity specified in the Form of Bid.

- If the Bidder having been notified of the acceptance of his bid by the Department during the period of validity.

- fails or refuses to execute the Form of Agreement in accordance with the Instructions to Bidders, if required; or

- fails or refuses to furnish the balance EMD and additional performance Security in accordance with the instructions to Bidders.

We undertake to pay to the Department up to the above amount upon receipt of his first written demand, without the Department having to substantiate his demand, provided that in his demand the Department will note the amount claimed by him is due to him owning to the occurrence of one or both of the two conditions, specifying the occurred condition or conditions.

This Guarantee will remain in force up to and including the date** …………………… after the dead line for submission of Bids as such deadline is stated in the Instructions to Bids or as it may be extended by the Department, notice of which extension(s) to the Bank is hereby waived.  Any demand in respect of this Guarantee should reach the Bank not later than the above date.

DATE……………….		SIGNATURE OF THE BANK ……………………..

WITNESS………………..	SEAL………………………………………………..

--------------------------------------------------------------------------------------------------------

(Signature, Name and Address)

--------------------------------------------------------------------------------------------------------

*	The Bidder should insert the amount of the EMD in words and figures denominated in Indian Rupee.  This figure should be the same as shown in the NIT.

**	6 months from the deadline date for submission of Bid. Date should be inserted by the Department before the Bid documents are issued.

ANNEXURE-I(b)

PROFORMA

BANK GUARANTEE FOR BALANCE E.M.D

(At the time of Agreement)

______________________________________________(name & address of Department)

______________________________________________

WHEREAS__________________________________________________ ________ _____________________________________________________________________ _____ __ _____________________(name and address of Contractor )  (hereinafter called “the Contractor”) has undertaken, in pursuance of Contract No. ________ dated: ____________ to execute  the work of _________________ [name of work];

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a Schedule bank for the sum specified therein as````````````` balance EMD / EMD for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE we hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of _____________________ [amount of guarantee]  _________________________________ [in words], such sum being payable and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ________________________ [amount of guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee shall be valid upto ……………………….. i.e., until 28 days from the date of expiry of the Defects Liability period.

Signature & seal of the Guarantor_____________________

Name of Bank_____________________________________

Address__________________________________________

Date_____________________________________________

ANNEXURE - I(c)

### PROFORMA

BANK GUARANTEE FOR ADDITIONAL FURTHER SECURITY

_______________________________________________(name and address of Department)

_______________________________________________

WHEREAS _______________________________ (name and address of Contractor) (hereinafter called “the Contractor”) has undertaken, in pursuance of Contract No. ________ dated: ____________ to execute _________________________ [name of Contract and brief description of works] (hereinafter called “the Contractor”);

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a Schedule bank for the sum specified therein as Additional further security bank guarantee for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE we hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of Rs._____________________ [amount of guarantee] _________________________________ [in words], such sum being payable and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ________________________ [amount of guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed there under or of any of the contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee shall be valid up to and until 28 days from the date completion.

Signature & seal of the Guarantor_____________________

Name of Bank_____________________________________

Address__________________________________________

Date_____________________________________________

# Annexure – I I

# FORM OF SOLVENCY CERTIFICATE BY BANKS

# (From Nationalised Banks / Scheduled Banks)

# I,_________________________ Managing Director/Manager/General Manager/ Agent of _______________________ Bank Limited do hereby certify that  a_________________________________________ _______________________ [here the Names and addresses of the contractor] to be solvent to the extent of Rs.__________________ [Rupees __________________________ ________________________________] as disclosed by the information and record which are available with the aforesaid bank.

# For the ___________________________ Bank

# Date:

# Place:

# Signature of Bank Manager

# [Authorised to Sign]

format for evidence of access to or

availability of credit facilities

(CLAUSE 8 (iii) OF TENDER NOTICE)

# (From Nationalised Banks / Scheduled Banks)

Bank Certificate

This is to certify that M/s. ……………….........................................……… is a reputed company with a good financial standing. If the contract for the work namely …………… …………….....…………………. is awarded to the above firm, we shall be able to provide over draft/credit facilities to the extent of Rs.……… to meet their working capital requirements for executing the above contract.

Signature of Sr. Bank Manager

Name of Bank

# Address of Bank

# CLEARANCE CERTIFICATE

# 1.		Name of the Dealer:

# 2.	Address:

# 3.	TIN:

# The above dealer has filed returns up to date (Month & Year ) and has paid Taxes due there in.

# The dealer has no pending arrears under APVAT Act 2005, CST ACT 1956 and APGST ACT 1957, A.P Entry Tax Act as on date.

# This certificate is valid up to a period of Twelve months from the date of issue.

# Date:

# Place:

# Assessing authority