TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED VOLUME - I ## SPECIFICATION NO: ## APT-e- 42 (CE/Zone/Kadapa)/2026-27 Name of the work: Replacement of existing ACSR Lynx conductor (16.37KM) with AAAC Panther conductor for 132KV Chittoor – Pakala SC line in Chittoor District under RMI 2024-25 on turn key basis CHIEF ENGINEER/ ZONE / KADAPA, APTRANSCO, TRANSSCO NILAYAM,, Sankarapuram, Kadapa, Andhra Pradesh 516002 Ph : 9440877700, 9490154205 Web site : www.apeprocurement.gov.in

VOLUME - I I N D E X Sl. No.; Description; Page No.. 1); Instructions To Bidders; 3. 1.0 General. 2.0 Bidders / Firms eligible to Bid. 3.0 Documents to be furnished. 4.0 Submission of bids. 5.0 Contents of the specification. 2); General Terms & Conditions (Section-I); 10. 3); Financial Terms & Conditions (Section-II) 27; 38. 4); Schedules ( I – X ); 63-80. 5); Check List (XI) 58; 81. 6); Schedule XII; 82. 7); Forms (A- F) 59 - 67; 83-90. 8); List of approved Manufacturers 68 - 71; 91-97. 9); List of approved Banks 72; 98. 10); Completion period (Schedule – D); 99. 11); List of makes of the materials proposed to supply if the contract is awarded (Schedule-E); 100. 12); Notice Invitation for Bids; 101. 12); Project Data sheet; 103. 13); Qualification Requirement; 104. Schedules. Price Schedules for Equipment/Material( Schedule –A); In Separate XL file. Price Schedules for Works ( Schedule –B ). Financial Bid/Price Bid ( Schedule – C).

# INSTRUCTIONS TO THE BIDDERS

  - General: The APTRANSCO invites bids on e-procurement platform for the works mentioned in the NIT and Project Data sheet for which date and time is specified in the NIT and will be opened online by either Bid inviting authority or his nominee based on the date and time mentioned in the NIT. The details of Bid inviting authority are mentioned in the Project Data Sheet.

  - The Bids should be in the prescribed form as per this specification and as per the guidelines of e-procurement and as specified in NIT and Bidding documents which can be downloaded free of cost from the website www.eprocurement.gov.in

  - The dates stipulated in the NIT are firm and under any circumstances they will not be relaxed unless officially extended by APTRANSCO in e-procurement plat-form.

  - The e-Procurement application is PKI (Public Key Infrastructure) enabled and supports the digital certificates issued by APTS Ltd.,(Andhra Pradesh Technology Services Limited) for signing the bids at the time of submission by bidder. The bidder has to procure the digital certificates issued by APTS Ltd., Vijayawada by following the procedure laid for the same. Digitally signed bids are to be submitted electronically through e-procurement without which the Bid will not be considered for opening.

  - The intending Bidders would be required to enroll themselves on the ‘e’-procurement market place at www.eprocurement.gov.in. If the bidders intend to know the procedure of bid submission on e-procurement platform, suitable training will be given by APTS Ltd, , 1st floor, ITEC Department, Indira Gandhi Municipal, Near Nalanda college, Beside Meeseva, Labbipet, Vijayawada-520010 Bidders are required to submit their bids in two parts:

      - Part-I :  Eligibility and Technical bid.

      - Part-II:  Financial bid.

  - The Bidder should upload scanned copies as specified in checklist and all enclosures required for the schedules and Appendices. The bidder should produce the originals of all uploaded documents for verification if asked for by the Competent Authority within 3 (Three) days.

  - The uploading of bids on-line through e-procurement cannot be possible after expiry of due date and time and it is sole discretion of APTRANSCO to consider any requests for extension.

  - Estimated Contract Value (ECV) : The basic contract Price is Rs.2,20,13,114/-exclusive of GST. GST at the rate applicable from time to time shall be paid additionally against submission of a valid tax invoice, subject to compliance with the applicable GST laws. The estimated GST at the prevailing rate of 18% is Rs.39,62,360.52 and the total present financial commitment, including GST, is Rs.2,59,75,474.52/-

  - Transaction fee:   The Transaction fee at 0.03% on Estimate Contract value (ECV) of work plus18 % GST on transaction fees shall be payable by electronic Payment on e-Procurement platform, which provides a facility to participating suppliers/ contractors to electronically pay the transaction fee from the platform, using their credit cards. The Payment Gateway accepts all Master and VISA credit cards issued by any bank.The payment of transaction fee online is mandatory for participating in the bidding.

  - Successful Bidder shall pay the Corpus fund to APTS @ 0.04% on ECV in the form of DD payable at Vijayawadaand drawn in favour of MD, APTS, Vijayawadato sustain ‘e’ procurement initiatives, research and development of software application for automation for process in user departments.

  - The successful Bidder is expected to complete the work within the time period specified in the Schedule – D and as per PERT/BAR Chart to be furnished by the Successful bidder at the time of kickoff meeting

  - APTRANSCO reserves the right to cancel/extend/alter the bid conditions at any time. In the process, if the tender process / works are stalled due to legal intervention or due to natural calamities, no compensation will be paid.

- Bidders / Firms eligible to Bid:

The Bidders / Firms who

- Possess the valid registration and satisfies all the conditions therein.

- Are not blacklisted or debarred or suspended by the Government /any power utility for whatever the reason, prohibiting them not to continue in the contracting business.

- Have complied with the eligibility criteria specified in the Clause 3 of General Terms & Conditions in Section -1 of this Specification are the eligible Bidders  /Firms.

  - Bidders / Firms ineligible to Bid:

- A retired officer of the Govt. of AP or Govt. of India or APTRANSCO or their subsidiaries’ is disqualified from tendering for a period of two years from the date of retirement without the prior permission of the Parent Department.The contractor shall intimate the list of his employees who were retired from Government/APTRANSCO along with the permission possessed from parent department.  The contractor shall intimate the list of his employees who were retired from Government/APTRANSCO along with the permission, they posses from parent department.

- The Bidder who has employed any retired officer as mentioned above shall be considered as an ineligible Bidder.

- The contractor himself or any of his employee is found to be Gazetted Officer who retired from Government Service and had not obtained permission from the parent department for accepting the contractor’s employment within a period of 2 years from the date of his retirement.

- The Contractor or any of his employees is found at any time after award of contract, to be such a person who had not obtained the permission of the Government as aforesaid before submission of the Bid or engagement in the Contractor’s service.

- Contractor shall not be eligible to Bid for works in APTRANSCO where any of his near relatives are employed in the rank of Assistant Engineer or Assistant Executive Engineers and above on the Engineering side and Assistant Accounts Officer and above on the accounts side.  The Contractor shall intimate the names of persons who are working with him in any capacity or are subsequently employed.  He shall also furnish a list of Gazetted / Non-Gazetted State Government Employees related to him.  Failure to furnish such information Bidder is liable to be removed from the list of approved contractors and his contract is liable for cancellation.

Note:  Near relatives include

- Sons, step sons, daughters, and step-daughters.

- Son-in-law and daughter-in-law.

- Brother-in-law and sister-in-law.

- Brothers and Sisters.

- Father and Mother.

- Wife / Husband.

- Father-in-law and Mother-in-law

- Nephews, nieces, uncles and aunts

- Cousins and any person residing with or dependent on the contractor.

vi)  The Companies which are blacklisted by any other utility and whose promoters firms or companies were already blacklisted /debarred by any other utility shall be considered as ineligible bidder. Further, the bidder shall give an undertaking(as per Schedule V- (E)that, if the information furnished in this regard is found to be false at a later date the bidder will be made ineligible or the contract will be terminated.

- Documents to be furnished for Qualification requirements of the Bidders:

  - The Bidder shall furnish the following particulars in the formats provided online and supported documentary evidence shall be uploaded.

Attested copies of documents relating to the Registration of the firm, Registration as Electrical Licensed Contractor in A.P, Partnership deed, Articles of Association, GSTIN registration certificate,Latest Income Tax Clearance certificate / PAN number from IT Department,Labour department registration etc.

Note: The Partnership firms, which are registered as Contractors shall intimate the change in partnership deed, if any, as per GO Ms No.58, I & CAD, dt.23.4.2002 within one month of such change. Failure to notify the change to the registration authority in time will entail the firms to forfeit their registration and their Bid will be rejected.  The intimation of change of partners if any and the acceptance by the Registration authority may be enclosed.  Further the change if any in the official address, phone/fax numbers etc., shall be intimated.

- Availability of key personnel for administration /site management and execution viz., technical personnel required for the work.

- Qualification criteria for opening of the price bid: Bidders qualified in the Technical /                   Pre-qualification Bid if they meet the requirements as per clause no. 3 ‘Qualification Requirements’ of Section -1

- Even though the Bidders are meeting the above qualification requirements, they are liable to be  disqualified / debarred / suspended / blacklisted if they have

- Furnished false / fabricated particulars in the forms, statements and /annexure submitted in proof of the qualification requirements and/or

- Not turned up for entering into agreement, when called upon with in the time specified in the letter of acceptance

- Record of poor progress such as abandoning the work, not properly completing the contract, inordinate delays in completion, litigation history or financial failures etc., and

- A history of criminal record in which the Bidder is involved if any.

- History of litigation with Government/APTRANSCO during the last 5 years in which the Bidder is involved.

f)	Any wrong declaration or hiding of information on clause (vi) above shall be viewed seriously and such firms will be blacklisted /debarred.

  - Even while execution of the work, if found that the work was awarded to the Contractor based on false /fake certificates of experience, the Contractor will be blacklisted and work will be taken over.

  - The bidders shall submit a written Power of Attorney authorizing the signatory of the bid to commit on behalf of the bidder.

  - Bidders are advised to find out the latest tax structure, applicability and rates before quoting the plus or minus tender percentage on ECV. Further to reduce the billing difficulties, bidders are advised to quote the percentage with not more than two decimal places.

  - SITE VISIT:  The bidders are advised to visit and examine the site of proposed Substations and the route of transmission line and obtain all information that may be necessary for preparing the bid such as access to site, communication, transport, leads and availability for water, sand, metal etc., right of way, the quantity of various items of work, the availability of local labour, availability and rates of materials, local working conditions, uncertainties of weather and period of crops and working seasons, involvement of river crossings, railway crossings etc.  The cost of visiting the site shall be at bidder’s own expense. Ignorance of site conditions shall not be accepted by the Purchaser as basis for any extra claim or additional rates or any compensation at a later date. The submission of a bid by the bidder will be construed as evidence that such an examination was made and later claims/disputes in this regard shall not be entertained.

  - It is the responsibility of the bidder to satisfy himself that sufficient quantities of construction materials required for the works shall exist in the borrow areas or quarries sites. The APTRANSCO does not accept any responsibility either in identifying the quarries or procuring the material or any other facilities in this regard.  The bidder will not be entitled for any extra cost /rate or claim for the misjudgment on his part for quantity and quality of materials available in the quarries.

3.9.1 Pre-Bid Meeting: Perspective Bidders can attend the pre-bid meeting to be held in the chambers of CE/Zone/Kadapa on the date notified in the NIT and seek clarifications/ doubts on any portion of the specification in writing. The purchaser will issue clarification in writing, if necessary.

- SUBMISSION OF BIDS :

The bidders who are desirous of participating in ‘e’- procurement shall submit their Technical bids, Price bids etc., in the standard formats prescribed in Bid documents, displayed at ‘e’- market place. The bidders should upload the scanned copies in support of their bids. Bidder should take care that the scanned copies are clear & visible. The bidders shall sign on all the statements, documents, certificates, being uploaded by them, owning responsibility for their correctness / authenticity.

If any bidder uploads the bid without paying BID SECURITY, the bid will be rejected and the bidder will be black listed. Similarly, if any of the certificates, documents, etc., uploaded by the bidder is/are found to be false / fabricated / bogus, the bidder will be blacklisted and his BID SECURITY forfeited.

The bids shall be uploaded on e-procurement platform with all particulars called for in the schedules enclosed to specification. Bid rates shall be furnished in the enclosed schedules only. There shall not be any deviation from the contents, description, quantity of the schedule. If the required documents, schedules, forms, supporting documents for Qualifying Requirements (both physical & Financial) are not uploaded on e-platform, the bid will be liable for rejection.

The information sought-for under schedules regarding qualification, financial status etc., shall be uploaded duly filling by typewritten in the formats attached, without interlineations, alterations or modifications. The bidder shall sign all pages of the bid and at the modification / corrections if any before uploading.

In case of JV, the lead partner should only submit the bid in e-procurement or otherwise the bid will be rejected at Prequalification stage itself.

Standard printed conditions uploaded along with the bid will not be considered or accepted. Deviations from the provisions of the specification will not be considered.

It is the responsibility of the Bidder to upload all the signed and scanned documents, Schedules, formats and other documents in the PDF format only. For the Price Bid (Schedule-A, B & C) the bidder shall submit both the downloaded commercial bid in XL file and also signed and scanned PDF file. The Quantities and description against the items of the Schedules shall not be modified.

It is the responsibility of the Bidder to upload all the documents required to prove his responsiveness to participate in this bidding as per the Qualification Requirements.

The bids once submitted on e-procurement platform cannot be withdrawn after scheduled bid submission closing date and also during bid validity period.

If any bid is withdrawn during the above period, the bidder will be blacklisted apart from forfeiting of bid security.

  - Submission of Price Bids:The bid consists of  the estimated cost of Materials in Schedule-A and estimated cost of labour, civil works and erection cost of equipment and materials in the Schedule-B which will be based on the prevailing market rates and SSR of the current year including all applicable taxes, duties etc., Bidder has to quote in Schedule-C, the percentage excess/ on par/ less on the total Estimated Contract Value of the materials and works given in the Schedule-A plus Schedule-B plus Project Insurance. The resultant amount in Schedule-C shall be quoted as lump sum amount in Bid Form.

  - (i)      As per G.O. Ms. No. 174 dated 01-09-2008 of I & CAD (PWR) submission of original hard

copies of the uploaded copies of DD/BG towards EMD and other certificates & documents by participating bidders to the tenders inviting authority is dispensed herewith.

        - All the bidders shall invariably upload the scanned copies of DD/BG/Insurance Surety Bond issued by Insurance Companies as per IRDAI guidelines in e-procurement system and this will be the primary requirement to consider the bid as responsive.

      - The Department shall carry out the technical bid evaluation solely based on the uploaded certificates/documents, DD/BG/Insurance Surety Bond issued by Insurance Companies as per IRDAI guidelines towards EMD in the e-procurement system and open the price bids of the responsive bidders.

      - The Department will notify the successful bidder for submission of original hard copies of all uploaded documents DD/BG/Insurance Surety Bond issued by Insurance Companies as per IRDAI guidelines towards EMD prior to entering into agreement.

      - The successful bidder shall invariably furnish the original DD/BG/Insurance Surety Bond issued by Insurance Companies as per IRDAI guidelines towards EMD, certificates/ documents of the uploaded scanned copies to the Tender inviting authority before entering into agreement either personally or through courier or post and the receipt of the same with in the stipulated date shall be the responsibility of the successful bidder.  The department will not take any responsibility for any delay in receipt/non receipt of original DD/BG/Insurance Surety Bond issued by Insurance Companies as per IRDAI guidelines towards EMD, certificates/documents, from the successful bidder before the stipulated time.  On receipt of documents the department shall ensure the genuinity of the DD/BG/Insurance Surety Bond issued by Insurance Companies as per IRDAI guidelines towards EMD and all other certificates/documents uploaded by the bidder in e-procurement system in support of the qualification criteria before concluding the agreement.

      - If any successful bidder fails to submit the original hard copies of uploaded certificates/ documents, DD/BG/Insurance Surety Bond issued by Insurance Companies as per IRDAI guidelines towards EMD within the stipulated time or if any variation is noticed between the uploaded documents and the hard copies submitted by the bidder, the successful bidder will be suspended from participating in the tenders on e-procurement plat form for a period of 3 years.  Besides this, APTRANSCO the department shall invoke all processes of law including criminal prosecution of such defaulting bidder as an act of extreme deterrence to avoid delays in the tender process for execution of the development schemes taken up by the Government.

  - Bids will be opened on-line at the time, date and place indicated in the NIT.

  - The bidders shall carefully examine the specification and all its enclosures and if they have any doubt as to the meaning of any portion of the specification or enclosures thereto, they shall obtain the required clarifications from the officer to whom the bids are addressed.

  - THE BIDS RECEIVED BY, OTHER THAN E-PROCUREMENT PLATFORM SHALL NOT BE ENTERTAINED UNDER ANY CIRCUMSTANCES.

  - The bidders are therefore advised to ensure that their bids are uploaded in complete shape in the first instance itself.  Post bid rebates, revisions or deviation in quoted price and/or conditions or any such offers which will give benefit to the bidder over others will not only be rejected straight but the original bid itself will get disqualified on this account and the bidder’s bid security amount will be forfeited.

  - COMPLETENESS OF BID:

  - The bid shall be quoted for all the works & all the items as per the bid specification.

  - Part bids or incomplete bids will not be accepted and will be rejected.

- Contents of the specification:

- Volume –I:

- Instructions To Bidders

- General Terms & Conditions (Section-I)                                      In the word file

- Financial Terms & Conditions (Section-II)

- Schedules    ( I – X )

- Check List   (XI)

- Forms    (A- F)

- List of approved Manufacturers

- List of approved Banks

- Price Schedules for Equipment/Material( Schedule –A)

- Price Schedules for Works ( Schedule –B)	(As separate XL file)

- Financial Bid/Price Bid    ( Schedule – C)

- Completion period (Schedule – D)

- List of makes of the materials proposed to be supplied

if the contract is awarded  (Schedule-E)

- Notice Inviting Bid    		-	In the word file

- Project Data sheet                    -

- Qualification Requirements	-

- Quality Assurance Plan  	-	As separate PDF file.

    - Formats

          - (i) Bank Guarantee proforma for Bid Security

(ii) Insurance Surety Bond Proforma for Bid Security

          - (i) Bank Guarantee proforma for performance security.

(ii) Insurance Surety Bond Proforma for Performance security

          - Bid form

          - Format for Bank’s Certificate for credit facilities

          - Format for joint venture agreement

          - Format for power of attorney for joint venture

iii) Volume-II:	Technical Specifications: (The drawings and GTPs are standardized and approved drawings & GTPs are available in APTRANSCO website.(www.aptransco.gov.in)

- General

- Technical specifications of  all Material

- Technical specifications of all equipment  	         In separate word files

- Technical Specification of Works 			in Volume-2 folder

- Technical specification for civil works

- Technical Specifications of AAAC Panther conductor       In separate folder File

and its Hardware

    - Schedules: To be filled up and furnished along with the bid. In case of joint venture,  schedules are to be filled up by both the partners

- Particulars of Registration 					:Schedule-I

- Details of Technical personnel					: Schedule-II

- Details regarding Financial standing 				: Schedule-III(A)

- Financial Turnover						: Schedule-III(B)

- Details of Works /Contracts executed                          		: Schedule-IV(A)

- Details of FabricatedTowers and structures                 		:Schedule-IV(B)

- Details of works under execution(APTRANSCO)		: Schedule - V (A)

- Details of works under execution other than APTRANSCO	:Schedule - V (B)

- Details of all ongoing works and balance Commitment	:Schedule - V I

- Under taking with regard to the Q.R				: Schedule - V (D)

- under taking with regard to the blacklisting by other utilities: Schedule - V (E)

- Details of gangs available  					:Schedule-VI

- Details of vehicles and T & P available			:Schedule-VII (A&B)

- Undertaking regarding relatives 				:Schedule-VIII

- Declaration for taking up awarded works  			:Schedule-IX

- Bank A/c. details for RTGS					:Schedule-X

- Check List							:Schedule-XI

- Declaration                                                                   : Schedule XII

- Price Schedules of Material 					:Schedule-A

- Price Schedules of Works					:Schedule-B

- Price Bid							:Schedule-C

- Completion Period & Bar Chart				:Schedule-D

- Makes of Materials proposed to supply			:Schedule-E

NOTE:

      - APTRANSCO is not responsible for any omissions in the bid specification downloaded by the bidders from the web site.

      - The bidders can verify the accuracy of the downloaded bid specification with the master copy available at the office mentioned in the Project Data Sheet.

      - The bidders are requested to check / verify the web site before scheduled closing date for any changes/ amendments in the tender.

***

TABLE OF CLAUSES – SECTION – I  ::    GENERAL

| Clause. No. | Description |
| --- | --- |
|  | Definition of terms |
|  | Scope of the contract |
|  | Qualification requirements |
| 3.1 | Physical experience |
| 3.2 | ## Financial turnover |
| 3.3 | ## Joint Venture |
|  | # General |
| ## 4.1 | ## Performance based experience |
| ## 4.2 | ## Awarding contract for more than one work |
|  | Bid validity |
|  | Bid security |
|  | Discrepancies |
|  | Evaluation of bids |
|  | Notification of award and acknowledging: |
|  | Service conditions |
|  | Sub-contractor and sub-orders |
|  | Power to vary or omit work |
|  | Execution of works relating to power line crossings and railway crossings: |
|  | Electricity rules: |
|  | Regulation of local authorities and statutes |
|  | Co-ordination with statutory bodies and other agencies |
|  | Co-operation with other contractors |
|  | Contractor's cooperation with the purchaser |
|  | Employment of technical staff for supervision, skilled and unskilled labour |
|  | Liability for accidents to persons: |
|  | Liability for damage to works and plants: |
|  | Approval of sub-vendors for equipment / materials |
|  | Quality assurance plan |
|  | Quality control & inspections |
|  | Time control |
|  | Management /co-ordination meetings |
|  | Site stores |
|  | Contractor's site office |
|  | Clearing up the site |
|  | Change orders |
|  | Water & power |
|  | Operation and maintenance manuals: |
|  | Safety plans |
|  | Bill of materials: |
|  | Photographs and progress report |
|  | Measurement of work and progress payments |
|  | Protection of work |
|  | Fire protection |
|  | Security (watch & ward) |
|  | Testing and commissioning |
|  | Indemnity bond for all materials |
|  | Accounting of surplus materials/ settlement of material account |
|  | Completion of Balance works and Handing Over |
|  | Manning of Substations Final account |
|  | Final Account |
|  | Taking over47.Technical Audit |

SECTION – I:  GENERAL

The Transmission Corporation of Andhra Pradesh Limited, hereinafter referred to as the APTRANSCO, invites bids for the Works as mentioned in the NIT and PROJECT DATA SHEET of this Specification.

      - DEFINITION OF TERMS:

In the contract, the following expression shall, unless the contract otherwise requires, have the meanings hereby respectively, assigned to them.

- The 'Purchaser/Employer' shall mean the Transmission Corporation of Andhra Pradesh Limited and shall include its successors and permitted assigns.

- The ‘Bidder’ shall mean the firm/company who is uploading their bids online to APTRANSCO.

- The 'Contractor' shall mean the bidder whose bid has been accepted by the purchaser and shall include the bidder's heirs, legal representatives, and successors and permitted assigns.

- The ‘Manufacturer’ shall mean the firm/company named in the contract, to whom the supply of material/ equipment and services of erection is entrusted by the contractor.

- The 'Engineer' shall mean the officer placing the order for the work with the Contractor and such other officer as may be authorized and appointed in writing by the Purchaser to act as Engineer for the purpose of supervising the Contract.

- The 'Supervising Engineer' shall mean such officer as may be duly appointed from time to time by the Purchaser or his Engineer to take general control and supervision of work.

- The 'Inspector' shall mean any person or persons nominated by the Purchaser and/or the Engineer to inspect stores or works under the agreement and/or his duly authorized representative appointed to act as the Inspector.

- The 'Contract' shall mean and include the bid and acceptance thereof, the general conditions, special conditions, Specifications, Schedules, drawings, Form of Bid, covering letter, schedules of prices, the final General conditions and the format Agreement executed on the stamped paper.

- The 'Specification' shall mean collectively all the terms, stipulations, and conditions of contract, technical provisions and annexure thereto and list of corrections and amendments mutually agreed upon from time to time in writing.

- ‘Tests on completion' shall mean such tests, as are prescribed by specification, to be made by the Contractor to the satisfaction of the purchaser before the work is taken over by the Purchaser.

- 'Commissioning' shall mean the satisfactory commissioning and operation of the equipment/work as specified in the project, after all necessary initial tests, checks and adjustments required at site, if any, have been satisfactorily completed and the equipment / works have been successfully charged.

- 'Commercial use' shall mean the use of the work, which the contract contemplates or of which it is commercially capable.

- 'Approval' shall mean the written approval of the Engineer and of the statutory authorities wherever such authorities are specified by any codes or otherwise.

- 'Month' shall mean calendar month.

- 'Writing' shall include any manuscript, typewritten or printed, statements, under or over signature or seal as the case may be.

- 'Letter of Intent' shall mean the purchaser's letter conveying his acceptance of the bid, subject to such reservations as may have been stated therein.

- ‘ECV’ shall mean Estimated Contract Value.

- ‘RTGS’ shall mean Real Time Gross Settlement.

- GST means Goods and Service Tax

      - SCOPE OF THE CONTRACT:The brief description of work/ project is mentioned in the NIT and Project Data Sheet. The detailed scope of work/ project is as per the schedules enclosed and as per the technical specifications given in Volume –II.

(A) 	Transmission Lines/ Substations:

- The APTRANSCO shall provide approved profiles, approved layouts, tower schedules.

- The contractor shall procure the materials / equipment with technical parameters as per the

technical specification volume-II, from the approved list of manufacturers / suppliers only

and execute the works as per the approved profiles / approved layouts. It is the responsibilityof the contractor to complete the works in full shape and handover to APTRANSCO in fullyoperational condition within the time specified in the contract.

- Being the turnkey work, if any petty/ minor items required for erection of the substations & lines, even though they have not been specifically included in this specification but are necessary for successful erection / operation of the substations & lines are deemed to be included in the specification.

d)    All the approved GTP’S &drawings of equipment/material are available at APTRANSCO

Websitei.e.www.aptransco.gov.in. However, the successful bidder shall obtain the approval  of General Technical Particulars and drawings of the equipment/materials required for the specified project which are available / not available in the APTRANSCO website from the Chief Engineer/Zone/ Kadapa.

3 	QUALIFICATION REQUIREMENTS:

The Bidder should upload the supported documents which are mandatory.

  - Physical Experience Requirements: Enclosed separately along with Project Data

## 3.2	FINANCIAL TURNOVER:

The Bidder should have the bid capacity not less than the estimated contract value or  value of work put to tender. The bid capacity will be calculated as per formula (2AN-B)> ECV. The bidder/Firm/ Company shall be a profit making Company.

where

A    =	Max. Value of Works executed in any one financial year during the preceding 5 financial years (updated to the current price level with a simple weightage of 10% per each financial year) taking into account the completed as well as works in progress. With regard to execution of the works during the last 5 years, the bidder shall produce the Chartered Accountant’s certificate with audited and approved profit and loss statement shall be produced.

N   =	Number of years prescribed for completion of the works for which tenders are invited. If N is less than 6 months it will be taken as 6 months

B    =	Value of existing commitments and ongoing works to be completed during the period of completion of work for which tenders are invited.

ECV = Estimated Contract Value (or) The Value of work put to tender

The bidder shall produce the statement showing the value of existing commitment and ongoing works as well as the stipulated period of completion remaining for each of the works. The statement must be supported by certificates issued by officers of the State/Central Government Department / Under takings not below the rank of Executive Engineer or the officer of equivalent rank and counter signed by the Superintending Engineer or the officer of equivalent rank (or) The bidder shall produce a declaration as mentioned below on a non-judicial stamp paper of Rs.100/- duly notarized.

“I, Sri/ Smt. /M/s………………… ……………… ……… ………   ……………………… do hereby solemnly affirm and declare that the balance works on hand as per the details furnished in  tender schedule  are true and also declare that in case it is found to be false fake/incorrect at a later date,  I/We will abide by any action such as disqualification or termination of contract under clause 60(a) PS to APSS or black listing or any other action deemed fit by APTRANSCO .”

Signature of the Bidder

3.3. 	Joint Ventures:

(This clause is applicable for the works /tenders with ECV more than Rs. 10.00 crores only)

Joint Venture Clause:

The bidders can also participate as a Joint-Venture containing not more than two firms/companies. The Physical / Technical experience and financial turnover of the partners of the Joint venture shall be added together to determine the JV bidder’s compliance with the minimum qualifying criteria set out in the specification. However, in order for a Joint Venture to qualify, the partners of Joint Venture must meet the following minimum criteria.

- The joint venture here in mean, Firms/companies not more than two, which are having Joint Venture agreement between them to participate and to execute the notified transmission project of APTRNASCO and shall clearly mention in the JV agreement, that both firms jointly and severally shall have responsibility in performing the project.

- The lead partner shall have at least 40% of the bid capacity which will calculated as per formula (2AN-B)> ECV.  However both the JV partners put together shall meet the required bid capacity.

- The lead partner shall have the following minimum technical experience.

- In case of tendered project involves multiple works like Sub-Station and Transmission line, then the lead partner shall meet technical qualification mentioned in the Specification either for one Sub-Station or for Transmission line.

- In case the tendered project involves only Transmission line, then the lead partner shall meet at least 50% of the technical qualification mentioned in the Specification.

- In case the tendered project involves only Sub-Station / Switching station / bay extensions, then the lead partner shall meet 100% of the technical qualification mentioned in the Specification.

However both the JV partners put together shall meet the technical qualification and financial bid capacity as required / as mentioned in the Specification.

- Any of the JV partners participating in the present tender, shall not participate in association with other bidders or participate individually in the same tender. If any one of the JV partners participates / submits more than one bid either individually or as JV partner, all such bids will be made disqualified and their bids will not be evaluated further.

- However, in order to qualify the Bid submitted by a JV partners, they shall comply with the following requirements. The joint venture bid with non-compliance of the following provisions will be disqualified.

  - Joint venture shall be represented by technical member as lead partners for the purpose of execution of the Bid. All the Payments shall be made through RTGS to the lead partner account as per the bank details mentioned in the Bid.

  - The uploaded scanned bid shall have authorised signatures of both the partners so as to be legally binding upon both members.

  - The lead partner shall be authorized to upload the bid in e-procurement and to incur liabilities and receive instructions for and on behalf of the partners of JV, and the entire execution of the Contract shall be done with the Lead Partner on behalf of the Joint bvVenture as per the power conferred to him in the Power of Attorney. The authorization shall be evidenced by submitting a power Attorney by legally authorized signatory of all partners as per proforma provided in the bidding documents.

  - The performance security shall be submitted by both the Joint Venture partners in the ratio of 75:25(Lead Partner : Associate Partner)

  - In case of any breach of the contract, both partners will be held fully responsible for the fulfilment of the contract.  In case of any default in execution of the contract, it is the sole discretion of APTRANSCO to transfer the order on any one of the partner to complete the work individually in such case the default partner will not be considered for participating in future tenders individually / JV or to terminate the total contract and get the balance works executed through alternate agency at the cost and risk of both the partners of the Joint Venture duly   en-cashing the Performance Security and any other securities and withholding pending payments if any in the present contract or in the other contracts of the JV partners individually or jointly. In such cases, both the JV partners are liable for blacklisting. It is mandatory for both the partners to attend the review meetings, failure of which will be viewed seriously.

  - The Joint Venture partners shall be profit making Companies / Firms.

  - The lead partner of the joint venture shall upload the following documents pertains to both the JV Partners.  (a)Authority of the partner/company to enter into joint venture business in memorandum of association  (b) A certified copy of the board resolution according permission to entering into the joint venture and to take up the notified work. (c) A certified copy of the board resolution according permission for affixing the company seal on the joint venture deed.

  - APTRANSCO shall in no way be responsible or connected or liable or suffer for the disputes arise between the Joint venture partners.

  - While calculating the bid capacities at the time of evaluation, the existing works with JV Partners will be taken as 75:25 ratio between lead partner and associated partner (for calculating value of the existing commitment i.e. B in 2AN-B). The lead partner of the joint venture shall upload the Schedule-V(C) pertains to both the JV Partner for calculating the balance commitments.

# 4	GENERAL:

- Bidders shall submit audited financial reports (audited Profit & Loss statement, audited Income & Expenditure statement and audited Balance Sheet) counter signed by Charted Accountant for last Five Financial years preceding the date of bid submission.

- Sub-Contractors’ experience may be consideredif it is officially recognized by Order Placing authority of the State Power Utility / Government organizations / PSU only.

## Responsibility for correctness of the information submitted in the bid lies with bidder. If any information furnished in the bid is proved to be false at a later date, the bid will not only be rejected but the bidder will be BLACKLISTED.

## 4.1   	PERFORMANCE BASED EXPERIENCE:

In case of any bidders who are already having one or more works awarded to them by APTRANSCO which are under execution at the time of bidding and who fails to execute the works already awarded as per the stipulated time schedule of completion, bids of such bidders will not be considered.

## 4.2   	AWARDING CONTRACT FOR MORE THAN ONE WORK

In case of contractors quoting more than one work / tender at similar time and becomes lowest in more than one work, the aggregate requirement of turnover will be examined  at the time of awarding based on the works already awarded / to be awarded / under consideration by APTRANSCO.

    - BID VALIDITY:

90 days from the Bid submission closing date.  Bids having validity less than 90 days are liable for rejection at the discretion of Transmission Corporation of Andhra Pradesh Limited.

    - BID SECURITY

The bidder has to upload the scanned copy of bid security for the amounts as indicated in the ‘Notice Inviting Bids’. In the absence of indicating the same in Bid notice, the bidder has to furnish the amount specified in the NIT as bid security. The bid security shall be in the form of a Demand Draft or a Bank Guarantee or Insurance Surety Bond.

The amount towards bid security will not be accepted by cheque, cash or money order.  It shall be paid by way of Crossed Demand Draft on any approved Bank as per the list enclosed, drawn in favourof  the Superintending Engineer, O&M Circle, APTRANSCO, Tirupati.

In case the bid security is paid by way of a Bank Guarantee, the BG shall be issued by any approved Bank as per the list enclosed, and the validity of the BG shall cover a period of 60 days over and above the period of bid validity. The BG shall be executed on Rs.100/- non-judicial stamp paper in favour of the Superintending Engineer/O&M Circle/APTRANSCO/ Tirupati.  Insurance Surety Bonds issued by Insurance companies as per IRDAI guidelines will also be accepted. In case of extension of bid validity by the bidder at the request of APTRANSCO, the validity of the bid security Bank Guarantee /Insurance surety Bond shall be suitable extended along with confirmation of Bid Validity.  The Bank Guarantee shall be issued by the Bank and the Insurance Surety Bonds shall be issued by an Insurance Company (As per IRDAI Guide lines) on behalf of the bidder or either of the Joint Venture partners only.

BIDS ON E-PROCUREMENT PLATFORM, WHICH DO NOT CONTAIN THE SCANNED COPY OF BID SECURITY, WILL BE REJECTED AND THE BIDDER WILL BE BLACKLISTED WITHOUT ANY CONSIDERATION WHATSOEVER. Bids with insufficient value or validity of bid security will be rejected without consideration whatsoever. The APTRANSCO will not be responsible for any omissions in this regard on the part of the bidders, which result in the rejection of the bids and the bidders will be blacklisted by the APTRANSCO.

The Bid security of the successful Bidder on his request can also be adjusted as part of Performance Security and the balance security deposit shall be paid at the time of concluding Agreement by the successful Bidder provided the bidder extends the validity of the bid security bank guarantee suitably.

The Bid Security will be forfeited in the following cases.

- When the successful bidder does not accept the order after issue of preliminary acceptance   letter or the Letter of Intent.

- When the successful bidder fails to furnish the Performance Security within 15 days from the date of issue of preliminary acceptance letter or Letter of Intent.

- When a bidder withdraws his bid or alters the prices after schedule bid submission closing date and before the expiry of the bid validity period or does not accept the correction of errors made in his bid or Offers post Bid rebates, revisions or deviations in quoted prices and / or conditions or any such offers.

7.        DISCREPANCIES: In case of difference in e-procurement lump sum amount and the amount arrived from the schedules the following will be adopted:

- Where there is a discrepancy between the total lump sum rate quoted in the  e-procurement platform web page and in the schedules uploaded, the total lump sum rate quoted in the e-procurement platform will govern for deciding L1.

- If any discrepancies arises after applying the tender percentage on the schedules:-

      - If the amount arrived is less than the e-procurement lump sum amount, then the lesser amount shall be taken for award of contract.

      - If the amount arrived is more than the e-procurement lump sum amount, thee-procurement lump sum amount shall be taken for award of contract. The unit rates shall be adjusted to match the e-procurement lump sum amount.

8.0 	EVALUATION OF BIDS:

8.1 	The bids will be opened on-line by bid inviting authority or assignee at the time and date specified in the Bid documents.

Physical and Financial capacities of all the bidders will be evaluated based on the documentary evidence furnished along with the bid.  Evaluation of Technical/ Commercial and Price bids will be made based on the available documentary evidence submitted along with the bid. However, the Tender opening Authority may seek clarification with the bidder as per clause 8.2, if required. If any information furnished in the bid is proved to be false later, the bid will not only be rejected but the bidder will be black listed.

If any significant discrepancies are observed in the Technical/Price schedules of any bid, due to which the bidder becomes lowest and withdraws the bid, the bid will be liable for rejection and forfeiture of Bid security and also liable for black listing of the bidder.

They are liable for rejection for any of the deviations mentioned below.

- No Bid Security or Insufficient Value or Validity of Bid Security

- Insufficient Validity of the Bid.

- Non-uploading of the required documents, schedules, forms, supporting documents for Qualifying Requirement.  Insufficient or illegible supporting documents, schedules, forms.

- Deviation from the Delivery schedule of the Specification.

- Deviation from the Payment terms of the Specification.

- Deviation from the General terms and conditions

- Deviation from the Technical Specification.

- Non-Compliance with the Qualifying Requirements.

- Record of Poor Performance in the previous / on-going works. Record of poor progress i.e. abandoning the work, not properly completing the contract, inordinate delays etc.

- Record of Black listing in any other Power Utilities / Government Department.

- Record of financial failures if any.

- History of litigation with Government/APTRANSCO during the last 5 years.

- History of criminal record in which the Bidder is involved.

- Non-uploading of the Price schedules. Insufficient or illegible Price Schedules. Change of Quantities / Description of the work / materials items in the Price Schedule uploaded by APTRANSCO.

- Furnishing of false / fabricated particulars in the forms, statements and annexure, submitted in proof of the qualification requirements.

- Not turned up for entering into agreement, when called upon with in the time specified in the letter of acceptance.

- Any other deviations of clause mentioned in this specification.

The price bids of qualified bidders in the pre-qualification analysis will only be considered.

While being equal or compatible in other aspects preference will be given to those bidders who have good experience / proven performance, past experience is superior in terms of quality and timely completion in similar works.

It is the sole discretion of APTRANSCO regarding finalization of the bids. Mere quoting and becoming of L1 (Lowest quoted) bidder shall not automatically entitle any rights for any bidder for award of contract. The past performance of the contractor and performance of the contractor in the ongoing works shall be taken in to account while finalizing the bids. The APTRANSCO reserves its right to reject any or all the bids and not to accept the lowest or any other without assigning reasons. The APTRANSCO reserves its rights to cancel the tender at any stage without assigning the reasons.

8.2 	Clarification on the Bid:“The Tender opening authority may call upon any Tenderer for clarification on the statements, documentary proof relating to the bid. The request for clarification and response thereto shall be in writing and it shall be only on the qualification information uploaded online by the Tenderer. The clarification called for from the Tenderers shall be furnished within the stipulated time, which shall not be more than a week.

The Tenderer if so desirous, shall agree in writing to furnish the clarification called for within the stipulated time and, for disqualification and rejection of his Tender in the event of failure to do so.”

No Clarification shall be asked/entertained regarding qualification requirements (Supply, Performance and Financial Turnover). Tenders shall be evaluated with uploaded documents in the e-procurement website only.

- NOTIFICATION OF AWARD AND ACKNOWLEDGING:

- The Bidder who’s Bid has been accepted will be notified, the award of the work by Bid inviting authority prior to expiration of the Bid validity period by registered letter / Fax. This letter (hereinafter and in the Conditions of Contract called “Letter of Intent”) will indicate the sum that the employer will pay the Contractor in consideration of the execution, completion, and maintenance of the Works by the Contractor as prescribed by the Contract (hereinafter and in the Contract called the “Contract Amount”).

- Upon intimation being given by the Bid inviting authority, of acceptance of his Bid, the Bidder shall make payment of the balance Security Deposit and additional security deposit wherever needed by way of Demand Draft or unconditional and irrevocable Bank Guarantee obtained from approved Bank with required validity period and sign an agreement in the form prescribed by the department for the due fulfillment of the contract. Failure to attend enter into the required agreement or failure to submit the Performance and Additional Securities as intimated in Detailed contract Order shall entail forfeiture of the Bid Security deposited. The written agreement to be entered into between the Contractor and the Superintending Engineer shall be the foundation of the rights and obligations of both the parties and the contract shall not be deemed to be complete until the agreement has first been signed by the contractor and then by the proper officer authorized to enter into contract on behalf of the Transmission Corporation of Andhra Pradesh Limited.

- The successful bidder shall submit the performance Bank Guarantee within 15 days of the issuance of the detailed contract.

- The successful Bidder has to sign and return a copy of the detailed contract within a period of 7 days from the date of issue of contract award letter.

- The kick off meeting shall be held by Zonal Chief Engineers within 15 days from the issue of the Letter of Intent for all works. The targets are to be fixed in the Kick-off meeting which shall be signed by the concerned Superintending Engineer and the contractor which shall become a part of the agreement. The targets fixed in the Kick-off meeting are final and shall be taken for imposing penalties. A copy of the targets fixed and minutes of the Kick-off meeting shall be sent to headquarter immediately. The format of the Kick-off meeting is appended to this specification.

- On the date of Kick-off meeting the Executive Engineer shall finalize and confirm to the contractor regarding specific type of Towers to be used and the drawings applicable and all the quantities of materials / equipment in writing and shall make a copy to the Headquarters.

- Any technical clarifications shall be done by the concerned Superintending Engineer. The Superintending Engineer shall arrange to hand over the approved layout, Final Ground Level for substation and approved profile for line on the day of kickoff meeting.

- The contractor or his representative shall invariably attend the meetings whenever called. The representative of the contractor who attends the kick-off meetings and review meetings shall be qualified and shall be authorized by the contractor with the details of qualification and responsibility and designation of the authorized person.

- The concerned Superintending Engineer/O&M Circle/ Tirupati shall be the agreement authority and the contractor shall attend the office of the concerned Superintending Engineerwithin 15 days of the detailed order to enter in to an agreement. The Superintending Engineer shall enter an agreement with the contractor duly verifying the following.

    - The PAN card, GSTIN Registration,Labor license, valid A-grade electrical license to execute EHT works in A.P.

    - Valid Performance Bank Guarantee.

    - Valid Project insurance covering 100% of project cost.

    - Authorization / power of attorney of the contractor representative to sign the agreement.

The following documents shall also be made part of the agreement.

- The copy of the letter of intent.

- The copy of the Purchase order.

- The copy of the volume-1 of the specification.

    - Copy of the Performance Bank Guarantee and its approval.

    - Authorization / power of attorney of the contractor representative to sign the agreement.

    - Copies of the statutory registrations of the contractor etc.,

- SERVICE CONDITIONS:

The Substation / Transmission Line will be operating under the following tropical conditions.

- Humidity				-	60 to 80%

- Max.isoceraunic level			-	40 thunder storm days per year.

- Max.temperature in shade		-	45 Deg.C

- Min.temperature in shade 		-	10 Deg.C

- Max.temperature in sun		-	55 Deg.C

- Altitude above sea level		-	550 meters to 1000 meters.

Due consideration will be given to any special devices or attachments, put forward by the bidder which are calculated to enhance the general utility and the safe and efficient operation of the line.

- SUB CONTRACTOR AND SUB ORDERS

11.1	The successful Bidder shall carry out all the works mentioned in the schedules by their company only.

Subcontracting may be permitted post award of contact based on following terms and conditions.Item of work proposed for Sub Contracting and sub-contractor to be got approved by order placing authority before or after placing of the contract order. However, the responsibility lies with the main contractor fails to perform, the work may be executed through the sub-contractor, but the payment shall be made through main contractor.

i.	The agency should posseslabor license for civil works.

ii.	The agency should be of A grade Electrical license for electrical involved works,

iii.	The agency should have minimum experience in similar work nature and shall be 			certified by the concerned Executive Engineer of APTRANSCO /power utilities

regardto electrical works and from any Government Organization regard to civil

works.

- The agency shall conclude an undertaking/agreement with the main contractor for complying all terms and conditions of the works to be performed for their quality and time schedule.-

11.2	Direct Payments to the sub-contractor and sub-vendors by APTRANSCO with the consent of Main contractor:

Direct payments to the approved sub-contractor and sub-vendors will be paid from APTRANSCO, based on request of the main contractor on whom the orders were placed, for the material and works portion on furnishing willingness by the main contractor and by obtaining an under taking from the main contractor.  However the payment made to the sub-contractor/sub-vendor by APTRANSCO shall be deemed to be, the payment made to the main contractor only, against the contract.  Any implication in this regard is to the account of main contractor on whom the order is placed by APTRANSCO.

- POWER TO VARY OR OMIT WORK:

No alterations, amendments, omissions or variations of the works under the contract shall be made by the contractor except as directed in writing by the APTRANSCO, but the APTRANSCO shall have full powers to instruct the contractor by notice in writing to make such variations without prejudice to the contract. The contractor shall carry out such variations and be bound by the same conditions as far as applicable as though the said variations occurred in the contract documents. If any suggested variations would, in the opinion of the contractor, if carried out, prevent him from fulfilling any of his obligations under the contract, he shall notify the APTRANSCO thereof in writing and the APTRANSCO shall decide forthwith whether or not, the same shall be carried out and if the APTRANSCO confirms its instructions, contractor’s obligations shall be modified to such an extent as may be mutually agreed.  Any agreed difference in cost occasioned by any such variation shall be added to or deducted from the contract price as the case may be.

APTRANSCO reserves the right to allot any surplus materials from APTRANSCO stores to this project (even though the scope of specification covers supply of materials) duly omitting that part of materials from Schedule-A. In such cases transportation shall be carried out by the Contractor and transporting charges shall be paid as per clause (3) Section-II Financial ‘Supplemental Quantities / Items’. The bidders shall supply only the balance materials required after allotment of such materials.

- EXECUTION OF WORKS RELATING TO POWER LINE CROSSINGS AND RAILWAY CROSSINGS:

Works such as erection of towers underneath an existing power line and paving out of conductors and earth wire and stringing the power line crossing span or a railway crossing span, will have to be done only after receipt of approval from the concerned officer, which, sometimes, may not match with the program of the contractor. In such cases, the contractor shall execute such works as and when approvals are received. His rates for tower erection and stringing shall take into consideration, such contingencies also.

- ELECTRICITY RULES:

All works shall be carried out in accordance with the relevant clauses of the Indian Electricity Act and Rules unless modified by this specification.In case of variation between the two, the latter shall be binding on the contractor.

Unless otherwise specified, works shall be carried out in accordance with the Indian Electricity Act, Electricity Rules or any revisions thereof, which may be issued during the currency of the contract and the requirements of any other Regulations and Acts in India to which the APTRANSCO may be subjected to.

All railway tracks, communication lines or other important track crossings and routing the line through Air field region shall conform to the relevant rules and procedures as may be laid down by Railway, Communications, Aviation or other concerned authorities from time to time.

Aviation signals will have to be provided at the top of the transmission line towers in the vicinity of civil and military aerodromes or airfield regions, if any. Similar provisions will have to be made on the special river crossing towers. The rates for tower erection shall include such works also.

  - REGULATION OF LOCAL AUTHORITIES AND STATUTES

  - The CONTRACTOR shall ensure compliance with all statutes laws ofIndia, rules and regulations of the Central or State Government or any other authority such as the Workmen's Compensation Act 1923, Payment of Wages Act, Minimum Wages Act 1948, Employees State Insurance Act, Employees Provident Fund Act, etc., and any statutory modifications thereof in connection with employees engaged by him in the work.  The contractor's offer shall be presumed to include financial liabilities arising from the above and the purchaser shall not be liable for any extra costs on this account.

  - The CONTRACTOR shall conform to the provisions of Indian Boiler Regulation, Factory Laws, Indian Electricity Act and rules made there under, and any other acts of legislature relating to the work and to the regulations and bye-laws of any authority and of any matter, lighting and other companies and/or authorities with whose systems the plant/structure proposed to be connected and shall, before making variations from the drawings or specifications may be necessitated by so conforming, give to PURCHASER/ENGINEER written notice,  specifying the  variations  proposed to be made and the reason for making it and apply for instructions thereof.

  - The CONTRACTOR shall arrange to give all notices required by the said Acts, Regulations or Bye-laws to be given to any Authority or to any Public Officer and pay all fees that may be properly chargeable in respect of the 'Works' and lodge the receipts with the PURCHASER/ ENGINEER, unless otherwise specified. Obtaining all permits and licenses required thereupon shall be the responsibility of the CONTRACTOR.

  - All registration and statutory inspection fees, if any, in respect of his work pursuant to this 'Contract' shall be to the account of the CONTRACTOR.  However, any registration, statutory inspection fees lawfully payable under the provisions of the Indian Boiler Regulations and any other statutory laws and its amendments from time to time during erection in respect of the plant and equipment ultimately to be owned by the PURCHASER shall be to the account of the PURCHASER.  Should any such inspection or registration need to be re-arranged due to the fault of the CONTRACTOR or his VENDOR, the additional fees for such inspection and/or registration shall be borne by the CONTRACTOR.

- CO-ORDINATION WITH STATUTORY BODIES AND OTHER AGENCIES

The Contractor is fully responsible for carrying out all co-ordination and liaison work to be required with Electrical inspectors, Factory inspector and other statutory bodies for implementation of the work.

The application on behalf of the Purchaser for submission to the electrical inspector and other statutory bodies along with copies of drawings complete in all respects shall be done by the Contractor and approval/ certificates taken well ahead of time so that the actual commissioning of equipment/ materials is not delayed for want of inspection and approval by the inspector and statutory bodies. The actual inspection work by the electrical inspector shall be arranged by the Contractor. However, any fees paid to electrical inspector/ statutory bodies, etc., in this regard shall be borne by the Purchaser.  Any modification on the installation suggested by the electrical inspector or any other statutory authority shall also be carried out by the contractor at no extra cost by the Purchaser.

- CO-OPERATION WITH OTHER CONTRACTORS

The Contractor shall co-operate with all other contractors or tradesmen of the Purchaser, who may be performing other Works on behalf of the Purchaser and the workmen who may be employed by the Purchaser and doing work in the vicinity of the Works under the contract.  The Contractors shall also so arrange to perform his work as to minimize, to the maximum extent possible, interference with the work of other contractors and their workmen.  Any injury or damage that may be sustained by the employees of the other contractors and the Purchaser, due to the Contractor's work shall promptly be made good at his own expense.

The Purchaser / Engineer shall determine the resolution of any difference or conflict that may arise between the Contractor and other contractors or between the Contractor and the workmen of the Purchaser in regard to their work.  If the Works of the Contractor is delayed because of any acts or omissions of another contractor, the Contractor shall have no claim against the Purchaser on that account other than an extension of time for completing his Works.  However extension of time will be considered after examination of its merits and at the discretion of the purchaser.

- CONTRACTOR'S COOPERATION WITH THE PURCHASER

In cases where the performance of the erection work by the CONTRACTOR affects the operation of the system facilities of the PURCHASER/ENGINEER, such erection work of the CONTRACTOR shall be scheduled to be performed only in the manner stipulated to be performed by the PURCHASER/ ENGINEER and the same shall be acceptable at all times to the PURCHASER/ ENGINEER. It will be the responsibility of the CONTRACTOR to provide all necessary temporary instrumentation, measuring devices and all other material/ arrangements required during the work for proper functioning of the equipment.

The CONTRACTOR at all times shall work in coordination with the PURCHASER/Engineer’s staff and offer them all reasonable facilities to become familiar with the erection, operation and maintenance of the equipment. In respect of observations of local rules, administrative orders, working hours etc., the CONTRACTOR and his personnel shall cooperate with the PURCHASER/ENGINEER.

- EMPLOYMENT OF TECHNICAL STAFF FOR SUPERVISION, SKILLED AND UNSKILLED LABOUR:

The contractor shall provide experienced, technically qualified supervising Engineers for the supervision. The Chief Supervising Engineer of the contractor or his agent shall have full power as the representatives of the contractor who can negotiate at site in regard to execution of the contract. The minimum qualification of site Engineer is a degree in Engineering. The contractor must make his own arrangements for recruiting skilled, semi- skilled and un-skilled labour in sufficient numbers. The contractor shall engage only competent skilled workers. The Executive Engineer/ In-charge of the work will have the right to remove any skilled worker employed by the contractor, if found not suitable.

The contractor shall employ at least the following Technical Staff indicated against each work.

| Work | Technical Personnel to be employed by the Contractor |
| --- | --- |
| 220 KV or 132 kV SS or SwStn | 1 B.Tech/BE Electrical+ 1B.Tech/BE Civil+1 Diploma Electrical |
| 220 KV or 132 kV Line /bays | 1 Diploma Electrical +1 Diploma Civil |

The contractor shall have one of the above technical staff as a project manager with five year’s experience in executing such contract of comparable nature.

In case of failure of the contractor to employ technical staff during execution as above, recovery shall be made from his bills at Rs. 10,000/- per month for each work, besides other penal action.

The contractor shall make his own arrangements for engagement of all labour, local or otherwise, their transportation, housing, feeding and payment thereof, in accordance with labour law, unless the contract otherwise provides.  No idle labour payment will be made to the contractor.

19.1	FACILITIES TO WORKERS

Minimum facilities for workers as per Factory Act and other relevant acts shall be provided for by the CONTRACTOR. If the CONTRACTOR fails to do so, the same shall be provided by the Purchaser and deduct the same from the CONTRACTOR'S bills.

First-Aid

The Contractor shall provide necessary first-aid facilities for all his employees, representatives and workmen working at the Site.  Enough number of Contractor's-personnel shall be trained in administering first-aid.

Cleanliness

The CONTRACTOR shall be responsible for keeping the entire area allotted to him clean and free from rubbish, debris etc., during the period of 'Contract'. The CONTRACTOR shall employ enough number of special personnel to thoroughly clean his work area. All such rubbish and scrap material shall be stacked or disposed in a place to be identified by the PURCHASER/ENGINEER.  Materials and stores shall be so arranged as to permit easy cleaning of the area.   Similarly, the offices of the CONTRACTOR shall be kept clean and neat to the entire satisfaction of the PURCHASER/ ENGINEER. Proper sanitary arrangements shall be provided by the CONTRACTOR, in the work areas and office of the CONTRACTOR and residential colonies.  If contractor fails to comply with these requirements inspite of instructions from the Purchaser, the areas will be cleaned by the purchaser at contractor's cost and the cost of the same will be deducted from the contractor's due amounts.

- LIABILITY FOR ACCIDENTS TO PERSONS:

  - The contractor shall indemnify the purchaser against all actions, suits, claims, demands, cost or expenses arising in connection with injuries suffered by persons employed by him, on the works whether under the General Law or under the Workers Compensation Act.1923 or any other statute in force at the date of the contract dealing with question of liability of employer for injuries suffered by employees and have taken steps properly to insure against any claims there under. Contractor should take insurance cover to all his workmen for injuries, disablement and death. All compensation against workmen’s compensation act should be settled by the Contractor.

  - On the occurrence of an accident which results in the death of workmen employed by the contractor which is due to the contract work and of so serious as to be likely to result in the death of any such workman, the contractor shall within 24 hours of happening of such accident intimate in writing to the Engineer and such other officers required by the provision of the workmen’s compensation act, the fact of such accident. The contractor shall indemnify the APTRANSCO against all loss or damage sustained by the APTRANSCO resulting directly or indirectly from his failure to give information in the manner aforesaid including the penalties or fines if any payable by the APTRANSCO as a consequence of the APTRANSCO’s failure to give notice under the workmen’s compensation act or otherwise conform to the provisions of the said act in regard to such accident.

  - In the event of any claim being made, or action brought against the purchaser involving the contractor and arising out of the matters referred to and in respect of which the contractor is liable under the clause of the contract shall be immediately notified thereof, and he shall conduct all negotiations for the settlement of the same or any litigation that may arise there from.

  - In the event of an accident in respect of which compensation may become payable under workmen’s compensation act VIII of 1923 and any subsequent amendment thereof, whether by the contractor or by the APTRANSCO, as principle it shall be lawful for the Engineer to retain out of moneys due and payable to the contractor such sum or such sums of money as may be in the opinion of the said Engineer be sufficient to meet such liability. The opinion of the Engineer shall be final in regard to all matters arising under this clause and will not be subject to any claim.

  - Liability for damage or loss to third party including inspection officers due to act of the contractor or by his representatives connected with the execution of this contract shall be fully borne by the contractor. The contractor shall maintain such detailed records to furnish information regarding engagement and discharge of all workmen employed under this contract as to be adequate for the timely and full settlement of claims under the workmen’s compensation act. All cases of accidents or injuries shall be reported to the Engineer with full details required for the settlement under the workmen’s compensation act.

  - The contractor should report about all accidents within 24 hours to the Engineer of the APTRANSCO in the preliminary accident form. He should furnish other particulars such as medical certificates, wage particulars, fitness certificates, and proof of having paid the compensation as per the rules in vogue in the due course without delay.

- LIABILITY FOR DAMAGE TO WORKS AND PLANTS:

  - The contractor during the progress of the work shall take every reasonable, proper, timely and useful precaution against accident or injury to the workmen from any cause and shall remain answerable and liable for all the accidents or injuries thereto which until the same, or be occasioned by the acts of omissions of the contractor or his workmen or his representatives and all losses and damages to the works as aforesaid, shall be made in the most complete and substantial manner by and at the sole cost of the contractor and to the reasonable satisfaction of the Engineer. Should such loss or damage happen to units of works or plant or materials falling outside the scope of this contract and due to the lapses of the contractor, these shall be replaced or compensated for by the contractor to the satisfaction of the Engineer.

  - In the case of loss or damage to any portion of the work occasioned by the causes, the same shall if required by the purchaser, be made good by the contractor in like manner but at the cost of the purchaser at a price to be agreed between the contractor and the purchaser and the purchaser shall pay to the contractor the contract value of the portion of the work so lost or damaged or any balance of such contract value remaining unpaid as the case may be.

  - Until the work shall be or deemed to be taken over as aforesaid, the contractor shall also be liable for and shall indemnify the purchaser in respect of all damage or injury to any person or to any property of the purchaser or other occasioned by the act of the contractor or his workmen or his representatives or by defective design, work or materials but not due to cause beyond his reasonable control.

  - Provided that the contractor shall not be eligible under the contract for any loss of profit or loss of contracts or any claims made against the purchaser not already provided for in the contract, not for any damage or injury caused by or arising from the acts of the purchaser or of others (save as to damage by fire, as hereinafter provided) due to the circumstances over which the contractor has not control nor shall his total liability for loss, damage or injury exceed the total value of the contract.

- APPROVAL OF SUB-VENDORS FOR EQUIPMENT / MATERIALS AND APPROVAL OF GENERAL TECHNICAL PARTICULARS, DRAWINGS, BOMS ETC.

The materials / equipment required for this project shall be invariably purchased from the manufacturers listed in the specification who have already been supplied similar materials to APTRANSCO and have proven performance.

The bidder shall furnish in Schedule-E, the list of manufacturers to a maximum of three companies per each material which were considered while quoting the prices and from whom they are going to purchase the materials if order is placed.

All the equipment / material offered in the Bid shall be fully type tested as per the relevant standards. The type tests should have been conducted not earlier than 5 years from the date of bid opening. If the type tests conducted are earlier than 5 years the bidder shall arrange to conduct type tests at his own cost.

The bidder shall submit all the type test certificates and General Technical Particulars of equipment / material along with the bid.

APTRANSCO has approved the General Technical Particulars and drawings of all equipment/materials of certain manufacturers and are available on APTRANSCO website www.aptransco.gov.in. However the successful bidder shall obtain the approval of General Technical Particulars and drawings of the equipment/materials which are not available in the APTRANSCO website from Chief Engineer/Zone/Kadapa.

With in 15 days of receipt of the Letter of Intent, the Contractor shall finalize the sub-vendors as per the list they have submitted in the bid and submit the finalized vendor list to APTRANSCO for approval along with the GTPs, Drawings, BOMs etc., Any delay in submitting the above list will lead to delay in execution of the project and responsibility lies with the Contractor.

- QUALITY ASSURANCE PLAN:

The Quality Assurance Plan of APTRANSCO is appended to this specification. The bidders are advised to go through the same before quoting the bids. The successful bidder will have to adhere to the Quality Assurance Plan during execution of works.

Bidder shall maintain the quality standards as per specification and shall attend the remarks of APTRANSCO Quality Control wing on top most priority without any reminders from APTRANSCO.

Setting up of Quality Control Laboratory at Site:

- Appropriate grade of concrete and cement content for R.C.C. items may be scrupulously followed as envisaged in IS 456-2000 considering appropriate exposure conciliations.

- Using of M30 grade shall be mandatory for R.C.C. members of all structures located in coastal areas.

- A quality control laboratory shall be setup by the contractor at the construction site for all major works in which the value of the civil works costing more than Rs. 2.00 Crore excluding tax component. List of testing equipment to be kept in the field laboratory is listed below.

| Sl.No. | Description of testing Apparatus/Equipment |
| --- | --- |
| 1. | Core Cutter Apparatus. |
| 2. | Standard Cone Penetration Test Equipment. |
| 3. | Proctor Density test Apparatus. |
| 4. | Compression Testing Machine. |
| 5. | Concrete Test Hammer. |
| 6. | Slump Cone Test Apparatus. |
| 7. | Vicat Needle Apparatus. |
| 8. | Sieve Analysis Apparatus for fine and coarse aggregates. |
| 9. | Screw guage, Vernier calipers. |
| 10. | Auto level, Theodalite, Chains and Ranging rods. |

Note:   In addition to the above field tests, the contractor has to conduct necessary lab tests as requested by the Engineer-in-charge/QC wing at Govt. Labs or at any reputed Govt./Private Engineering College testing labs.

- QUALITY CONTROL & INSPECTIONS

Standard: The goods supplied under this contract shall conform to the standards mentioned in the Technical Specifications and when no applicable standard is mentioned, the standard specified by the Institution of Central/State Government or internationally recognized Institutions shall be applicable and such standards shall be of latest version issued by the concerned institution.

Inspections and Tests:

- The purchaser or his representative shall have access to the Contractor’s or Manufacturer’s work at any time during working hours for the purpose of inspecting and testing the materials during manufacturing of the materials / equipment and may select test samples from the materials going into plant and equipment.

- The inspections and tests may be conducted in the premises of the manufacturer/supplier, at the point of delivery and/or at the final destination stores i.e. at the site. Where tests are conducted in the premises of Manufacturer / supplier, all reasonable facilities and assistance including access to drawings and production data shall be furnished at no extra charge to the Purchaser.

- Should any inspected or tested materials fail to conform to specifications, the inspection officer may reject them and the Manufacturer / supplier shall either replace the rejected materials or make all alterations necessary to meet specification requirements free of cost to the Purchaser.

- The Purchaser’s right to inspect, test and where necessary, reject the materials/equipment after their arrival at the site, shall in no way be limited or waived by reason of the materials/equipment having been previously inspected, tested and passed by the Purchaser or his representative prior to the dispatch.

- After satisfactory completion of testing as per procedures/standards, and if the material passes through the tests, the inspecting officer will issue dispatch clearance immediately at manufacturer’s premises. The contractor may dispatch the same material to the site immediately and however, a copy of the clearance certificate cum minutes of meeting of testing shall be submitted to Order placing authority.

- The cost of making any test shall be borne by the contractor, if such test is clearly intended by or provided for in the contract.

Cost of tests not provided for: APTRANSCO may decide to conduct certain other tests not covered in this specification on the materials supplied by the bidder by an independent person or agency at any place other than the site of the place of manufacture of the materials. The cost of such tests shall still to be borne by the contractor.  If the tests show that the workmanship or quality of materials are not in accordance with the provisions of the contract the same may be replaced with new one conforming to specification at Contractor’s cost.

Quality of Materials and Workmanship: All materials and workmanship shall be of the respective kinds described in the contract and in accordance with the Engineer’s instructions and shall be subjected to change from time to time to such tests as the Engineer may direct at the place of manufacture or fabrication or on the site or at all or any such places. The contractor shall provide such assistance, instruments, machines, labour and materials that are normally required for examining, measuring and testing any work and the quality, weight or quantity of any materials used and shall supply samples of materials before incorporation in the works, for testing as may be selected and required by Engineer.

Cost of Samples: The contractor at his own cost shall supply all samples, if the supply thereof is clearly intended by or provided for in the contract.

Uncovering and Making Openings: The APTRANSCO reserves the right to uncover and examine any part of the works if it is found to be not according to specification. The contractor shall uncover any part of the works or make openings as the Engineer may from time to time direct and shall reinstate and make good such part or parts to the satisfaction of the Engineer.

Inspection of operation: The Engineer and any person authorized by him shall at all times have access to the works and to all workshops and places where work is being prepared or from where materials are being obtained for the works and the contractor shall afford every facility and every assistance in or in obtaining the right to such access.

Removal of improper work and materials:

  - The APTRANSCO representative shall, during the progress of works, have power to order in writing from time to time the removal from the site within one week of receipt of notice, of any materials which in their opinion are not in accordance with the contract.

  - In case of default on the part of the Contractor in carrying out such an order, the APTRANSCO shall be entitled to employ and pay other persons to carry out the same and all expenses consequent therein or incidental thereto shall be recoverable from the contractor by APTRANSCO from any money due to or which may become due to the contractor.

- Inspection of MS/GI Materials:

The Contractor / fabricator shall invariably use the steel angles manufactured by SAIL, VSP, TISCO and ISCO only or any other APTRANSCO approved re-roller for the fabrication of Line and Substation structures. The contractor shall offer inspection after fabrication of material duly enclosing the readiness letter of the fabricator. The cost of inspection, 3rd party laboratory charges and any other testing charges and samples collection expenses are to the account of contractor and shall include in the cost of materials while quoting.

  - INSPECTION DURING ERECTION:

The provisions of the clauses entitled in the specification for other sections Inspection, Testing and Inspection Certificates shall also be applicable to the erection portion of the Works. The PURCHASER/ENGINEER shall have the right to re-inspect any equipment though previously inspected and approved by him, at the CONTRACTOR's works, before and after the same are erected at Site. If by the above inspection, the PURCHASER/ENGINEER rejects any equipment, the CONTRACTOR shall make good for such rejections either by replacement or modifications/repairs as may be necessary to the satisfaction of the PURCHASER/ENGINEER. Such replacements will also include the replacements or re-execution of those works of other CONTRACTORS and/or agencies, which might have got damaged or affected by the replacements or re-work done by the CONTRACTOR's work.

ACCESS TO SITE AND WORKS ON SITE: Suitable access to and possession of the 'Site' shall be afforded to the CONTRACTOR by the PURCHASER in reasonable time.

The work so far as it is carried out on the Purchaser's premises, shall be carried out at such time as the Purchaser may approve.

In the execution of the Works, no persons other than the Contractor or his duly appointed representative, Sub-contractor and workmen, shall be allowed to do work on the Site except by the special permission, in writing of the Engineer or his representative.

Access to the 'Site' at all times shall be accorded to the PURCHASER/ENGINEER and other authorized officials and statutory Public Authorities. Nevertheless, the CONTRACTOR shall not object to the execution of the work by other Contractors or tradesmen whose names shall have been previously communicated in writing to the CONTRACTOR by the PURCHASER/ ENGINEER and afford them every facility for the execution of their several functions simultaneously with his own.

- TIME CONTROL

Program: Time is the essence of the contract. The contractor shall organize his resources and perform his works so as to complete the contract in the stipulated completion period.

The contractor shall execute the project as per completion period given in Schedule D.  The timing of the tasks / activities given in the bar chart shall be followed for timely completion of the contract.

During the execution of the contract, if the Engineer opines that proper progress is not maintained, suitable changes shall be made in the balance program of works to ensure proper progress.

Progress of Work:

If it is found that the progress of work is not commensurate with the program of completion, APTRANSCO will be entitled to terminate the contract in part or full, giving 15 days notice and get the balance works / supplies completed through other agencies at the contractor's cost and risk. This right of APTRANSCO is in addition to levying of “Penalty” for delayed works.

The contractor shall furnish a monthly statement for the quantity of material supplied, quantity consumed and balance quantity held with him to the to the Executive Engineer/O&M concerned and SE/O&M/TIRUPATI, with a copy marked to Chief Engineer/ Zone/Kadapa.

- MANAGEMENT /CO-ORDINATION MEETINGS

Contractor shall attend the monthly review meetings held by concerned Superintending Engineer/O&M to review the work progress and record reasons for delay and any other bottlenecks based on the weekly dairy of the work done jointly recorded by Assistant Engineer  or Assistant Executive Engineer, and the Contractor .

Early Warning: The contractor has to intimate the APTRANSCO at the earliest opportunity of specific likely future events or circumstances, which may adversely affect the Project Implementation Schedule. The contractor shall cooperate with the officers of APTRANSCO in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced.

- SITE STORES:

The contractor shall establish temporary stores at his cost at the sub-station site for storing material/equipment such as cement, steel, panels etc. This store should be dismantled and site cleared after the completion of the work.

- CONTRACTOR'S SITE OFFICE:

The CONTRACTOR shall establish a Site Office at the 'Site' and keep posted an authorized representative for the purpose of the 'Contract'. Any written order or instruction of the PURCHASER/ENGINEER or his duly authorized representative shall be communicated to the authorized representative of the CONTRACTOR at the Site Office and the same shall be deemed to have been communicated to the CONTRACTOR at his legal address. A complete set of specifications, drawings and a copy of the contract agreement shall be kept in the site office at all times.

- The attested copies of the following shall be invariable kept by the Contractor at the site office and Sub-Station site / Line Site locations and shall have access to the Field Engineers and Inspecting officers.

- Agreement copy along with price schedules.

- Volume-1, Volume-2 and volume-3 of the Specification.

- Approved copies of Guaranteed Technical particulars of materials / equipment, BOMs, approved drawings for all structures, foundations, equipment and materials.

- Applicable Technical Standards like IS and ISS which are mentioned in the Volume-2 of the specification.

- In cases where ‘New works’ are taken up as ‘supplemental items’ under the ‘Original Agreement’ all the above documents related to the extent of these new works also shall be made  available at Site / locations.

- CLEARING UP THE SITE:

During construction, the contractor shall keep the work site and storage area used by him free from accumulation of waste materials or rubbish and before completing the works the contractor shall, at his own cost, remove or dispose off in a manner satisfactory to the engineer in charge.  All temporary structures waste and debris shall be cleaned, all holes in the ground shall be filled in and the land restored to its original state as far as is practicable and the entire premises should be in a neat and tidy condition as directed by the Engineer.  Any damage done to the permanent or temporary work of the Department by the contractor shall be made good at contractor's expenses.

- CHANGE ORDERS:

The Purchaser may at any time by a written order given to the Contractor, make changes within   general scope of the contract in any one or more of the following:

- Drawings, designs or specifications for material/equipment.

- Method of packing,

- The services to be provided by the contractor.

If any such change causes an increase or decrease in the cost of, or the time required for the material or works, an adequate adjustment shall be made to the contract price or delivery schedule or both and the contract shall be accordingly amended.

- WATER & POWER:   The successful bidder has to make use of the water and power supply available if any at Substation site. Transport of water from the available source to the Sub-station site will be the bidder’s responsibility. The contractor has to use power driven equipment at his own cost for pumping water.  In case water is not available at site the bidder has to make his own arrangements and any extra claim on account of this will not be entertained. Temporary Power supply if required for construction purpose will be arranged by APTRANSCO at one point in the substation site from DISCOM. Further cabling up to the contractor’s office/works is in the contractor’s scope only.

The following are the responsibility of the contractor:

- The power consumption charges including deposits if any for temporary supply will have to be borne by the contractor.

- To settle all the bills raised by DISCOM regarding the consumption charges and to obtain & submit “No Due Certificate” from DISCOM on completion/closing of works.

- If any mal-practice/theft of energy takes place during the execution of contract by the contractor, it is the responsibility of the contractor to settle such cases by DISCOM before completion of substation works.

The estimated cost of 11 kV or 33 kV line if any for getting temporary supply shall be borne by APTRANSCO.

- OPERATION AND MAINTENANCE MANUALS:

Contractor shall supply 10 copies of operation and Maintenance manuals and approved drawings along with the equipment. If the contractor does not supply the operation and Maintenance manuals and approved drawings as stated above the equipment bills will be kept on hold.

10 copies of Contract Agreements with specification, QAP, all the approved drawings of Materials, GTPs, BOMs, Layout plans etc., shall be supplied by the Contractor to distribute to field TLC and TL & SS wings and to keep the spare records at Head Quarters.  The Contractor shall prepare the final tower schedule and shall supply in 10 copies. The cost of the above shall be borne by the Contractor and shall provide as instructed by the concerned Executive Engineer.

- SAFETY PLANS

# GENERAL SAFETY RULES FORMED FOR FOUNDATIONS, TOWER ERECTION AND STRINGING:

- Steel/ Aluminums /Wooden ladders of 3.5 meters length shall be used for movement of    labour in excavation, stub setting and concreting works. Keep cement out of the eyes.

- All polypropylene ropes and slings, shackles proposed to be used shall be tested and              inspected thoroughly before use.

- Walkie talkie sets & Cell Phones shall be used for effective communication.

- Binoculars shall be used for closer view

- Red and Green flags shall be used for illiterate communication.

- Pilot wires and joints shall be tested and thoroughly inspected before use

- Ropes and guy wires shall be tested and thoroughly inspected before use

- Ensure travelers in frictionless and good condition.

- Load rating of stringing, pulling lines, conductor grips, load bearing hardware and

accessories, rigging and hoists shall not be exceeded.

- Traveler grounds should be installed at the fist and last tower between tensioner and puller, when stringing in proximity to energized lines. Traveler ground at a maximum distance not exceeding 3 KM. Personnel shall never be in series with a ground lead. Traveler grounds shall have a suitable grounding stub located in an accessible position to enable placing and removing the ground clamps with hot sticks when necessary.

- The conductor reel stands shall have breaking device to prevent over running and backlash as the conductor is pulled out.

- The location of the puller, tensioner and intermediate anchor sites shall be selected such that the structures are not over loaded.

- Slack shall be removed from all anchor lines prior to loading to minimize the possibility of equipment movement or impact loads to the anchors.

- All equipment, conductors, anchors and structures within the work area shall be bonded together and connected to the ground source.

- A running ground shall be installed between the reel stand and tensioner for conductor, or puller for pulling line, and the first tower.

- When clipping is being done, care must be exercised to ascertain that the conductor are grounded prior to clipping, placing a local ground upon the conductor at the location of work.

- Care must be exercised to ensure that concentrated load of the men, car and equipment dose not increase the sag appreciably to cause a hazard from obstructions over which the car will pass while installing spacers in bundle conductors.

- If two conductors are to be spliced, the conductors shall be bonded and grounded before being spliced.

- To cross over of energized lines, the line clear permit system shall be followed without any ambiguity to de-energize the lines. The de-energized lines shall be earthed effectively. Men and material clearance on line shall be ensured before returning permit.

## GENERAL SITE SAFETY RULES & REGULATIONS

- All personals engaged for this job shall wear Safety Helmet & safety shoes.

- Appropriate Hand Gloves shall be used for Materials handling, Welding, Grinding, Gas cutting, Chemical Handling & Electrical work.

- Suitable goggles must be ensured for the personnel deployed for Welding, Gas Cutting Chipping etc Grinders shall use face shield.

- The personnel engaged in the noise zone such as Compressor Operator, Pneumatic Vibrators & Breakers, DG Operator etc. shall be equipped with suitable ear protection.

- All personal working over 2.0-meter height shall wear full body safety harness with double lanyard and scaffold hook, before climbing. Further he will have to anchor the safety harness to a fixed structure before starting the work at a height, Fall Arrest Devices will be used in conjunction with safety harness, wherever the requirement arises.

- Smoking is prohibited in all restricted area except in authorized smoking areas/ shelters.

- Horseplay is prohibited at workplace. Running at the site is prohibited, except in case of emergency.

- Material shall not be thrown from the height. It should be lowered from height.

- Other than the electricians, no one is allowed to carry out electrical connections, repairs on electrical equipment or other jobs related thereto.

- Inserting of bare wires for tapping the power from electrical sockets is completely prohibited.

- Electrical supply to portable equipments should be through Earth leakage circuit breaker (ELCB) of 30 milliamps sensitivity.

- All major /minor accidents and near misses to be reported to Site in charge / Site Safety Engineer to enable the management to take necessary steps to avoid the recurrence.

- All tools and tackles shall be inspected before use. Defects to be reported immediately. No lifting tackle to be used unless it is certified by a competent person/ Safety Engineer.

- Workers should possess induction tester. Whenever a shut down is taken this device should be used to ensure no current is on the conductor.

- Move carefully when walking or climbing.

- Keep the working area as neat as possible.

- Remove hazards as soon as they are noticed.

## ENERGIZED ELECTRICAL WORKS, BASIC REQUIREMENTS ARE:

- Face shields/ Voltage rated gloves/ Voltage rated rubber floor matting Shepherd’s Hook/ Warning/ Safety signs/ barricades.

- Pay close attention to what is being done.

- Disconnect power tools before adjusting them.

- Keep power tool guards in place.

- Avoid interrupting another person who is using a power tool.

  - STORES

      - A layout demarcating areas for stacking, storing and disposing the materials is made.

      - The materials are stacked with passage to reach them. The aisle is marked. Materials should not protrude beyond the marked area posing tripping hazard.

- Name bards shall be displayed to mention the place for every item.

- The racks installed must be supported well to prevent from falling.

- To reach the rack top, person should not climb on the rack shelf, ladder should be used.

- Vertical stacking of materials should not exceed the prescribed norms, posing falling hazard because of imbalance.

- Adequate lighting is provided.

- Flammable, materials like Dissolved acetylene, paints etc. are stored under well- ventilated shed. Electrical connection in these locations should be proper and maintained well such that they do not cause short circuit. Smoking, carrying matchbox or any other fire causing materials is prohibited in these areas.

- Sufficient fire extinguishers are kept at conspicuous places and the path to reach them shall not be blocked anytime.

- Toxic materials are labeled and kept at secured place where only authorized persons shall handle.

- Nail pullers shall be used whenever possible to remove nails from boxes and crates. Metal strapping should be cut with proper safety tool.

- Barrels and drums shall preferably be placed on one end. If placed on their side, these shall be provided with racks or blocked so these cannot roll.

- Oils, greases and paints shall not be openly stored at any time.

- The scrap pile and junk materials shall be kept as orderly as conditions will permit. Extreme care shall be used in handling scrap material to prevent personal injury.

- All T&P issued to the site to be ensured in safe working conditions by a competent person and damaged T&P to be identified and place at a marked place.

- First aid box shall be available at work site.

  - TRANSPORTATION OF MATERIALS

- Only identified crew does the loading and unloading of the materials.

- The gang leader and the crew should be aware of the weight of the materials they are to

handle.

- Proper and reliable tackles like slings, D- shackles etc. shall be used for material handling.

- Lashing to be done after the materials loaded on the trailer.

- Red flag is tide on structures extending beyond the trailer body. At night reflectors to be

fixed.

- Structures extending beyond the cabin height are prohibited from transporting.

- The drive should be aware of the path to the terminal he is to transport the material and

ensure on blockaded are there.

- The gang leader should know the specific spot for unloading the materials.

- Two tag lines shall be tide to the end of the structures while handling by crane.

- All structural steel shall be placed on wooden sleepers.

- Stable and sufficient wooden sleepers to be ensured by the Foreman /gang   leader.

- Workmen should not travel along with the loaded material.

- It is better to plan material shifting in sequence in such a manner that one gang is engaged for   loading and another gang should be made available for unloading. This will reduce the traveling of workmen on transport vehicles.

- The supplier/Manufacturer shall provide such packing for the material/equipment as is required to prevent their damage or deterioration during transit to their final destination as indicated in the Technical specification for material/equipment. The packing shall be sufficient to withstand, without limitation, rough handling during transit and exposure to extreme temperatures, humidity etc. during transit and open storage.

  - SAFETY SIGNS

- Safety warning signs shall be placed to provide adequate warning of hazards. Sign shall be removed or covered when the hazards no longer exist.

- Warning signs shall indicate the cautions to be observed regarding the hazards concerned and the necessary information and, also, actions of employees required to initiate.

- It is recommended that safety signs on the Project conform with the current national colour codes.

- Signs shall be in English & Local language where located near public highways and facilities.

- Sign required to be seen at night shall be illuminated. Kerosene and open flame pots shall not be used for illumination.

  - BILL OF MATERIALS:

Wherever the drawings and designs are provided by APTRANSCO, the suitability of these designs and drawings shall be verified by the bidder for design requirements as per standards, site and soil conditions based on the soil investigation and environmental conditions prevailing for that particular project before submitting BOMs for approval. Substitutions if any of steel sections of the tower parts of higher size due to non-availability or otherwise, shall be to the contractors account. The supplier shall raise the invoices as per the approved BOMs.

- 35.PHOTOGRAPHS AND PROGRESS REPORT

Contractor shall furnish three (3) prints to the PURCHASER/ENGINEER of progress photographs of the work done at 'Site'. Photographs shall be taken when and where indicated by the PURCHASER/ENGINEER or his representative.  Photographs shall be adequate in size and number to indicate various stages of erection.  Each photograph shall contain the date, the name of the CONTRACTOR and the title of the photograph. Normally photographs may be taken once every 15 days and for all special events.

The above photographs shall accompany the fortnight/ monthly progress report detailing out the progress achieved on all erection activities as compared to the Schedules. The report shall also indicate the reasons for the variance between the scheduled and actual progress and the action proposed for corrective measures wherever necessary.  The contractor shall furnish progress reports as and when requested by the PURCHASER/ ENGINEER.

Photographs shall be taken by the contractor for each tower location of EHT lines in the following stages of

- After excavation is over in normal soils.

- Before and after blasting in Hard rock soils.

- During dewatering.

- During concreting.

- Shoring & strutting.

For Substations:

At all important stages like leveling, foundations, laying of slab etc.

Note: The photographs should be clear and hard copy or soft copy (2 Nos) shall be submitted to the Engineer   in charge immediately.

- 36.MEASUREMENT OF WORK AND PROGRESS PAYMENTS

The PURCHASER/ENGINEER may, from time to time, intimate the CONTRACTOR that he requires the works to be measured and the CONTRACTOR shall attend or send a qualified agent to assist the PURCHASER/ENGINEER or his representative in taking such measurements and calculations and to furnish all particulars as may be required by him. Joint measurement certificate must be signed immediately on completion of foundation for each location to avoid delay for arranging payment.

Where the erection of equipment, vessels and structural steel is involved, the basis of such measurements and progress evaluation shall be weights specified in the bidding documents or invoices or drawings as decided by the PURCHASER/ ENGINEER.

Should the CONTRACTOR not attend or neglect or omit to send such agents, then, the measurement taken by the PURCHASER/ENGINEER or approved by him shall be taken to be the correct measurements of the work.  The CONTRACTOR or his agent may, at the time of measurement, take such notes of measurements as he may require.

When measurements are affected by conditions already established, the CONTRACTOR shall take field measurements notwithstanding scale or dimensions shown on the drawings.

The measurements so taken and certified correct by the PURCHASER/ENGINEER shall be the basis for the progress payment to the CONTRACTOR. Where the breakup of 'Contract on unit basis price' is difficult to arrive at, the PURCHASER/ENGINEER and the CONTRACTOR shall work out at the commencement of the 'Contract', the weightages or the cost break-ups to arrive at a mutually agreeable basis for computation of the progress estimates.

To the value so arrived at on the basis of the CONTRACTOR's monthly progress evaluated, shall be added the amounts earned by the CONTRACTOR under supplemental contracts and orders, if any, till date of progress estimate.  From the total thus computed, all previous payments plus any amounts due to the PURCHASER in accordance with the terms of this contract shall be deducted. The remainder shall be paid by the PURCHASER to the CONTRACTOR under interim Certificates from the ENGINEER.

In case of work is nearly suspended, or in case only unimportant progress is being made, or in case it is apparent that the CONTRACTOR is about to forfeit his 'Contract' or that the money yet due to him shall not complete his 'Contract', the PURCHASER may at his discretion withhold any payment which may be due to the CONTRACTOR.

The PURCHASER may withhold part or whole of any payment for erection claimed by the CONTRACTOR, which in opinion of the PURCHASER, is necessary to protect himself from loss on account of:

- Defective work not remedied or guarantees not met

- Claims filed against the CONTRACTOR

- Failure by the CONTRACTOR to make due payment for materials supplied or labour employed by him.

- Damage to other Contractor's, PURCHASER’s or OTHERS' property.

- Failure to meet the mutually agreed schedules for completion of the contract.

When the grounds for withholding payments are removed, payments of the amount due to the CONTRACTOR shall be made by the PURCHASER without delay.

The CONTRACTOR shall not demand nor be entitled to receive payment for the work or portion thereof, except in the manner set forth in this 'Contract' and only after the PURCHASER/ ENGINEER shall have given a certificate for such payment.

- PROTECTION OF WORK:

The CONTRACTOR shall have total responsibility for protecting his 'Works' till it is finally accepted by the PURCHASER/ ENGINEER. No claim will be entertained by the PURCHASER/ ENGINEER for any damage or loss to the CONTRACTOR's works and the CONTRACTOR shall be responsible for the complete restoration of the damaged 'Works' to its original condition to comply with the specifications and drawings.  If any such damage occur to the CONTRACTOR's Works because of other party not under his claim directly with the party concerned the same shall be dealt by the contractor alone.  During construction of the project, the PURCHASER will continue to operate the plant and equipment already put in service. The CONTRACTOR shall protect all such plant, structures, piping, conduits, equipment and facilities against damage during its operations.

- FIRE PROTECTION

The Work procedures that are to be used during the erection shall be those, which minimize fire hazards to the extent practicable.  Combustible materials, combustible waste and rubbish shall be collected and removed from the 'Site'. Fuels, oils and volatile or inflammable materials shall be stored away from the construction and equipment and materials, storage areas, in safe containers. Untreated canvas paper, plastic or other inflammable flexible materials shall not at all be used at 'Site' for any other purposes unless otherwise specified.  If any such materials are received with the equipment at the 'Site', the same shall be removed and replaced with acceptable material before moving into the construction area or storage.

Similarly, corrugated paper fabricated cartons, etc., will not be permitted in the construction area either for storage or for handling of materials. All such materials used shall be of waterproof and flame resistant type. All the other materials such as working drawings, plans, etc., which are combustible but are essential for the 'Works' to be executed shall be protected against fire resulting from welding sparks, cutting flames and other similar fire sources.

All the CONTRACTOR's supervisory personnel and sufficient number of workers shall be trained for fire fighting and shall be assigned specific fire protection duties.  Adequate number of such trained personnel must be available at the 'Site' during the entire period of the 'Contract'.

The CONTRACTOR shall provide and maintain fire protection equipment, adequate in design and numbers for the warehouses, office, temporary structures etc.  Access to such fire protection equipment shall be easy and kept open at all times. The compliance of the above requirements under fire protection shall in no way relieve the CONTRACTOR of any of his responsibilities and liabilities due to fire accidents occurring either to his materials and equipment or to those of others working in the area.

- SECURITY (WATCH & WARD)

The CONTRACTOR shall have total responsibility for all equipment and materials in his custody stored, loose, semi-assembled and/or erected by him at 'Site'. The CONTRACTOR shall make suitable security arrangements including employment of security personnel to ensure the protection of all   materials, equipment and 'Works' from theft, fire, pilferage and any other damage and loss.

40.TESTING AND COMMISSIONING

The MRT wing of APTRANSCO shall supervise and assists the Contractor and his sub-vendors in testing & commissioning of Equipment.  However the 'Testing and Commissioning' of the equipment erected by the CONTRACTOR shall be the responsibility of the CONTRACTOR. The CONTRACTOR shall provide in addition, test instruments, calibrating devices, etc. which are not available with MRT wing for successful and speedy completion of testing and commissioning. The labour required for the successful performance of these inspection tests shall have to be arranged by the Contractor. If it is anticipated that the above tests may prolong for a long time, the CONTRACTOR's workmen required for the above inspection tests shall always be present at 'Site' during such inspection tests.  All the expenditure for the above arrangements will be to the contractor’s account only.

41.INDEMNITY BOND  FOR ALL MATERIALS:

For all materials supplied by the Contractor, the Contractor shall take delivery of materials after executing an indemnity bond in favour of the Purchaser against loss, damage and any risks involved, for the full value of the materials.  This indemnity bond shall be valid till the scheduled date of testing, commissioning and handing over of the line to the Purchaser.

42.ACCOUNTING OF SURPLUS MATERIALS/ SETTLEMENT OF MATERIAL ACCOUNT:

42.a	On completion of works, all the surplus material which has been already billed by contractor to Transco but not used by contractor in the project, shall be handed over designated APTRANSCO stores at the cost of the contractor within 2 months of commissioning of the project. However, if the material is not handed over within such time limit or in the opinion of designate officer of APTRANSCO who is in-charge of the works, such material is not in fit condition for use, such material shall be retained by the contractor and recovery shall be made from the contractor at the rate as per the PO terms and conditions.

42.b	In exceptional cases, in order to expedite work progress, whenever APTRANSCO issues material from its stores on returnable basis to the contractor, the contractor shall return such material within 30 days from the date of issue of such material along with interest on the value of such material at the rate of 2% per month or part thereof. However, if contractor fails to return material within 30 days of issue of such material, the material shall be deemed to have been sold to contractor on the date of its issue to contractor at a price which shall be 150% of the procurement cost and such cost shall be recovered from contractor along with interest at 2% per month or part thereof from the date of issue of material till amount is recovered.

- COMPLETION OF BALANCE WORKS AND HANDING OVER :

All the balance works if any shall have to be executed by the contractor within two months of charging of substation / line. If the Contractor fails to complete the balance works with in the above time schedule the works will be executed by the other agencies and will back charge to the contractor. However the completed works shall be handed over to the concerned O&M wing by the executing engineers within 3 months after commissioning.

- FINAL ACCOUNT:

- Not later than one (1) month after handing over of the works complete in all respects i.e., after successful testing and commissioning, the Contractor shall submit a draft statement of ‘final account’ and supporting document to the Engineer/Engineer’s Representative showing in detail the value of the work done in accordance with the contract.

- Within one (1) month after receipt of the Draft Final Account and all information reasonably required for its verification, the Engineer/Engineer’s representative shall determine the value of all matters to which the Contractor is entitled to under the contract. The Engineer/Engineer’s representative shall then issue to the Contractor a statement showing the final amount to which the Contractor is entitled to under the contract.

- The Contractor shall sign the Final Account as an acknowledgement of the full and final value of the work performed under the contract and shall promptly submit a signed copy to the Engineer/Engineer’s representative.

- On receipt of Final Account, the Engineer/Engineer’s representative shall promptly prepare and issue to the Contractor a “Final Payment Certificate” certifying any further amounts due to the Contractor in respect of the contract.

- If the contractor does not finalize the material account within 2 months from the date of completion of works/ handing over of works, the field Executive Engineer will prepare the final bill duly deducting the cost of all the unaccounted / unhanded over material and will issue a notice to the contractor for signing on the bill.  If the contractor do not turn-up within 15 days of that notice, the bill will be processed without signatures of the contractor.The cost of the unaccounted material will be taken as per Clause 42 above.

45.	TAKING OVER:

Upon successful completion of all the commissioning tests to be performed at site on equipment furnished and erected by the Bidder, and on successful commissioning of the project, the Purchaser   shall issue to the Contractor ‘a taking over Certificate’ as a proof of the final acceptance of the project. However such taking over certificate will be issued only after handing over of all the manuals, drawings, tower schedules as per Clause 32 above and after settlement of materials account and final bill.

46. 	 TECHNICAL AUDIT:

i) 	All the completed works shall be technically audited by Quality Assurance wing within two months of the completion / commissioning of the project for the correctness of project in terms of agreements, specifications, detailed project report/technical sanction, deviation in quantities & rates.

- All the remarks which are pointed out by Quality assurance wing in the above technical audit shall invariably attended by the concerned engineers within one month and in case the remarks are pertaining to the execution of work which is in the scope of the agreement, the Contractor has to attend the remarks without insisting of any additional payment. The Quality Assurance plan & check formats for construction of 220KV & 132KV transmission lines & substations are available in Quality Assurance Plan (PDF file)

- Contractor must be held responsible for rectification/completion of works as on date of commissioning and for defects within the warranty period. However all the liabilities of the contractor covered under performance guarantee period shall hold good.

47.	The decision of Chief Engineer/Kadapa Zone /Kadapa to accept any tender and to reject any or all tenders is final:

Not withstanding the Chief Engineer/Kadapa Zone /APTRANSCO/ Kadapa,reserves the right to accept or reject any tender and to annul tendering process and reject any or all tenders at any time prior to the award of contract without thereby incurring any liability to the affected tenderer or tenderers on the grounds of its action.

TABLE OF CLAUSES - SECTION-II :: FINANCIAL

| Clause. No. | Description |
| --- | --- |
|  | Bid Prices |
| 1.2 | Price Variation (PV) clause |
|  | Statutory Variation |
| 2.1 | Payment of taxes, levies, duties, statutes |
| 2.1.5 | GST |
| 2.2 | Taxes &Cess deductible at sources |
| 2.3 | Seignorage charges |
| 2.4 | Insurance |
| 2.5 | Royalties for patents |
|  | Supplemental quantities / items |
| 3.1 | For increased Quantities |
| 3.2 | For Supplemental/New items |
|  | Performance guarantees |
| 4.1 | Performance security |
| 4.2 | Additional security |
| 4.3 | Mobilization Advance Security |
| 4.4 | Security for executing more than 3 works |
|  | Mobilization Advance payment (Optional) |
|  | Terms of payment |
| 6.1 | For works |
| 6.2 | For Supply of Materials/Equipment |
|  | Completion period |
| 8.1 | Penalty for late supplies / completion: |
| 8.2 | Penalties imposed for deficiencies in quality of works |
| 9. | Incentives for early completion of works |
| 10. | Extension of the completion date |
| 11. | Force Majeure Conditions |
| 12. | Delays ordered by the purchaser |
| 13. | Responsibility of the contractor |
| 14. | Claims due to delays beyond contractor’s control |
| 15. | Recovery of money from contractor in certain cases |
| 16. | Way leaves & tree cutting in transmission line corridor |
| ##### 17. | ##### Termination of contract |
| 18. | Arbitration |

SECTION-II: FINANCIAL

1.0 	Bid Prices: The prices quoted shall be Firm except for Cement, Reinforcement steel and Earth Flat (GI &MS) in Schedule B and Transmission Line Tower Parts, Substation Structures, Cables, Isolators and Conductors in schedule –A. The estimates / Schedules are prepared with prices FADS inclusive of packing and forwarding, GST basedHSNC/SACseignorage charges, Labour welfare Cess and other legally permissible duties and levies wherever applicable, handling charges to cover the transport from destination to site / stores, unloading at destination and insurance (transit and storage at site including erection risks), civil,erection,testing and commissioning .

It is the responsibility of the Bidder to verify the correct rates of duties and taxes leviable on the materials and services at the time of bidding.  The proforma credit available to the bidder on the purchases of inputs (raw materials) (IPC) consequent to the introduction of “GST” Scheme may be taken into account while quoting the prices. The Bidder shall indicate the total bid price of the Materials and services under the contract in Schedule-C.

- In case of local supplies, sales tax, local taxes and other levies and duties solely in respect of the transaction between the APTRANSCO and the Contractor under the contract, if any shall not be included in the bid price, but those shall be indicated separately, wherever applicable. These amounts will be payable (along with subsequent variation if any), by the Employer on the supplies made by the Contractor but limited to the tax liability on the transaction between the APTRANSCO and the contractor.

1.1  For Equipment & Materials and for works:

The Bidder has to quote in Schedule-C, the percentage (both in words and figures) Excess/ On Par/ Less over the total estimated contract value given in the Schedule-A + Schedule-B. The detailed contract order will be released duly applying the quoted percentage on Schedule-A + Schedule-B.

The quoted rates i.e. quoted percentage on  Schedule-A + Schedule-B shall remain same irrespective of (i) increase / decrease in quantity (ii) execution of contract beyond the scheduled completion period for whatever reasons (iii)increase in the rates of material or labour or both during execution with and beyond the completion period. However Price variation as per Clause 1.2, Statutory Variation as per Clause 2 and applicable rates for supplemental quantities beyond agreement quantities as per Clause 3, shall be applicable.

- PRICE VARIATION (PV) Clause:

The price variation is applicable for Cement and Reinforcement steel in works schedule and Transmission Line Tower Parts, Substation Structures, Cables, Earth Flat (GI &MS), Isolators, Conductor, Circuit Breakers, CT& PT, CVT, LAs, GSS Earth wire, Control/Power cable and XLPE Cable in materials schedule and the calculation of Price Variation is as below.

- Price Variation Clause for Cement &Reinforcement Steel.

The Price Variation is applicable in respect of the items Cement and Reinforcement steel as per G.O.Ms.No.94, Dt.16.04.2008 and T.O.O(CE-Civil) Ms.No.24, Dt.28.04.2008.

- The price adjustment shall be applicable within contract period or Period extended on grounds of the departmental delays and valid reasons and shall not be applicable to the extensions granted on account of the contractor’s fault as envisaged in G.O.Ms.No.94 of I&CAD Dt:01.07.2003.

- The price adjustment shall be applicable for actual components of works actually carried out during the period of the bill.  The price variation formula is PV = (Final Rate – Basic Rate) * Quantity.

- The price adjustment will be applied for all variations in Base Rate by more than 5% (no ceiling in increase or decrease) (As per T.O.O.Ms.No.5(CMD) dated 10.12.2013) i.e. actual variation will be considered if increase or decrease is more than 5%.

    - Thus if the price excess is 10%, payment will be made only to the extent of 5% (10% - 5%). Further same procedure should be is also followed for Negative price variation.

    - For the time extension due to department fault, both +ve and –ve price variations are applicable

    - For the time extension due to contractors fault, Negative price variation is applicable

- The Basic rate of reinforcement steel and cement as taken in the estimate were furnished in Project Data Sheet.

- The final rate of Cement for the purpose of price variation shall be the rate informed by Govt. of A.P for the month during which to the works are executed and for reinforcement steel the rate is one month prior to which the works are executed.

- Positive price variation amount will be given on differential base rate (i.e. without taxes) with GST prevailing as on date. In case of negative price variation, the differential base rate with taxes already paid will be recovered.

- Price variation clause for Transmission line Tower Parts, Sub-Station Structures and Earth Flat.

The Price adjustment applicable in respect of the items Transmission Line Tower Parts, Substation Structures and Earth Flat is as per T.O.O (CE-Const) MS. No 50 and T.O.O. (CE-Const) Ms. No.87 dt.10-06-2008 and as per T.O.O. (CE-Construction-2) Ms. No.242 dt.08-11-2012 subject to the following conditions.

a)	The price adjustment shall be applicable within original contract period or period extended on grounds of the departmental delays and valid reasons and shall not be applicable to the extension granted on account of the contractor’s fault.

b)	Price adjustment shall be applicable for actual components of items of supply actually carried out.  The price variation formula is PV = (Final Rate – Basic Rate) * Quantity.

c)	The adjustment scheme will be applied where the variation is more than 5%.

i. Thus if the price excess is 10%, payment will be made onlyto the extent of 5% (10% - 5%).Further the same procedure should be also followed for Negate price variation.

    - For the time extension due to department fault,both +ve and –ve price variations are applicable.

    - For the time extension period  due to contractors fault, only -ve price variation is applicable

- The Basic rate of Transmission Line Tower Parts, Substation Structures and Earth Flat as taken in the estimate were furnished in the Project Data Sheet.

- The final rate of Transmission Line Tower Parts, Substation Structures for the purpose of price variation shall be the rate communicated by the Chief Engineer/Concerned for every month as on 2 months prior to the date of check measurement as per Form-13 and for earth flat one month prior to the date of check measurement as per Form-13.

- Positive price variation amount will be given on differential base rate (i.e. without taxes) with GST prevailing as on date. In case of negative price variation, the differential base rate with taxes already paid will be recovered.

- The total price increase per MT of Tower parts, Substation Structures and earth flat/rod(both MS & GI) will be limited to maximum ceiling of 50%. However, there is no ceiling for negative variation.

1.2.3 PRICE VARIATION CLAUSE FOR AAC/AAAC/ACSR CONDUCTORS

The Price variation for conductor is calculated as follows: as per circular Cir. No:103/DIV/Conductor/05 May 15, 2012

P= Po + WA (AL - ALO) + WF (FE- FEo)

Note- For AAC/AAAC Conductor WF (FE- FEo)=0

Wherein,

P = Ex-works price payable in Rs. per km as adjusted in accordance with the price variation

clause

Po = Ex-works price quoted/confirmed in Rs. per km.

WA = Weight of Aluminium in AAC/AAAC/ACSR Conductor in MT per Km. as per the type of conductor (Refer as per above circular giving this factor for various types of conductors)

ALo = Price of EC Grade Aluminium Ingot/Rod (as per contract) exclusive of excise duty in Rs./MT for AAC/AAAC/ACSR Conductor

Or Price of Aluminium alloy Rod in exclusive of excise duty Rs./MT for AAAC Conductor

This price is applicable prevailing as on 30 days prior to the date of tender opening.

WF= Weight of Steel Content in ACSR Conductor in MT per Km. as per the type of conductor Refer as per above circular -Giving this factor for various types of conductors

Feo= Price (exclusive of excise duty) of High Tensile Galvanized Steel Wire in Rs./MT of appropriate size This price is applicable prevailing as on 30 days prior to the date of tender opening.

AL = Price of EC Grade Aluminium Ingot/Rod (as per contract) exclusive of excise duty in Rs./MT for AAC/ACSR Conductor Or Price of Aluminium alloy Rod in exclusive of excise duty Rs./MT for AAAC Conductor

This price is applicable prevailing as on 30 days prior to the date of delivery.

FE=Price (exclusive of excise duty) of High Tensile Galvanized Steel Wire in Rs./MT of appropriate size This price is applicable prevailing as on 30 days prior to the date of delivery.

For example, if the date of delivery is 31st December 2008, the applicable raw material prices (AL and FE) would be those prevailing as on the 1st day of December 2008.

The above prices and indices are as published by IEEMA vide circular reference IEEMA(PVC)/Al.Conductor/-- The date of delivery is the date on which the Conductor is notified as being ready for inspection/dispatch (in the absence of such notification, the date of manufacturer's dispatch note is to be considered as the date of delivery) or the contracted delivery date (including any agreed extension thereto), whichever is earlier.

- For ACSR conductor, WA and WF are as follows

| Conductor | Variation in Rs. Per KM of conductor |  |
| --- | --- | --- |
|  | For Aluminium/ EC Grade/ Alloy kg/km | For HTGS wire 3.00 mm to 4.09 mm KS |
| Panther ACSR | 0.586 | 0.388 |
| Zebra ACSR | 1.185 | 0.436 |
| Moose ACSR | 1.465 | 0.539 |

MATERIAL PRICE VARIATION CLAUSE FOR HTLS CONDUCTOR- as per circular IEEMA(PVC)/HTLS Conductor/2024 1st March-2024.

HTLS – ACSS Conductors

P = Po + WAL (AL ‐ ALo) + WFe (Fe – Feo)

Wherein, P      =    Ex‐works price payable in Rs. per km as adjusted in accordance with the price variation clause

Po    = Ex‐works price quoted/confirmed in Rs. per km.

WAL = Weight of Aluminium in HTLS ACSS Conductors in MT per Km

ALo = Price of Daily LME Cash Seller Settlement Price of Aluminium (refer notes)                This price is as applicable 30 days prior to the date of tender opening.

AL =   Price of Daily LME Cash Seller Settlement Price of Aluminium (refer notes)   This price is as applicable 30 days prior to the date of delivery.

For example, if tender date is 31st October 2026, the applicable Aluminium price would be, prevailing as on 1st October 2026.

WFe  = Weight of Steel Content in HTLS ACSS Conductors in MT per Km

FEo  =    Price of High Tensile Galvanized Steel Wire of 1.57 mm in Rs./MT

This price is as applicable for the month, ONE month prior to the date of tender opening.

FE    =    Price of High Tensile Galvanized Steel Wire of 1.57 mm in Rs./MT

This price is as applicable for the month, ONE month prior to the date of delivery.

For ACSS conductor are as follows.

| Conductor | Variation in Rs. Per KM of conductor |  |
| --- | --- | --- |
|  | For Aluminium KAl | For HTGS wire 3.00 mm to 4.09 mm KS |
| Panther ACSS | 0.565 | 0.379 |
| Zebra ACSS | 1.109 | 0.511 |
| Moose ACSS | 1.349 | 0.653 |
| Lynx ACSS | 0.495 | 0.327 |

For example, if date of delivery is 31st December 2026, the applicable Aluminium price would be, prevailing as on 1st December 2026.

The above prices and indices are as published by IEEMA vide circular reference IEEMA(PVC)/ AL Conductor‐LME /mm/yyyy

The date of delivery is the date on which the HTLS Conductor is notified as being ready for inspection.

Notes: 1. All prices of raw materials are exclusive of GST amount.

2. Price of Daily LME Cash SELLER Settlement price of Primary Aluminium in US$ per MT is as published by London Metal Bulletin (LME). Premium for Aluminium Ingot in US$ per MT is added in this Daily LME price and converted in Indian Rs./MT using exchange rate and adding appropriate customs duty

3. The price of High tensile Galvanized Steel Wire (in Rs./MT) for 1.57 mm is the price as quoted by   manufacturer/s

In respective of  above conductors :

- Irrespective of increase in the prices of raw materials, the total Price Increase per KM of the Conductor will be limited to a maximum of 50% over the Ex-works price mentioned in Purchase Order. However there is no ceiling for negative variation.

- The Price Variation amount can be claimed for each batch of supplies made from time to time (out of total quantity) and will be payable after due verification

- If the date of delivery as defined in the P.V. formula is beyond the contracted delivery date the contracted delivery date or the actual delivery date whichever is advantageous to the Purchaser will form the basis for calculation of price variation.

- Notwithstanding the formula applicable for regulating the price variation, if at any time any documentary evidence proof or certificate in regard to the price variation bills is required by the Purchaser, the supplier will have to furnish the same to the Purchaser.

1.2.4 Price Variation formula applicable for XLPE cables.

Price variations XLPE Cables   will be calculated as per the latest IEEMA formulas as and when they are amended.

    - Price variation clause for Control /Power Cables and Isolators:

1.2.5.1	The Price Variation applicable in respect of cables and Isolators is subject to the following conditions:

- Price variation shall be applicable for both upward and downward variation in prices of respective items within the original completion period. Price variations for all cables and isolators have been adjusted with IEEMA.

- The price quoted/accepted shall based on the input cost of raw materials/components and labour cost as on the date of quotation and the same is deemed to be related to prices of raw materials and all India average consumer price index number for industrial workers as specified in the price variation clauses given below in case of any variation in these raw materials prices /indices, the price payable shall be subject to adjustment up or down in accordance with the formulae mentioned under clause 1.2.4.2 below.

- For the purpose of Price adjustment, the date of delivery shall be the date on which the Cable /Isolator is notified as being ready for inspection / dispatch.(In the absence of such notification, the date of manufacturer’s dispatch note shall be considered as the date of delivery) or the contracted delivery date (including any agreed extension thereto) whichever is earlier.

- The price variation amount can be claimed for each batch of supplies made from time to time (out of total quantity) and will be payable after due verification.

- If the date of delivery as defined in the P.V. formula is beyond the contracted delivery date, the contracted delivery date or the actual delivery date whichever is advantageous to the APTRANSCO will form the basis for calculation of price variation.

- The total adjustment for Control cables, LT Aluminium power cable and Isolators shall be subject to a maximum ceiling of (+ 50%) individually of the respective Ex-works prices/bid prices (own manufactured/bought out items as the case may be).However there is no ceiling for negative variation.

- Notwithstanding the formula applicable for regulating the price variation, if at any time any documentary evidence proof or certificate in regard to the price variation bills is required by the APTRANSCO, the supplier will have to furnish the same to the APTRANSCO.

- IEEMA indices have been taken into consideration for arriving the base rates of all   cables and isolators.

Note:All the price variations for Power/Control Cables and Isolators will be calculated as per latest IEEMA Formulas/Circulars as and when they are amended.

1.2.5.2 PRICE VARIATION FORMULA APPLICABLE FOR CABLES

(i)   For Steel Armoured PVC Insulated Copper Control Cables:

P = P0 +CuF(Cu-Cuo)+CCFCu(CC-CCo) + FeF(Fe-Feo)

ii)	For Unarmored PVC Insulated Copper Control Cables:

FeF = 0

P = P0 +CuF(Cu-Cuo)+CCFCu(CC-CCo)

Wherein,

P  =	Price payable as adjusted in accordance with the above formula in Rs per Km

P0=  Price quoted/accepted in Rs. per Km

CuF = Variation factor for Copper applicable depending upon type and size of the cable.

Cuo= 	Price of CC copper rods

This price is as applicable on the 1st working day of the month, ONE month prior to the date of tendering i.e., Bid Submission Closing date.

CCFCu = Variation factor for PVC Compound applicable depending upon type and size               of the  cable.

CCo  =   Price of PVC Compound

This price is as applicable on the 1st working day of the month, ONE month prior to the date of tendering i.e., Bid Submission Closing date.

FeF= Variation factor for Steel for Steel Armoured PVC Insulated Copper Control  Cables applicable depending upon type and size of the  cable.

Feo  =   Price of steel strips/steel wires

This price is as applicable on the 1st working day of the month, ONE month prior to the date of tendering i.e., Bid Submission Closing date.

Cu =    Price of CC copper rods

This price is as applicable on the 1st working day of the month, ONEmonth prior to the date of delivery.

CC  =   Price of PVC Compound

This price is as applicable on the 1st working day of the month, ONE month prior to the date of delivery.

Fe   =   Price of steel strips/steel wires

This price is as applicable on the 1st working day of the month, ONE month prior to the date of delivery.

(*) 	Variation factor for copper conductor (CuF),   PVC compound (CCFCu) for PVC Insulated Control Cables, Steel (FeF) for control cables with copper conductor is tabulated below.

TABLE - I

VARIATION FACTOR FOR COPPER CONDUCTOR (CUF)CONTROL CABLE WITH COPPER CONDUCTOR

| No. of Cores | Nominal Cross Sectional Area ( in Sq mm) = 2.5 Sq mm |
| --- | --- |
| 2 | 0.047 |
| 3 | 0.070 |
| 4 | 0.094 |
| 5 | 0.117 |
| 6 | 0.141 |
| 7 | 0.164 |
| 8 | 0.182 |
| 9 | 0.205 |
| 10 | 0.235 |
| 12 | 0.282 |
| 14 | 0.329 |
| 16 | 0.376 |
| 18 | 0.410 |
| 19 | 0.446 |
| 20 | 0.456 |
| 24 | 0.563 |
| 27 | 0.634 |
| 30 | 0.704 |
| 37 | 0.869 |
| 44 | 1.033 |
| 52 | 1.221 |
| 61 | 1.432 |

TABLE - II

VARIATION FACTOR FOR PVC COMPOUND (CCFCu)PVC INSULATED CONTROL CABLEs WITH COPPER CONDUCTOR

| No. of Cores | Core Size) = 2.5 Sq mm |  |
| --- | --- | --- |
|  | Unarm | Arm |
| 2 | 0.125 | 0.139 |
| 3 | 0.141 | 0.157 |
| 4 | 0.161 | 0.179 |
| 5 | 0.187 | 0.206 |
| 6 | 0.234 | 0.260 |
| 7 | 0.234 | 0.260 |
| 8 | 0.292 | 0.325 |
| 9 | 0.300 | 0.335 |
| 10 | 0.303 | 0.337 |
| 12 | 0.334 | 0.371 |
| 14 | 0.389 | 0.409 |
| 16 | 0.435 | 0.458 |
| 18 | 0.474 | 0.500 |
| 19 | 0.476 | 0.501 |
| 20 | 0.519 | 0.546 |
| 24 | 0.584 | 0.615 |
| 27 | 0.631 | 0.664 |
| 30 | 0.706 | 0.743 |
| 37 | 0.835 | 0.879 |
| 44 | 1.019 | 1.026 |
| 52 | 1.100 | 1.158 |
| 61 | 1.246 | 1.312 |

TABLE – III

VARIATION FACTOR FOR STEEL (FeF)PVC INSULATED CONTROL CABLES WITH COPPER CONDUCTOR

| No. of Cores | Core Size = 2.5 Sq mm | Shape of armour |
| --- | --- | --- |
| 2 | 0.277 | W |
| 3 | 0.289 | W |
| 4 | 0.314 | W |
| 5 | 0.342 | W |
| 6 | 0.379 | W |
| 7 | 0.379 | W |
| 8 | 0.456 | W |
| 9 | 0.275 | F |
| 10 | 0.325 | F |
| 12 | 0.342 | F |
| 14 | 0.360 | F |
| 16 | 0.372 | F |
| 18 | 0.350 | F |
| 19 | 0.397 | F |
| 20 | 0.400 | F |
| 24 | 0.475 | F |
| 27 | 0.478 | F |
| 30 | 0.503 | F |
| 37 | 0.548 | F |
| 44 | 0.601 | F |
| 52 | 0.641 | F |
| 61 | 0.685 | F |

1.2.5.3 For Aluminium conductor PVC Insulated Cables:

P   = 	P0 +AIF (AI-AIo) +CCFAI (CC-CCo) + FeF (Fe – Feo)

Wherein,

P =	Price payable as adjusted in accordance with the above formula in Rs per Km

P0 =    Price quoted/accepted in Rs per Km

AIF= Variation factor for Aluminiumapplicable depending upon type and size of the cable.

AIo= Price of EC grade Aluminium rods (proper Zi rods). This price is as applicable on the 1st working day of the month, ONE month prior to the date of tendering i.e., Bid Submission Closing date.

CCFAI = Variation factor for PVC Compound applicable depending upon type and size of  the cable.

CCo  = Price of PVC Compound.  This price is as applicable on the 1st working day of the month, ONE month prior to the date of tendering i.e., Bid Submission Closing date .

AI = Price of EC grade Aluminium rods (proper Zi rods). This price is as applicable on the 1st working day of the month, ONE month  prior to the date of delivery.

CC  =  Price of PVC Compound. This price is as applicable on the 1st working day of the month, ONE month prior to the date of delivery.

(*)  Variation factor for Aluminum (AIF),   PVC compound (CCFAI) for PVC Insulated Power cables, Steel (FeF) for PVC Insulated Power cables with Aluminum conductor is tabulated below.

TABLE – IV

VARIATION FACTOR FOR ALUMINIUM (AIF)POWER CABLES WITH ALUMINIUMCONDUCTOR

| Nominal Cross Sectional Area( in Sq mm) | 3.5 core |
| --- | --- |
| 25 /16 | 0.262 |
| 35 /16 | 0.345 |
| 50 /25 | 0.478 |
| 70 /35 | 0.687 |
| 95 /50 | 0.949 |
| 120 / 70 | 1.221 |
| 150 /70 | 1.464 |
| 185 /95 | 1.861 |
| 225/120 | 2.287 |
| 240 /120 | 2.421 |
| 300 /150 | 3.033 |
| 400 /185 | 3.873 |

TABLE – V

VARIATION FACTOR FOR PVC COMPOUND (CCFAI) PVC INSULATED 1.1 KV POWER CABLES WITH ALUMINIUM CONDUCTOR

| Nominal Cross Sectional Area ( in Sq mm ) | 3.5 core |  |
| --- | --- | --- |
|  | Unarm | Arm |
| 25 | 0.422 | 0.444 |
| 35 | 0.489 | 0.515 |
| 50 | 0.613 | 0.645 |
| 70 | 0.707 | 0.744 |
| 95 | 0.908 | 0.927 |
| 120 | 1.024 | 1.045 |
| 150 | 1.289 | 1.315 |
| 185 | 1.499 | 1.530 |
| 225 | 1.840 | 1.878 |
| 240 | 1.990 | 2.031 |
| 300 | 2.361 | 2.409 |
| 400 | 2.616 | 2.669 |
| 500 | 3.687 | 3.762 |

(*) FeF = Variation factor for steel

Feo = Price of steel strips/steel wire. This price is as applicable on first working day of the month, one month prior to the date of tendering.

Fe = Price of steel strips/steel wire. This price is applicable on the first working day of the month, prior to the date of delivery.

TABLE – VI

VARIATION FACTOR FOR STEEL (FeF) PVC INSULATED 1.1 KVPOWER CABLES WITH ALUMINIUM CONDUCTOR

| Nominal cross sectional Area ( in Sq mm) | 3.5 core | Shape of armour |
| --- | --- | --- |
| 25 | 0.382 | F |
| 35 | 0.411 | F |
| 50 | 0.469 | F |
| 70 | - | F |
| 95 | 0.616 | F |
| 120 | 0.675 | F |
| 150 | 0.731 | F |
| 185 | 0.820 | F |
| 240 | 0.937 | F |
| 300 | 1.055 | F |
| 400 | 1.172 | F |
| 500 | 1.348 | F |

- STATUTORY VARIATION:

It is the responsibility of bidder to consider the correct rates of duties and taxes leviable on the equipment/material/Work at the time of bidding. After considering the correct rates of duties and taxes only the bidder shall quote the percentage on ECV.

For both Schedule-A and B, any variation up or down in statutory levy or new levies introduced after tendercalling date under this specification will be to the account of APTRANSCO.

In cases where delivery schedule is not adhered to by the contractor and there are upward variation/ revision after the agreed delivered date the contractor will bear the impact of such levies and if there is downward variation / revision the APTRANSCO will be given credit to that effect. For the variations beyond the scheduled completion period the payment of taxes shall be limited to the tax rates applicable within the scheduled completion period.

  - PAYMENT OF TAXES, LEVIES, DUTIES, STATUTES

- Contractor shall be entirely responsible for payment of all taxes, levies, duties, license fees, etc., incurred until delivery of the contracted goods to the purchaser.

- In respect of supply portion, the contractor shall pay all types of fees, levies, taxes, duties etc. required to be paid by any National or State statute, ordinance or other law or any regulation or bye-law of any local or other duly constituted authority in relation to the execution of works and by the rules and regulations of all Public bodies and companies whose property or rights are affected or may be affected in any way of the works. The contractor shall in compliance with the above keep the Purchaser indemnified against all such penalties and liability of every kind for breach of any statute, ordinance or law, regulation or bye-law.

- Nothing in the contract shall relieve the contractor from his responsibility to pay any tax that may be levied by the Government on the turnover / profits made by him in respect of the contract.

- The present rates of taxes and duties which have been considered in the estimate are mentioned in the Project Data Sheet. However it is the responsibility of the bidder to ensure the correct rate and any change of rate of taxes and duties at the time of quoting.

2.1.5	GST:

2.1.5.1e-way bills

For supply of material/ equipment e-way bills are to be provided by the bidder only. APTransco will not provide any way bills for the supplies against this tender unless there is clear instructions in this regard by the concerned authorities.

2.1.5.2 Reverse charge mechanism – Contractor being unregistered

Reverse charge mechanism was not applicable in respect of purchases made from the composition dealer/ registered dealer, incase the service provider is an unregistered dealer,the e-waybill will be issued by the APTRANSCO. The contractor must mention onthe tax invoice if the tax is payable on reverse charge.

  - TAXES & CESS DEDUCTABLE AT SOURCES:  As per provision of taxation act, necessary applicable taxes will be deducted at source at all stages of payment on the bills and same will be remitted to the concerned department as per the rules / acts of the State / Central Government. The present rates of the TDS are mentioned in the Project Data Sheet. However the deductions will be as per the rates prevailing as on the date of billing.

If the contractor availed the interest bearing advance from APTRANSCO, the contractor shall submit the certificate of Tax Deduction at Source (TDS) on interest within 3 months from the end of the quarter in which adjustment of advance has been made, for claiming refund of TDS amount from APTRANSCO.  No claim for refund will be entertained after end of the aforesaid period of 3 months.  Further, while submitting the TDS Certificate the details of Contract No, Project, Region, Quarter etc to which the TDS certificate pertains, shall also be submitted tallying the amount with the TDS Certificate.

No TDS will be made at the time of payment of interest bearing initial advance.

But TDS will be made at the time of adjusting the interest bearing initial advance to the extent adjusted along with TDS on regular payment.

  - SEIGNORAGE CHARGES:

Seignorage charges have to be paid by the bidder to the Assistant Director Mines & Geology Department otherwise it will be deducted from the bills as per rules in vogue.

  - INSURANCE:

The price quoted by the bidder is inclusive of insurance charges for transit, storing and erection risks materials and insurance for labor as per the labor laws in vogue.

All the materials / equipment shall be insured by the contractor for loading, transit, unloading, storage and erection risks. Any insurance premium payable shall be borne by the contractor  and shall cover the following risks also.

a)	Full cover against damage to other people’s property

b)	Coverage against death or injury caused by the contractor’s acts or omissions to:

- Anyone authorized to be on the site.

- Third parties who are on the site.

c)	Full cover against theft and damage to the works and materials during transit, storage and construction, till to the commissioning and handing over of the project in full shape.

It is the entire responsibility of the contractor for the safety of all the materials / equipment and labour till the notified project / work are handed over to APTRANSCO after commissioning. While doing the insurance for the workmen, the Contractors are advised to follow the labourdepartment rules in vogue. Any additional insurance premiums if required during the course of project execution shall be borne by bidder.

All costs on account of insurance liabilities covered under this contract will be on contractor’s account. The Contractor shall provide the purchaser with a copy of all the insurance policies and documents taken over by him in pursuance of the contract. Such copies of documents shall be submitted to the purchaser immediately after such insurance coverage. The Contractor shall also inform the purchaser in writing at least sixty (60) days in advance, regarding expiry, change, any modification, amendments etc., without prior approval of purchaser the Contractor shall not cancel any of the Insurance policies made for the project. It is the Contractor’s responsibility to ensure revalidation or renewal of the insurance policies well in advance.

The bidder shall   a) Initiate and pursue insurance claim till settlement and

b)  Promptly arrange for repair and/or replacement of any damaged items in    full irrespective of settlement of insurance claim by the under writers.

The Goods supplied under this Contract shall be fully insured against loss or damage incidental to manufacture or acquisition, transportation, storage, delivery and erection. The insurance shall be at least for an amount equal to 100% of the cost of the goods from "warehouse to warehouse (final destination)" and storage up to commissioning thereafter on "All Risks" basis including War Risks and Strike Clauses.

The insurance paid by the contractor cannot be claimed by the contractor. The insurance shall be valid up to commissioning of the project and however the same shall be suitably extended until the commissioning of the project.

In addition, the following provisions will apply to the portion of the 'Works' to be done by CONTRACTOR. Comprehensive Insurance of equipment/materials during erection and commissioning, Workmen's Compensation Insurance, Comprehensive Automobile 	Insurance and Comprehensive General Liability Insurance shall be the responsibility of the CONTRACTOR.

The Contractor shall also maintain an insurance policy against all claims which may be made upon Purchaser whether under the Workmen's Compensation Act or any other statue in force during the currency of the contract or at common law in respect of any employee of contractor.  The Contractor shall be responsible for anything which may be excluded from the insurance policies referred to above and also for all other damage to any property or persons out of and incidental to the negligence or defective carrying out of this contract.

  - Third party Compensation:

In particular, the Contractor shall effect and maintain an insurance policy of at least Rs.3.00 lakhs for one person and Rs.5.00 lakhs per accidental for injury or death and at least Rs.5.00 lakhs per accident for third party property damage, to indemnify purchaser against all third party accident/damage claims which may arise in respect of the work or in consequence thereof.

  - Workmen's Compensation Insurance:

This insurance shall protect the CONTRACTOR against all claims applicable under the Workmen's Compensation Act, 1948 (Government of India).  This policy shall also cover the CONTRACTOR against claims for injury, disability, disease or death of his or his SUB-CONTRACTOR's employees, which for any reason are not covered under the Workmen's Compensation Act, 1948.  The liabilities shall not be less than:

Work Men’s compensation	-	As per statutory provision

Employees liability		-	As per statutory provision.

  - Comprehensive Automobile Insurance:

This insurance shall be in such a form to protect the CONTRACTOR against all claims for injuries, disability disease and death to members of public including the PURCHASER's men and damage to the property of others arising from the use of motor vehicles during on or off the 'Site' operations, irrespective of the purchaser-ship of such vehicles.

The liability covered shall be as herein indicated:

Fatal injury		:  Rs.  1,00,000 each person

Rs.  2,00,000 each occurrence

Property damage	:  Rs.  1,00,000 each occurrence

  - Comprehensive General Liability Insurance:

This insurance shall protect the CONTRACTOR against all claims arising from injuries, disabilities, diseases or death of members of public or damage to property of others due to any Act or omission on the part of the CONTRACTOR, his agents, his employees, his representatives and SUB-CONTRACTOR’s from riots, strikes and civil commotion.  This insurance shall also cover all the liabilities of the CONTRACTOR arising out of the clause entitled 'Clause. 33.0’ of GCC Indemnify the Purchaser under 'General Conditions of Contract'.

The above are only illustrative list of insurance covers normally required and it will be the responsibility of the CONTRACTOR to maintain all necessary insurance coverage to the extent both in time and amount to take care of all his liabilities either direct or indirect, in pursuance of the 'Contract'.

It will be the responsibility of the Contractor to lodge, pursue and settle all claims with the Insurance Company in case of any damage, loss, theft, pilferage or fire and the Purchaser shall be kept informed about it.

- ROYALTIES FOR PATENTS:

All royalties for patents or charges for the use of infringement thereof that may be involved in the construction or use of any material shall be included in the bid prices.  The bidder shall protect the APTRANSCO against any and all such claims arising out on account of the use thereof.

  - The bidders are requested to consider all the applicable deductions and taxes & duties while quoting and no additional payment will be made if the bidder did not consider any of the prevailing taxes and duties and deductions at the time of quoting.

3.0 		SUPPLEMENTAL/DEVIATION QUANTITES / ITEMS:

The quantities indicated in the Schedule-A (Materials / Equipment) and Schedule-B (Works) are only provisional and are likely to change during actual execution.  When quantities of any item are likely to exceed beyond 10% over and above the scheduled quantity or any new items / supplemental items arises, the Contractor shall bring the fact to the notice of the Chief Engineer/Zone/Kadapa well in advance and take prior orders for going ahead with the work.  Without approval of this office, the Contractor shall not go ahead with the work wherever there is increase in quantities exceeds beyond 10% over and above the scheduled quantities or any new items / supplemental items arises.

The contractor is bound to execute all Increased / supplemental / new items that are found essential, incidental and inevitable during execution of the contract at the rates to be worked out as below:

  - Increased Quantities:

- For Material / Equipment covered in Schedule-A:The rates accepted for individual items of material / equipment shall hold good even for the increased quantities up to and beyond 25% over and above the agreement quantities.

- For work items covered in Schedule-B:

The rates accepted for individual items shall hold good even for the increased quantities up to and beyond 25% over and above the agreement quantities .

  - For Supplemental / New Items:

- For the items relating to the Schedule-B where the rate can be deduced from the estimate                or APTRANSCO / DISCOMS / common SSR, the rate applicable will be the estimated / SSR rate +/- tender percentage quoted/ accepted by the bidder for Schedule –B. The schedule of rates adopted for supplemental items / new items shall be from the current SSR applicable during the execution period.

- For the items relating to the Schedule-A or Schedule-B where the rates of new items cannot be deduced from the estimate / SSR, the rate payable will be arrived based on the prevailing market rates duly enquiring / collecting quotations and observing the reasonableness of the rates by the Purchaser without tender percentage.

  - The contractor shall plan and procure the materials indicated in the schedule ‘A’ duly verifying with the approved layout and profile, So that the procured quantities match with actual requirement to avoid excess supply of materials. The Executive Engineer shall give the details of the materials such as quantities of type wise towers and extensions and other line materials based on the line approved  profile and  the quantities of type wise structures and other materials based on the approved layout on the date of Kickoff meeting without fail.

  - The Schedule time required to complete the new / supplemental items including the balance work will be indicated in the approval letter issued for new / supplemental items.

- PERFORMANCE GUARANTEES

  - The contractor shall warrant for the satisfactory functioning of the materials / equipment supplied and for the satisfactory operation of the workmanship performed by him, for a minimum period of12 months from the date of commissioning of the works/project.

  - Where the Suppliers/Manufactures provide longer period of warranty, such as 18 months from the date of check measurement, than the period of mentioned above, the Purchaser shall be entitled for such longer warranty.

  - Equipment, sub-assemblies or spares, or parts replaced / repaired under warranty shall have further warrantee of 12 months from the date of replacement / repair.

  - After commissioning and handing over of the project to the APTRANSCO, the contractor shall arrange for thorough patrolling of the line during the first six months of the guarantee period so that the defects if any noticed during that period may be rectified by the contractor free of cost to the APTRANSCO without having to wait for the APTRANSCO to suggest such rectifications.

  - If during the period of guarantee, the Engineer decide and inform in writing to the   contractor that any equipment, part of equipment, material or works is defective, the contractor on receiving details of such defects or deficiencies shall at his own expense, irrespective of reimbursement of insurance company, rectify/replace the defective material or works within seven (7) days of his receiving the notice or within such reasonable time as APTRANSCO may deem proper for making it good.  The decision whether correction of the defects should be through repair or by replacement shall be the sole discretion of the APTRANSCO.

  - In the event of contractor not responding to the intimation of the Engineer as mentioned in above, the Engineer may arrange for a third party to correct the Defects and the extra costs for such .

  - The Engineer is to give the contractor at least seven (7) days notice of this intention to use a third party to correct a Defect. If the contractor does not correct the Defect himself within this notice period, the Engineer may have the Defect corrected by the third party. The cost of the correction will be deducted / collected from the Retention amounts or Performance / additional / Retention securities or amounts / bills pending to the contractor either in this contract or other contracts or any other Securities.

  - PERFORMANCE SECURITY:

The successful bidder to whom the contract is awarded will be required to furnish performance security for a value equal to Five percent (5%) of the value of Schedule –A plus (+) five percent (5%) of the value of the Schedule-B for the proper fulfillment of contract with a validity of 12 months over and above the completion period and with two months claim period.

In case of Joint Venture, Performance Security shall be furnished as 75% by lead partner and 25% by associate partner respectively of the values mentioned above, which would stand surety for collective responsibility in executing the works.

If the successful bidder fails to furnish the performance security as specified above, the contract is liable for cancellation and forfeiture of the bid security.  The performance security shall also be forfeited if the successful bidder fails to fulfill the terms of the contract.

Performance security may be made by Demand Draft on any approved Bank payable at TIRUPATI in favor of the Superintending Engineer/O&M/ TIRUPATI or by way of Bank Guarantee from approved Bank, or Insurance Surety bonds (ISB) issued by Insurance Companies as per IRDAI guide lines in favour of the Superintending Engineer/O&M/ TIRUPATI , in the prescribed proforma.

The performance Bank guarantees furnished by the successful bidder shall be extended suitably as and when required to cover the Warranty period of the materials and services as per clause 4.0 above.

However Additional Performance is not required for the case of face value enhances provided the value of balance work to be done is less than the performance BG furnished. Contractor shall ensure the performance BG submitted should cover the works completed and proposed for claim the same without which the bill will not be processed.

  - ADDITIONAL SECURITY:

If the rate quoted by the bidder less than 10% of the APTRANSCO’s total estimated cost will be considered as abnormally low rate. In the case of abnormally low quoted rates i.e., less than 10% additional security deposit (ASD) to be paid for the less percentage below 10% i.e., if the bidder quotes 20% below the total estimated cost then he has to pay ASD equivalent to 10% of the total estimated cost.

The Additional security may be made by Demand Draft on any scheduled Bank payable at TIRUPATI in favor of the Superintending Engineer/O&M/ TIRUPATI or by way of Bank Guarantee from a Nationalized/ Scheduled Bank as per the list enclosed, in favour of tender inviting authority covering a period of 2 months over and above the completion period.

  - MOBILIZATION ADVANCE SECURITY:

If the bidder is interested to avail interest bearing advance from APTRANSCO, the bidder shall furnish an unconditional & irrevocable Bank Guarantee in favour of APTRANSCO for 110% (one hundred ten percent) of the amount of advance as per the Proforma attached to the Bidding Documents.  The said Bank Guarantee shall be initially valid up to the end of sixty (60) days after the scheduled date for Completion of the project and shall be extended from time to time till sixty (60) days beyond the actual date of Completion of the project, as may be required under the Contract.

The Advance Payment Security shall be allowed to be reduced every one (01) year after First Running Account Bill/Stage payment under the Contract if the validity of the Bank Guarantee is more than one year.  The cumulative amount of reduction at any point of time shall not exceed seventy five percent (75%) of the advance corresponding to cumulative value of the project completed as per a certificate to be issued by the Project Manager.  It should be clearly understood that reduction in the value of advance Bank Guarantee shall not in any way dilute the Contractor’s responsibility and liabilities under the Contract including in respect of the project for which reduction in the value of security is allowed.

  - SECURITY FOR EXECUTING MORE THAN 3 WORKS:

Bidders who are executing three (3) Nos. 400 kV contracts (in case of 400 kV tenders) or three (3) Nos. 220/132 kV contracts (in case of 220/132 kV tenders) in APTRANSCO as on date of tender opening shall submit a Bank Guarantee for 5% of total contract value in addition to the performance Bank Guarantee in case becoming L1.  The bidder shall submit an undertaking in their bid on confirmation of submission of 5% BG, failing which the bid will not be considered.  This 5% BG shall be valid till commissioning of the Sub-station, Bay extensions and Transmission line.

This is in addition to the Performance Security Bank Guarantees to be submitted by the contractor towards supply and erection.

Whenever any of the first three awarded projects commissioned and completed in all respects, the subsequent projects will be reclassified (e.g., the fourth work will be treated as the third work) and the additional security provided for the work that become third or lower in sequence after reclassification will be released.

  - All Bank Guarantees, which are executed in accordance with this specification, shall be on a Stamp paper of value not less than Rs.100/- (Rupees one hundred only).  Bank Guarantee executed on the stamp paper of value less than Rs.100/- will not be accepted. “All banking charge should be to the account of the Contractor”.

  - The Performance and Additional Securities will be forfeited in the following cases.

  - When the successful bidder does not fulfills the obligations under the contract or proven to be false submission of the information either in the bid or the information relating to the contract.

  - When the successful bidder fails to execute the work in accordance with the clauses under this   specification.

  - When the successful bidder executing the work with in-ordinate delays or with poor quality which hampers the prime object of the contract, the securities will be en-cashed and will be adjusted towards such losses incurred by APTRANSCO or towards risk purchase.

  - When the successful bidder pleads his inability to erect the Substation / Line and backs out of his obligations after issue of the preliminary acceptance letter or the letter of intent, the APTRANSCO will forfeit his performance/ additional/ bid securities and also recover the loss, if any, sustained by the APTRANSCO as a consequence of such backing out.  In addition, the company will be blacklisted.

- MOBILIZATION ADVANCE PAYMENT :( OPTIONAL)

5.1	APTRANSCO introduced interest bearing mobilization advance to enable the contractors to commence the works immediately. Note: ** This payment is an optional payment.  The Contractor has the option of taking the interest bearing advance or otherwise.

5.2	Interest rate applicable on advance payment to the Contractor is minimum of 12.5% per annum, on monthly rent basis against the advance, subject to revision of the same upward (depending upon upward revision of the rates on CC limits by State Bank of Hyderabad).  The said interest rate shall remain fixed and shall be applicable till the advance amount is fully repaid.  The interest will be charged considering proportionate adjustment of advance against progressive payment clause mentioned below.  The interest shall be calculated on the daily progressive balances outstanding as on the date of recovery/adjustment.

- For Works:

        - 10% of the amount under the works agreement (SCHEDULE B) exclusive of taxes shall be paid as an interest bearing advance after signing the contract Agreement.

        - This 10% payment as an Interest Bearing Advance (Optional*) will be made within 30 days subject to

          - Establishment of Contractor’s site offices for preparatory to mobilization for Installation establishment,

          - Submission of Performance Bank Guarantee as per the terms & conditions of the Contract Agreement.

          - Detailed HR/ invoice.

          - Submission of an unconditional & irrevocable Bank Guarantee for 110%  of the advance amount as detailed in 4.3

- For supply of Materials / Equipment :

i.) 	10% of the Ex-works price of the materials under the agreement (SCHEDULE A) (equipment/ materials including mandatory spares) shall be paid as an interest bearing advance after signing the contract Agreement.

ii.)	This 10% payment as an Interest Bearing Advance (Optional*) will be made within 30 days subject to

- Detailed approved Pert chart/Bar chart by APTRANSCO.

- Submission of Performance Bank Guarantee as per the terms & conditions of the Contract Agreement.

- Detailed HR/ invoice.

- Submission of an unconditional & irrevocable Bank Guarantee for 110%  of the advance amount as detailed in 4.3

5.3	The said Bank Guarantees shall be initially valid up to the end of sixty (60) days after the scheduled date for Completion of the project and shall be extended from time to time till sixty (60) days beyond the actual date of Completion of the project, as may be required under the Contract.

5.4	Provided further that the Invoice/HR for advance payment along with all supporting documents is to be submitted by the Contractor to the Employer within 3 months from the date of issue of LOI.

5.5	In case the contractor does not submit the requisite documents including applicable Bank Guarantee(s)/Security(i.e.,) within the aforesaid period the advance shall not be payable.

- TERMS OF PAYMENT:

All the bidders who shall accept the following terms of payment are only acceptable. Bids received stipulating terms other than the following terms will be invalidated.

  - For Works:

            - IF MOBILIZATION ADVANCE NOT AVAILED:

- Payments will be made up to 90% of the bills for the items of works completed during a month. For this purpose the contractor shall submit monthly bills to the Executive Engineer regularly to ensure payments in time. The contractor shall give full details of items of works done against each location in support of the bill. Bills submitted without supporting details will not be taken into cognizance.

- Out of the balance 10% amount, 5% payment will be released after completion of all works & upon submission of material account, provided if all the works including testing & commissioning of the project are completed and the same is certified by the purchaser.

- The final 5% payment will be released after completion of the Guarantee period or on submission of a Bank Guarantee for the equivalent amount, valid for the guarantee period plus two months claim period, subject to settlement of material account.

            - IF MOBILIZATION ADVANCE AVAILED:

- Payments for the erection will be made up to 90% on monthly basis duly deducting advance paid with interest at the rates approved in the schedules for the items of work done.  For this purpose the Contractor shall submit monthly bills to the Executive Engineer regularly to ensure payments in time.  The Contractor shall give full details of items of works done against each location in support of the bill.  Bills submitted without supporting details will not be taken into cognizance.

- Out of the balance 10% amount, 5% payment will be released after completion of all works & upon submission of material account, provided if all the works including testing & commissioning of the project are completed and the same is certified by the purchaser.

- The final 5% payment will be released after completion of the Guarantee period or on submission of a Bank Guarantee for the equivalent amount, valid for the guarantee period plus two months claim period, subject to settlement of material account.

            - The date of commissioning/energizing the project will not be considered for reckoning the purchase guarantee period.

            - If the contractor has received any over payments by mistake or if any amounts are due to the APTRANSCO due to any other reason, when it is not possible to recover such amounts under the contract, APTRANSCO reserves the right to collect the same from any other amounts and/or Bank Guarantees of the company due to or with the APTRANSCO.

            - When the supplier does not at any time, fulfill his obligations in replacing/rectifying etc. of the damage/defective materials in part or whole promptly to the satisfaction of the APTRANSCO’S Officers, the APTRANSCO reserves the right not to accept the bills against subsequent dispatches made by the supplier and only the supplier will be responsible for any demurrages, wharfages or damage occurring to consignment so dispatched.

            - The supplier shall invariably submit a guarantee on the bill itself to the effect that if the test certificates, wherever necessary for the supply of materials or Goods are not approved stating that certificates will be furnished in due course, and if they are not accepted or not satisfactory, all payments received for the materials or Goods shall be refunded in full by the supplier/contractor.

  - For supply of Materials / Equipment :

              - IF MOBILIZATION ADVANCE NOT AVAILED:

- 80% payment will be made within 30 days for the material / equipment supplied in complete shape subject to their delivery as per the schedule of work contained in the bar chart and on its receipt at destination stores/site in good condition (i.e. from check measurement date in Form-13). The concerned AEE/TLC will receive the equipment/material in full shape at site and the concerned EE/TLC will do the check measurement and issue the Form-13. The check measurement shall be done within five days from the date of receipt of materials.

- 10% payment will be made after erection of equipment / material.

- Balance 10% payment will be made after commissioning of equipment/material.

              - IF MOBILIZATION ADVANCE AVAILED:

i.) 	80% payment duly deducting advance paid with interest will be made within 30 days for the material/equipment supplied in complete shape on its receipt at destination stores/site in good condition (i.e from check measurement date in Form-13).  The concerned AEE will receive the equipment/ material in full shape at site and the concerned EE will do the check measurement and issue the Form-13.  The check measurement shall be done within five days from the date of receipt of materials along with all relevant documents.  The due date for payment will be reckoned from the date of check measurement mentioned in Form-13.

ii.) 	10% payment will be made after erection of equipment/material.

iii.) 	Balance 10% payment will be made after commissioning of equipment/ material.

6.3	The Contractor shall furnish the following documents to the pay officer in quadruplicate for arranging initial payment in Indian rupees only as per 5.b (i) for the equipment / material supplied.

- Original Copies of the invoices showing Contract No., Goods description, quantity, unit price and total amount.

- Acknowledgement of receipt of material from consignee i.e. Form-13

- Manufacturers / Suppliers Warranty Certificates.

- Proof of payment of Excise duty (Not applicable for bought out items)

- Acknowledgment of Consignee on Delivery Challan in original.

- 6 copies of detailed packing list

- Documentary proof for the freight.

- Copies of Insurance Certificate / policies

- Test certificates approval and Dispatch clearance.  (Not applicable for furniture and general items)

- Certificate certifying that the defects, if any, pointed out during inspection have been rectified.

- The payments against Schedule-A and B are subject to the acceptance of the Performance Security with a validity of 14 months as on the date of Check Measurement for proper fulfillment of performance obligations.

6.4	Payments will be made by cheques / by way of Electronic Fund Transfer / RTGS from APTRANSCO funds. The contractor has to furnish requisite details for establishing RTGS in proforma as per Schedule -X. Once RTGS system is established, the bank account details submitted are final and cannot be changed till completion of the contract. An amount of Rs.50/- will be recovered from the bill amount for each disbursement on LOA raised by unit officers towards RTGS.  For payments, Bank charges are to be borne by the contractor.

- COMPLETION PERIOD:

The overall completion period for this project is as per the Project Data Sheet. For completion period for individual works, refer Schedule-D. Within one week of receipt of intimation from Superintending Engineer/Executive Engineer concerned, the contractor shall take over the approved profiles & tower schedules for the line and substation levels/ site cum Electrical Layout for the Sub-station. Otherwise the date after one week of intimation to the contractor for taking over of approved profiles, tower schedules and substation levels /site cum Electrical Layout shall be the deemed date of handing over of profiles/ substation levels /Electrical layout and will be taken as date of commencement of work. The detailed program for execution of works / supplies is enclosed in the Schedule-D.  The bidder shall execute all the works / supplies as per the program of works.

  - PENALTY FOR LATE SUPPLIES / COMPLETION:

The completion period mentioned in Schedule-D is the essence of   contract. Penalty will be levied as follows for the delay in executing the works or supply of material.

    - Penalties for delays in execution of the works with in completion period:“In case of non-achievement of Targets of the scheduled works by the Contractors when compared with the PERT charts as accepted in the Kickoff meetings, whatever may be the reasons, the APTRANSCO shall levy and collect the penalty @ 1% per month of value of non-achieved targets fixed in the Kickoff meeting. However if the work is completed within the total scheduled completion period the penalty recovered shall be released”.

    - Penalties after overall completion period:

“In case of delay in erection of the works or supply of material / equipment beyond overall completion period, whatever may be the reasons; the APTRANSCO shall levy and collect the penalty @ 0.5% per week of the delay on the delayed value of the works / Materials / Equipment.

However the sum of the penalties stated above are subject to a maximum of 10% of the total value of the contract. Once the maximum is reached, APTRANSCO may consider termination of contract.

The right of the APTRANSCO to levy penalty shall be without prejudice to its rights under the law including the right to get the balance works executed by other agencies at the risk and cost of the successful bidder.  This is in addition to the right of the APTRANSCO to recover any damages from the contractor and also blacklisting.

In case the successful bidder fails to execute the supplies/works as per the program or in the opinion of purchaser, the supplies/works are progressing at a slow pace, APTRANSCO reserves its right to get the balance or part of supplies/works executed through other agencies at the risk and cost of the successful bidder, this is in addition to the right of the APTRANSCO to recover any damage from the contractor and also blacklisting.

  - PENALTIES IMPOSED FOR DEFICIENCIES IN QUALITY OF WORKS:  During execution of works, if any deficiencies in quality of works is found in deviation to the Specification/ Agreement, a minimum penalty of Rs.5000 to Rs.30,000/- shall be levied for deficiencies as per each category as mentioned below.

Category I :	Not using (i) prescribed shoring, shuttering and dewatering equipment,(ii) measurement boxes, (iii) Form boxes for different types of foundations and steel measuring boxes, (iv) not providing adequate number of chairs to the steel reinforcements, (v) not carrying out back filling and compaction of the foundation pits in layers and leveling the tower footings properly, (vi) not ensuring that the excavated earth is dumped at least 2 meters away from the pit etc., and (vii) not providing copings to the tower legs/stubs (viii) not providing water tanker, Earth rammers/Earth vibrators.

Category II :	Use of reinforcement steel other than TISCO, VSP and SAIL makes, not using vibrators for effective consolidation of the concrete during foundation works, not using proper templates for firmly keeping the stubs in position when templates are supplied by the contractor & improper fixing of stubs, non ensuring of tower verticality, use of rusted stubs and tower parts if supply is by the contractor, non painting of butt joints and rusted stubs with zinc rich paint immediately after erection of the towers & stringing, non fixing of earth flat to the stub, non deployment of technical personnel for supervision of works by the contractor.  Also not fixing of vibration dampers firmly, repair sleeves wherever necessary, not properly fixing of arcing horns both tower side and line side and bird guards etc., as per specification.

Category III : Use of improper grade / quality of raw material like H.B.G. metal, water and sand for concreting, using clogged and / or lump / clotted cement for concreting, not ensuring proper curing for foundation concrete, not ensuring that all the members of the tower are placed in position and firmly fixed with bolts and nuts immediately after erection of tower, not ensuring that Half round seam welding of the nuts before stringing of the line.

For the above deficiencies in the quality of works noticed by the Engineer, penalties shall be levied as given below.

| # Type of category | First instance (Rs.) | Second instance (Rs.) | Third instance (Rs.) |
| --- | --- | --- | --- |
| Category I | 5,000/- | 10,000/- | 15,000/- |
| Category II | 7,500/- | 15,000/- | 22,500/- |
| Category III | 10,000/- | 20,000/- | 30,000/- |

In the event of fourth instance of noticing the deficiency of quality of works in any of the above categories, the bidder shall be debarred from participating in future tenders for a minimum period of one year.

Non-providing of vehicle as per the requests of the section officer shall attract a penalty of  Rs. 500/- per day as per condition stipulated in clause 24 of Section I of this Specification.

- Incentives for early completion of the works:Incentives to executing agencies / contractors will be given for early completion of the transmission line works based on the formula as detailed below.

- Incentive Bonus Formula.

I = Z * {Y/(X/3)} * 4%,

Where as

I = Incentive Bonus,

Z = Project cost

Y = Days equivalent to the difference of the Scheduled Project commissioning Date and the Project commissioning date.

X=Time period in days for completion of a Project specified in the Specification/ bidding documents of the Project.

However Y should be > 30 days and Incentive Bonus is limited to 4% of the Project Cost

Example for a project cost of a line with 10 corers for which the completion period is           12 months (365 days.). Ifthe agency completed the work before 60 days ahead of the schedule.

The bonus is

I = 10 Cr * {60 / (365/3)}*4% = Rs. 19, 72,602/- (However the bonus will be limited to 4% of project cost)

Incentives will not be applicable for Substation and Bulk Load, Private Power Project works and DC works.  Incentives are applicable for the Transmission lines taken up under capital works. No incentives for lines less than 10KM.  Length of line for incentive is the line length specified in the lot.

- EXTENSION OF THE COMPLETION DATE

When a work cannot be completed within the completion period indicated for reasons beyond the control of the contractor i.e. due to Force Majeure conditions mentioned below or due to the reasons attributable to APTRANSCO, the contractor shall represent for the same and extension of time without levying penalty shall be granted only on the issue of an undertaking by the contractor that they will not put forth at a later date, any claims for extra payments towards increased overheads, material/equipment/works costs etc. during the extended period. It is the sole discretion of the APTRANSCO to grant extension of completion period.

- FORCE MAJEURE:

- The Contractor will not be liable for forfeiture of its performance security, penalty for late delivery, or termination for default if and to the extent that its delay in performance or other failure to perform its obligations under the Contact is the result of an event of Force Majeure.

- For purposes of this clause, "Force Majeure" means an event beyond the control of the Supplier and not involving the Supplier's fault or negligence and not foreseeable.  Such events may include, but are not restricted to, wars or revolutions, fires, floods, epidemics, quarantine restrictions, and freight embargoes.

- If a Force Majeure situation arises, within 15 days from the date of eventuality the Contractor shall notify the Purchaser in writing of such condition and the cause thereof.  Unless otherwise directed by the Purchaser in writing, the Contractor shall continue to perform their obligations under the Contract as far as it is reasonably practice, and will seek all reasonable alternative means for performance not prevented by the Force Majeure event.

- DELAYS ORDERED BY THE PURCHASER

APTRANSCO reserves the right to suspend and reinstate execution of whole or any part of the Works without invalidating the provisions of the contract. Orders for suspension or reinstatement of the Works will be issued by the Engineer to the Contractor in writing. The time for completion of the works will be extended suitably to account for duration of the suspension.  Any costs incurred by the contractor due to increased overheads, idling of labour etc., as a result of such suspension will not be reimbursed to the contractor.

- RESPONSIBILITY OF THE CONTRACTOR:

The successful bidder is responsible

- For the safe delivery of the goods in good condition at destination and execution of the works ensuring quality.  He should acquaint himself of the conditions obtaining in regard to supply of the materials.

- To mobilize and plan for the labour and APTRANSCO shall not be responsible for any mismatch of work on account of whatever so the reasons and the successful bidder has to bear the costs towards ideal labour on account of mismatch of work if any.

- To submit the work/ material bills, (preferably monthly for work bills and for materials immediately after receipt of them at site) promptly and submit all the required enclosures with out fail.   APTRANSCO shall not be responsible for any delayed payments whatever so the reasons.

The bidders are requested to study all the existing conditions and all the above aspects of the project while quoting itself and no extra claim will be entertained on the above reasons.

- CLAIMS DUE TO DELAYS BEYOND CONTRACTOR’S CONTROL:

The contractor shall not be entitled to claim compensation on account of delays or hindrances to the works for any cause whatsoever.  Should the cause of delay or hindrance not be the responsibility of the contractor, the Chief Engineer will consider whether it is possible or not to grant extension of time to compensate for this delay or hindrance. The contractor will not, however, be eligible for any compensation by way of increase in the rates for the works executed beyond the contract period.

- RECOVERY OF MONEY FROM CONTRACTOR IN CERTAIN CASES:

In every case in which provision is made for recovery of money from the contractor, the APTRANSCO shall be entitled to retain or deduct the amount thereof from any moneys that may be due or may become due to the contractor under these present and/or under any other contract or contracts or any other account whatsoever, including Bank Guarantees, Bid Security/Performance Security etc., held up by the APTRANSCO.

- WAY LEAVES & TREE CUTTING IN TRANSMISSION LINE CORRIDOR:

Payment of compensation for damaged crops or fruit bearing trees shall be initially made by the contractor, which will be reimbursed by APTRANSCO later on. The compensation so payable in respect of damaged crops shall be based on the assessment of MRO. In respect of the trees, compensation shall be payable as per the guidelines issued in T.O.O. Dir (Transmission) Ms.no.238, Dt.10.11.2006. The contractor shall take up the payment of compensation amount only after written approval by the Executive Engineer. The contractor shall pay 75% of the compensation in pursuance with the early completion of work. The payment through Account payee cheques shall be done in the presence of Assistant Engineer.

However after finalization of compensation of amounts by the department, the balance amount shall also be paid by the contractor and can claim for the reimbursement of the actual based on the estimates sanctioned by the department and on production of the copies of the cheques given to the land owners/farmers and on production of the receipts/ acknowledgments taken from the land owners.   The Superintending Engineer/OMC shall finalize the compensation claims.

- TERMINATION OF CONTRACT:

If it is found that Progress of works are not commensurate with the program of completion or if the contractor does not fulfill his obligations as per the terms of the specification APTRANSCO will be entitled to terminate the contract in part or full by giving 15 days notice and get the balance works completed through other agencies at the contractor’s cost and risk.

Warning letters will be issued by the concerned Superintending Engineer or/and Chief Engineer  if the progress is not satisfactory. If the progress continues to be poor even after the second warning letter, show cause notice / final notice will be issued by the Superintending Engineer. If no satisfactory reply is received or the progress of the works are not improved within 15 days of issue of the final notice / show cause notice, the Superintending Engineer shall terminate the agreement, which will be followed by stoppage of all payments to the contractor, encashment of the BGs, and after termination of contract the balance works / supplies shall be completed through alternate agencies at contractor’s risk and cost. The contractor so penalized shall be blacklisted for 3 years from the date of termination of contract.

In the event of termination of contract due to delay attributable to the contractor, APTRANSCO is entitled to get back equipment/ material from the contractor for the payment already made but the material is not put to use, and then get the works done by other agency/ agencies for completion of contract by using the said recovered material. The contractor shall have no objection in this regard.

- ARBITRATION

All and any disputes or differences arising out of or touching the order based on this specification shall be decided by a panel of arbitrators as detailed below:

| Sl. No. | Value of Claim | Panel of Arbitrators |
| --- | --- | --- |
|  | Disputes involving amounts up to Rs.10,000/- and below. | Superintending Engineer of the APTRANSCO other than the circle to which the disputes relate. |
|  | Disputes involving amounts ranging from Rs.10,001 to Rs.50,000/- | Any Chief Engineer of the APTRANSCO. |

There shall not be any reference of disputes, the value of which is above Rs.50000/- to arbitration. The parties shall approach the competent Civil Courts situated in Kadapa Jurisdiction only, if any such disputes shall arise involving more than Rs.50,000/-.

A reference for adjudication under this clause shall be made by either party to the contract, within one year from the date of intimating the contractor of preparation of final bill or his having accepted the payment.

CHIEF ENGINEER/ZONE/KADAPA.
SCHEDULE – I

PARTICULARS OF REGISTRATION OF THE BIDDER /BOTH PARTIES INCASE OF JV

| Sl. No. | Details | : | To Be filled by the Bidder |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Name &Address of the Firm / Bidder | : |  |  |  |
|  | State whether a) Individual b) Registered partnership firm c) Unregistered partnership firm d) Pvt. Ltd. Co. e) Public Ltd. Co. f) Others (Please specify) | : |  |  |  |
|  | Registrations under the following If Yes fill the registration No. and enclose a copy of the registration certificate | : | Yes / No | Registration No. | Whether copy enclosed/ not |
|  | Class ‘A’ registration at CEIG | : |  |  |  |
|  | Company of registration Act. |  |  |  |  |
|  | Large, medium or small scale industry at Industries Dept. | : |  |  |  |
|  | GST | : |  |  |  |
|  | Registration under Labour Laws |  |  |  |  |
|  | Any other state sales tax law (please specify) | : |  |  |  |
|  | Name and full address of the partners (in case of partnership firm) or directors (in case of Ltd. Co.) | : |  |  |  |
|  | Name and full address of the JV partner (in case of JV) |  |  |  |  |
|  | Authority of the person signing the contract to represent the company | : |  |  |  |
|  | Whether Photostat copies of the following documents attested. | : |  |  |  |
|  | Copy of partnership deed. | : |  |  |  |
|  | Copy of Memorandum of Articles. | : |  |  |  |
|  | JV Agreement in original (Where applicable) | : | Not Applicable |  |  |
|  | Authority of the partner/company to enter into business in memorandum of association. | : |  |  |  |
|  | A certified copy of the board resolution ( in case the partner is a company) according permission to entering into the joint venture | : |  |  |  |
|  | A certified copy of the board resolution ( in case the partner is a company) according permission for affixing the company seal on the joint venture deed. |  |  |  |  |

Signature of the Bidder/				        (along with the seal)

SCHEDULE - II

DETAILS OF TECHNICAL PERSONNEL OF THE BIDDER

Name of the Bidder/(Both the partners in case of JV)

| Sl. No. | Designation | Name & Qualifications | Professional experience and details of works carried out | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Construction Engineer |  |  |  |
| 2 | Supervisory Staff |  |  |  |
| i) |  |  |  |  |
| ii) |  |  |  |  |
| iii) |  |  |  |  |
| iv) |  |  |  |  |

Signature of the Bidder/

#### Lead Partner

(Along with the seal)

SCHEDULE – III A

###### DETAILS REGARDING FINANCIAL STANDING OF THE BIDDER  /BOTH THE PARTNERS IN CASE OF JV

Name of the Bidder/Lead Partner in case of JV

The following particulars may be filled in.

| Sl. No. | Name of the Bank | Actual balance at credit of the contractor | Permissible overdraft / credit | Total credit | Bank Guarantee Limits | Remarks |
| --- | --- | --- | --- | --- | --- | --- |

Note:	Latest certificates from the Bankers in proof of cash balance and other credit facilities shall be furnished in support of the above information without fail.

Signature of the Bidder/

Lead Partner

(Along with the seal)

SCHEDULE – III B

DETAILS OF FINANCIAL TURNOVER OF THE BIDDER/BOTH PARTNERS IN CASE OF JV

(Here the balance sheet for the last financial year, annual turnover, debt equity ratio and other relevant financial parameters and the proof of their credits standing may be furnished)

Name of the Bidder/Lead Partner in case of JV

| Financial Year | Turnover in Rs. | M.F with weightage of 10% per each financial year | Updated Turnover In Rs. | State whether the required certified copies are enclosed in support of turnover |
| --- | --- | --- | --- | --- |
| (i) | (ii) | (iii) | (iv) = (ii)*(iii) | (v) |
| 2024-25 |  | 1 |  |  |
| 2023-24 |  | 1.1 |  |  |
| 2022-23 |  | 1.2 |  |  |
| 2021-22 |  | 1.3 |  |  |
| 2020-21 |  | 1.4 |  |  |

The Maximum updated Turnover from the above i.e. A    = Rs.

Value of existing commitments and ongoing works i.e. B = Rs.

(As per schedule V-C)

Completion period of the notified works in No. of years i.e. N=

(As per project Data Sheet)

2AN-B = Rs.

In case of JV this statement of both the JV partners are to be given jointly duly showing tee tails of the individual partners

NOTE:	The bidder shall furnish the Certificate from Chartered Accountant in support of their Turnover or can be certified this schedule-III B itself.

If Completion period of this work is less than 6 months, then N = 0.5

Signature of the Bidder/

Lead Partner

(Along with the seal)

SCHEDULE – IV A

DETAILS OF WORKS/CONTRACTS EXECUTED OF SIMILAR TYPE AND MAGNITUDE CARRIED OUT BY THE BIDDER/PARTNER HAVING PHYSICAL EXPERIENCE IN CASE OF JV

Name of the Bidder/ Partner having physical experience in case of JV

| Sl. No | Name of the Line with full description such as Place & State | Length of the Line in km | Order Value | Date of award of contract | Period of completion as per Agreement | Period in which actually completed | Reasons for delay | Date of actual completion & actual cost of work | Principle features |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 132KV |  |  |  |  |  |  |  |  |
|  | Total |  |  |  |  |  |  |  |  |
|  | 220KV |  |  |  |  |  |  |  |  |
|  | Total |  |  |  |  |  |  |  |  |
|  | 400KV |  |  |  |  |  |  |  |  |
|  | Total |  |  |  |  |  |  |  |  |

Note:	 Experience Certificates issued by the an officer not below the rank of Executive Engineer or equivalent cadre of state power utility / Government organizations / PSU only” shall be furnished by the bidder without fail, in support of the above information.

Signature of the Bidder/

Lead Partner

(Along with the seal)

SCHEDULE - IV(B)

DETAILS OF FABRICATED AND SUPPLIED TOWERS/SUBSTATION STRUCTURES   BY THE BIDDER

Name of the Bidder having physical experience/Both parties in case of JV

-------------------------------------------------------------------------------------------------------------------------------------

Sl.           Name of the                  Place and              Quantity           Period of 	      Principal

No.              work                             State                  supplied            supply                        features

------------------------------------------------------------------------------------------------------------------------------------

1	       2     		    3	                   4  		    5      	                       6			                                                                                                           ------------------------------------------------------------------------------------------------------------------------------------

--------------------------------------------------------------------------------------------------------------------------------------

Note:	Experience Certificates issued by the an officer not below the rank of Executive Engineer or equivalent cadre of state power utility / Government organizations / PSU only shall be furnished by the bidder without fail, in support of the above information.

#### Signature of the Bidder/

(Along with the seal)

SCHEDULE - V (A)

DETAILS OF ONGOING WORKS UNDER EXECUTION IN APTRANSCO

(as on the date of submission of the bid)

Name of the Bidder/Both the Partners in case of JV:

|  |  |  | Works on Hand |  |  |  | Works bidded-for |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl. No | Name of the work/ Description | Place & State | Tendered cost in Rs. | Stipulated period of completion | Cost of remaining work | Anticipated date of completion | Estimated cost in Rs. | Date when decision is expected | Stipulated date of completion |
|  | 132kV 220kV 400kV Discoms |  |  |  |  |  |  |  |  |

I / We M/s………………………………… here by declared that the information furnished in respect of works under execution in the above said schedule is true to the best of my / we knowledge and belief.  I / We hereby undertake that in the event of any of the above information found to be false or incorrect at a later date the APTRANSCO is entitled to reject the bid or terminate the contract agreement entered into besides black listing the bidder.

Signature of the Bidder/

Lead Partner

(Along with the seal)

SCHEDULE – V (B)

DETAILS OF ONGOING WORKS UNDER EXECUTION IN OTHER THAN APTRANSCO

(as on the date of submission of the bid)

Name of the Bidder/Both the parties in case of JV:

| Sl. No. | Name of the work | Place and State of work execu-tion | Tender-ing authority / Organization name | Work on hand |  |  | Works tendered for |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Contract value in Rs. | Stipulated date of completion as per contract & scheduled date of completion as per contract | Cost of remain-ing work as on date in Rs. | Anticipated date of completion | Estimated cost in Rs. | Date when decision is expected | Stipulated date of completion |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
|  | 132kV 220kV 400kV Other works |  |  |  |  |  |  |  |  |  |

Note:	The bidder should submit details of all the works on hand invariably which should include the works being executed in other Departments and in other states. If any information found unfurnished or any information furnished in the bid is proven to be false at a later date, the bid will not only be rejected but the bidder will be black listed.

Signature of the Bidder/

Lead Partner

(Along with the seal)

SCHEDULE - V (C)

DETAILS OF ALL ONGOING WORKS UNDER EXECUTION / ALREADY AWARDED AND TO BE TAKEN UP (AWARDED BY APTRANSCO &OTHERS UTILITIES)

Name of the Bidder/Both the Partners in case of JV:

|  |  |  |  | Works on Hand |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl. No. | Name of the work/ Description | Place & State | Order Placing Utility /Authority | Order Value in Rs. | Value of Balance work (x) | Net Value of Balance work to be loaded | Remaining Stipulated period of completion | Whether Certificate issued by the State/Central Government Department / Under takings enclosed |
| I | As an individual |  |  |  |  | x*1 |  |  |
| 1) |  |  |  |  |  |  |  |  |
| 2) |  |  |  |  |  |  |  |  |
| II | As Lead Partner of JV |  |  |  |  | x*0.75 |  |  |
| III | As Associate Partner of JV |  |  |  |  | x*0.25 |  |  |
| Total Value of existing commitment Rs. |  |  |  |  |  |  |  |  |

I/We, Sri./Smt./M/s………………… ……………… ……… ………   ……………………… do here by solemnly affirm and declare that I/we have the balance works on hand as per the details furnished above are true and also declare that in case it is found at a later date to be false fake / incorrect,  I/We …………………………… will abide by any action such as rejection of the bid or disqualification or determination of contract under clause 60(a) PS to APSS or ing or any action may deem fit .

Signature of the Bidder/       Lead Partner

(Along with the seal)

Date:

Place:

Signature of the

Chartered Accountant

(Along with the seal)

Date:

Place:

SCHEDULE - V (D)

UNDER TAKING WITH REGARDS TO THE QUALIFICATION REQUIREMNTS

I.	PHYSICAL EXPERIENCE:

The Physical Experience as per the Qualification Requirement is =

The above Qualification are meeting by considering the following works done by  us=

(i)

(ii)

(ii)

Totals for each type of works. The relevant Certificates are to be attached.

II.	FINANCIAL TURNOVER:

The Financial Turnover as per the Qualification Requirement is i.e. ECV = Rs.

2AN-B arrived as per IIIB is  = Rs.

I/We, Sri./Smt./M/s………………… ……………… ……… ………   ……………………… do here by solemnly affirm and declare that I/we have meeting the qualification requirements as per our knowledge and  the details of Physical experience and financial turnovers furnished above are true and also declare that in case it is found at a later date to be false fake / incorrect,  I/We …………………………… will abide by any action such as rejection of the bid or disqualification or determination of contract under clause 60(a) PS to APSS or black listing or any action may deem fit.

Signature of the Bidder

(Both the partners in case of JV)

Name:

Designation:

Seal:

Date:

Place:

SCHEDULE - V (E)

UNDER TAKING WITH REGARDS TO THE BLACKLISTING BY OTHER UTILITIES

I/We, Sri./Smt./M/s………………… ……………… ……… ………   ……………………… do here by solemnly affirm and declare that I/we as per our knowledge are not blacklisted by any other  utility and our promoters firms or companies were not blacklisted /debarred by any other utility. The information furnished above is true and also undertake that in case if it is found at a later date to be false /fake / incorrect,  I/We …………………………… will abide by any action such as rejection of the bid or disqualification or determination of contract under clause 60(a) PS to APSS or black listing or any action may deem fit.

Signature of the Bidder

Name:

Designation:

Seal:

Date:

Place:

SCHEDULE – VI

DETAILS OF GANGS AVAILABLE FOR ERECTION OF LINE

Name of the Bidder/ Partner having Physical Experience in case of JV:

| Sl. No. | Name of the work under execution | Technical / supervisory staff | Skilled workers | Semi-skilled workers | Un-skilled workers |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 |

Signature of the Bidder/

Lead Partner

(Along with the seal)

SCHEDULE-VII

DETAILS OF VEHICLES AND TOOLS & PLANTS REQUIRED TO BE AVAILABLE WITH BIDDER

Name of the  Bidder/ Partner having physical experience in case of  Joint Venture:

------------------------------------------------------------------------------------------------------------------------

Sl.No.         Tools and Plants                                                 		Quantity

------------------------------------------------------------------------------------------------------------------------

1.         Theodolite                                                             		1 No.

2.	Ranging Rods							20 Nos.

3.	Chain 30 mtrs. Long 						2 nos.

4. 	a) Levelling instrument with					2 Nos.

b) Levelling staves 						2 Nos.

c) No.of flags							20 Nos.

5.	Welding machine with transformer gloves,     			1 set

shield and handle

6.	Hand drilling machine					1 No.

7. 	Steel measuring tape 15M					1 No.

8.	Steel measuring tape 30M					1 No.

9.	Column boxes for a height of 1 M				4 Nos.

10.	a) pin vibrator							1 No. + 1 no. spare

b) Fan vibrator							1 No. + 1 no. spare

c)  Miller  							1 No. + 1 no. spare

11.	Template leveling jacks					30 sets

12.	Rod bending tools (6mm to 20mm sizes)			1 set

13.       Radial drilling machine with drill bits upto			1 set

20mm diameter

14.       Concrete mixer							1 No.

15.       Water pump with hose for curing				1 No.

16.       De watering pump						1 No.

17.        Derrick pole for erection of structures				1 No.

18.	Pipe Derrick 							10 Nos.

19.	Tension stringing equipment for Twin Moose			2 sets.

Conductor (purchase proof has to be enclosed)

20.	100 Tonne compressors with die sets.				2 nos.

21.	Rubberised Aerial rollers					30 nos.

22.	Rubberised Ground rollers					60 nos.

23.	Come along clamps for conductor &earthwire		6 nos.

24.	Leg winches with required steel wire rope			3 nos.

25.       Poly propylene ropes of each 20M minimum length  		10 Nos.

26      	(a) Double end spanners of various sizes upto			1 set

22mm diameter

(b) Ring spanners of various sizes upto 22m diameter  	1 set

(c) Box spanners of various sizes				1 set

(d) Screw drivers and cutting pliers				1 set

27.     	Equipment erection derrick pole 36' height			1 No.

28.	Tripod stand with chain pulley block of 3 Mt

capacity or arrangement to provide a crane

having adequate boom length for erecting equipment

29.       Trifor (2 Tonne) capacity 					Complete set

30.       Gas welding and cutting					1 set

31.       Megger  							1 set

32.	Crimping tools for cable termination				1 No.

33.       Drum lifting jack for mounting cable drums             		2 Nos.

for unwinding cable

34.       Safety belts for the workmen					Complete set

35.	Helmets for the workmen                                        		Complete set

36.       Dynamo meter						Complete set

37.       Other necessary T & P required for complete

execution of the work.

38.	Vehicles :

a)   Jeeps							1 No.

b)  Lorries							2 Nos.

c)  Tractor							1 No.

39. 	Templates            At least 2 Nos templates for each type of tower required for the notified works.

Note:	Based on the studies carried out by the Engineer, minimum suggested major equipment to attain the completion of works in accordance with the prescribed construction schedule are shown in the above list.

Signature of the Bidder/

Lead Partner

(Along with the seal)

SCHEDULE  - VIII

UNDERTAKING TO BE GIVEN BY THE BIDDER

I/We ____________________________________________________ representing the Company/ Partnership Firm/Contractor responding to the bid invitation by the APTRANSCO vide Specification No. APT-______________ hereby sincerely and solemnly affirm and state as follows:

(Strike out whichever is not applicable)

- That myself or any of the representative of my Company/Firm do not have any relatives as deferred in appended Annexure in the APTRANSCO/DISCOM.

OR

- That the following officers/employees of the APTRANSCO/DISCOM are related to me and to my representative of my Company/Firm and their status in the APTRANSCO/DISCOMS is as under:

| S.No. | Name of the Officer/ Employee | Designation and Place of working | APTRANSCO/ DISCOM | Relationship |
| --- | --- | --- | --- | --- |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| 6 |  |  |  |  |

It is certified that the information furnished above is true to the best of my knowledge and belief.  It is hereby undertaken that in the event of any of the above information found to be false or incorrect at a later date, the APTRANSCO/DISCOM is entitled to terminate the contract agreement entered into besides recovering damages as may be found necessary with due notice.

Signature of the Bidder/

Lead Partner

(Along with the seal)

ANNEXURE TO SCHEDULE - VIII

LIST  OF   RELATIVES:

1. 	Father					14. 	Daughter’s Husband

2. 	Mother (including Step .Mother)	15. 	Daughter’s Son

3. 	Son (including Step Son)		16. 	Daughter’s Son’s Wife.

4. 	Son’s Wife				17	Daughter’s Daughter

5. 	Daughter (including Step Daughter)	18. 	Daughter’s Daughter’s Husband

6. 	Father’s Father				19. 	Brother (including Step Brother)

7. 	Father’s Mother			20. 	Brother’s Wife

8. 	Mother’s Mother			21. 	Sister (including Step Sister)

9. 	Mother’s Father			22. 	Sister’s Husband.

10. 	Son’s Son				23. 	Son’s Wife’s Father

11. 	Son’s Son’s Wife			24. 	Son’s Wife’s Mother

12. 	Daughter				25. 	Daughter’s Husband’s Father

13. 	Daughter’s Husband			26. 	Daughter’s Husband’s   Mother

SCHEDULE - IX

DECLARATION TO BE GIVEN BY THE BIDDERFOR TAKING UP THE AWARDED WORKS

On  award of work against Specification No. APT-_________________            , I/We_____________________ will take up the works promptly and achieve progress as per the programme communicated for each of the work.  If I/We _____________________do not show the progress as per Schedule communicated for each work and the progress is (are) proved to be very slow which may result in delay in completion, the APTRANSCO can cancel all such works and may be got executed through alternate agencies at our cost and risk and without prejudice to the right of APTRANSCO to levy any penalties as per the terms of contract.

Signature of the Bidder/

(Along with the seal)

SCHEDULE -X

BANK ACCOUNT DETAILS FOR RTGS

.  The Purchaser will advise his bank to transfer the said amount to the bank account of the Contractor.

1.	Name of the Bank		:

2.	Name of the Branch		:

3.	Branch Code			:

4.	City				:

5.	Account No.			:

6.	MICR No.			:

7.	IFSC No.			:

8.	Income Tax PAN No.		:

9.	GSTIN Registration No.		:

10.	Date of GSTIN Registration	:

11.	Place of GSTIN Registration	:

Signature of the Bidder/

Lead Partner

(Along with the seal)

SCHEDULE -XI

CHECK LIST

Only Positive Confirmations on the following will make the bid responsive.	  Indicate Yes/No

| 1 | State whether the work / materials offered conforms to the relevant APTRANSCO's / ISS Specifications and drawings. (If not Specify the Deviations in Annexure) |  |
| --- | --- | --- |
| 2 | State whether Qualification and Performance particulars are uploaded along with necessary performance certificates in PDF formats. |  |
|  | State whether copies of ‘Tax Deducted at Source’ certificates are uploaded with proper attestation in PDF formats. |  |
|  | State whether copy of ‘GSTIN Registration Certificates’ are uploaded with proper attestation in PDF formats. |  |
|  | State whether copy of ‘A-Grade license certificate’ issued by CEIG of AP is uploaded with proper attestation in PDF formats. |  |
|  | State whether copy of ‘Income Tax registration / PAN registration certificate’ are uploaded with proper attestation in PDF formats. |  |
|  | State whether complete Quantity is quoted. (Bidder must quote for 100% of quantities of all items) |  |
|  | State whether scanned copy of BG / DD for Bid Security is uploaded in PDF format. |  |
|  | State whether Clause 1.0 of Section II Financial is accepted. |  |
|  | State whether Bid Validity is offered as per specification. |  |
|  | State whether APTRANSCO’s Payment Terms are accepted. |  |
|  | State whether APTRANSCO’s completion period & Penalty Clause is accepted. |  |
|  | State whether APTRANSCO's Delivery Schedule / Completion period is accepted. |  |
|  | Are you prepared to furnish Performance Security B.G. if order is placed? |  |
|  | State whether APTRANSCO’s Guarantee Clause is accepted. |  |
|  | State whether Bid form uploaded |  |
|  | State whether Bank’s Certificate for availability of Credit facilities are uploaded |  |
|  | State whether all the signed copy of Schedules (I to X and D& E) are uploaded. |  |
|  | In case of J.V. firm, state whether J.V agreement as per format are uploaded |  |
|  | In case of J.V. firm, state whether Power of attorney for J.V are uploaded |  |
|  | State whether the Guaranteed Technical Particulars for Section-2 to Section -6 of technical Specification are uploaded |  |
|  | State whether copies of type test certificates for equipment/materials are uploaded. |  |
|  | State whether all the clauses are accepted. |  |
|  | State whether prices Schedule –C are uploaded in PDF file. (Commercial schedules) |  |
|  | State whether the total lump sum amount quoted in Bid form is as per schedule-C |  |

Signature of Bidder	/

Lead Partner

(Along with the seal)

SCHEDULE –XII

DECLARATION

The bidder shall produce a declaration as mentioned below on a non-judicial stamp paper of Rs.100/- duly notarized.

“I, Sri/ Smt. /M/s………………… ……………… ……… ………   ……………………… do hereby solemnly affirm and declare that the balance works on hand as per the details furnished in  tender schedule  are true and also declare that in case it is found to be false fake/incorrect at a later date,  I/We will abide by any action such as disqualification or termination of contract under clause 60(a) PS to APSS or black listing or any other action deemed fit by APTRANSCO .”

Signature of Bidder

With Seal and Date

(A) (i) BID SECURITY FORM

Whereas.  .............. (hereinafter called "the Bidder") has submitted its Bid dated (date of submission of bid) for the supply, erection, testing and commissioning of.  ..................………….. (Description of the work) (hereinafter called "the Bid").

KNOW ALL PEOPLE by these presents that WE  .............(Name of bank) having our registered office at  ...........(address of bank)(hereinafter called "the Bank"), are bound unto  ...............(name of Purchaser) (hereinafter called "the Purchaser") in the sum of Rs………………… for which payment well and truly to be made to the said Purchaser, the Bank binds itself, its successors, and assigns by these presents. Sealed with the Common Seal of the said Bank this day of  2026 .

THE CONDITIONS of this obligation are:

1.	If the Bidder

a) Withdraws its Bid during the period of bid validity specified by the Bidder on the Bid Form; or

b) does not accept the correction of errors in accordance with the Bid Specification

OR

2.	If the Bidder, having been notified of the acceptance of its bid by the Purchaser during the period of bid validity;

(a)	Fails or refuses to furnish the performance security, in accordance with the Bid Specification.

(b)	Fails or refuses to execute the Contract Form if required; or

We undertake to pay the Purchaser up to the above amount upon receipt of its first written demand, without the Purchaser having to substantiate its demand, provided that in its demand the Purchaser will note that the amount claimed by it, duly mentioning the B.G. No. and date.

We undertake APTRANSCO that once BG issued; it will not be cancelled with in its validity period without written consent of APTRANSCO, even though bidder produces original Bank Guarantee. (In e-procurement the bidder will upload the scanned copy of the Bid Security and shall not submit the original BG to APTRANSCO, Hence for cancellation of BG, written consent from APTRANSCO is required.)

This guarantee will remain in force up to and including _________________ (mention the date after                the period of the bid validity + 45 days) and any demand in respect thereof should reach the Bank not later than the above date.

...........  .........

(Signature of the Banker)

NOTE:	This will be executed on a Rs.100/- non-judicial stamp paper issued by a scheduled Bank.

- (ii)-FORMAT OF INSURANCE SURETY BOND FOR BID SECURITY

(To be executed on Non-Judicial Stamp Paper of Appropriate Value)

Insurance Security Bond No. __________

Date: __________________

Name of the Tender: __________________________

Tender Specification No.: _____________________

To:

The Chief Engineer,

Kadapa Zone, APTRANSCO,

Transco Nilayama, Sankarapuram, Kadapa.

Whereas.(Name of the Bidder) .............. (Hereinafter called "the Bidder") has submitted its Bid dated (date of submission of bid) for the supply, erection, testing and commissioning of.  ..................………….. (Description of the work) (hereinafter called "the Bid").

KNOW ALL PEOPLE by these presents that WE .............(Name of the Insurance company) having our registered office at ...........(address of Insurance Company) (hereinafter called "the Security"), are bound unto  APTRANSCO...............(name of Purchaser) (hereinafter called "the Purchaser") to the sum of Rs………………… for which payment well and truly to be made to APTRANSCO, the Security binds itself, its successors, and assigns by these presents. Sealed with the Common Seal of the said Security this day of …………../ 2026.

THE CONDITIONS of this obligation are:

1.	If the Bidder

a) withdraws its Bid during the period of bid validity specified by the Bidder on the Bid Form; or

b) does not accept the correction of errors in accordance with the Bid Specification

OR

2.	If the Bidder, having been notified of the acceptance of its bid by the Purchaser during the period of bid validity;

  - fails or refuses to furnish the performance security, in accordance with the Bid Specification.

  - fails or refuses to execute the Contract Form if required; or

We undertake to pay to the APTRANSCO up to the above amount upon receipt of its first written demand, without the APTRANSCO having to substantiate its demand, provided that in its demand the APTRANSCO will note that the amount claimed by it, duly mentioning the Insurance Bond No. and date.

We undertake APTRANSCO that once Security issued, it will not be cancelled within its validity period without written consent of APTRANSCO, even though the bidder produces original Insurance Security Bond. (In e-procurement the bidder will upload the scanned copy of the Security Bond for Bid Security and shall not submit the original Security Bond to APTRANSCO, Hence, for cancellation of Security, written consent from APTRANSCO is required.)

This Insurance Security bond will remain in force up to and including _________________ (mention the date after the period of the bid validity + 60days) and any demand in respect thereof should reach the Security not later than the above date.

For and on behalf of the Insurance Company ………………………………….. in the capacity of

……………………………..

Common Seal of the Insurance Company with complete address including Tel. Nos. / e-Mail Id.

Staff Authority No. of the officer of the Insurance Company /Signatory

##### (B) (i) PERFORMANCE SECURITY FORM

To:(Name of Purchaser)

WHEREAS……………………………………………………….(Name of the Contractor/ Company) (hereinafter called "the Contractor") has undertaken, in pursuance of Contract No.............dated.............201_ to supply/erect  ...........…………………………... (Description of work) (hereinafter called "the Contract").

AND WHEREAS it has been stipulated by you in the said Contract that the contractor will furnish you with a Bank Guarantee by a recognized Bank for the sum specified therein as security for compliance with the Contractor’s performance obligations in accordance with the Contract.

AND WHEREAS we ………………… (Name of the Bank with full address) have agreed to give the Contractor a Guarantee.

THEREFORE WE hereby affirm that we are Guarantors and responsible to you, on behalf of the Contractor, up to a total of Rs............................. (Amount of the Guarantee in Words and Figures) and we undertake to pay you, upon your first written demand declaring the Contractor to be in default under the Contract and without cavil or argument, any sum or sums within the limit of Rs................ (Amount of Guarantee) as aforesaid, without your needing to prove or to show grounds or reasons for your demand or the sum specified therein.

This guarantee is valid until the.  ... day of.  ..... 2020 .

Signature and Seal of Guarantors

..........................................

Date.  .......................2020 .

..........................................

..........................................

Address:....................…...

..........................................

..........................................

NOTE:	This will be executed on a Rs.100/- non-judicial stamp paper by a scheduled Bank.

(B)(ii) - FORMAT OF INSURANCE SURETY BOND FOR PERFORMANCE SECURITY

(To be executed on Non-Judicial Stamp Paper of Appropriate value)

Insurance Surety Bond No...........

Date...................................

Name of the contract:

Lr.no:

To: (Name of the Purchaser)

The Chief Engineer,

Kadapa Zone, APTRANSCO,

Transco Nilayam, Sankarapuram, Kadapa.

In consideration of The Chief Engineer/ Kadapa Zone, APTRANSCO, Transco Nilayam, Sankarapuram, Kadapa,  (hereinafter referred to as the 'Employer' which expression shall unless repugnant to the context or meaning thereof, include its successors, administrators and assigns) having awarded to _______________________(Contractor Name) having its Registered Office &_________________________(hereinafter referred to as the 'Contractor, which expression shall unless repugnant to the context or meaning thereof, include its successors administrators, executors, and assigns), a Contract by issue of Employer's Letter of Intent Lr.No ______________and the same having been acknowledged by the Contractor,. For Rs. _____________ (Rupees ________ only) for Specification No._______________-“     “(Description of Project) and the Contractor having agreed to provide a Contract Performance Guarantee for the faithful performance of the Contract, equivalent to Rs.__________/- (Rupees ___________ only) of the said value of the aforesaid work under the Contract to the Employer.

WE The ____________________________ having our registered office at _______________________(hereinafter called "the Surety"), which expression shall, unless repugnant to the context of meaning thereof, include its successors, administrators, executors and assigns) do hereby guarantee and undertake to pay the Employer, on demand any and all monies payable by the Contractor to the extent of Rs._______________/- (Rupees _________________only) of the as aforesaid at any time up to ____________ (days/month/year] without any demur, reservation, contest, recourse or protest and/or without any reference to the Contractor. Any such demand made by the Employer on the Insurance Company shall be conclusive and binding notwithstanding any difference between the Employer and the Contractor or any dispute pending before any Court, Tribunal, Arbitrator, or any other authority. The Surety undertakes not to revoke this guarantee during its currency without previous consent of the Employer and further agrees that the guarantees herein contained shall continue to be enforceable till the Employer discharges this guarantee or till__________ (days/month/year] whichever is earlier

The Employer shall have the fullest liberty, without affecting in any way the liability of the Insurance Company under this guarantee, from time to time to extend the time for performance of the Contract by the Contractor. The Employer shall have the fullest liberty, without affecting this guarantee, to postpone from time to time the exercise of any powers vested in them or of any right which they might have against the Contractor, and to exercise the same at any time in any manner, and either to enforce or to forbear to enforce any covenants, contained or implied, in the Contract between the Employer and the Contractor or any other course or remedy or security available to the Employer. The Insurance company shall not be released of its obligations under these presents by any exercise by the Employer of its liberty with reference to the matters aforesaid or any of them or by reason of any other act or forbearance or other acts or omission or commission on the part of the Employer or any other indulgence shown by the Employer or by any other matter or thing whatsoever which under law would, but for this provision have the effect of relieving the Insurance Company

The Surety declares that this Insurance Surety Bond is issued by the _______________(name of Insurance Company)  having our registered office at _______________   _as per applicable rules and regulations of insurance regulatory development authority of India (IRDAI), and also agrees that the Employer at its option shall be entitled to enforce this Guarantee against the Insurance Company as a principal debtor, in the first instance without proceeding against the Contractor and notwithstanding any security or other guarantee the Employer may have in relation to the Contractor's liabilities.

- Our liability under this Insurance Surety Bond shall not exceed Rs. ______________/- (Rupees ___________________________ only) of the

- This Insurance Surety Bond shall be valid up to ________________

- We are liable to pay the guaranteed amount or any part thereof under this Insurance Surety Bond only and only if Employer serve upon Insurance Company a written claim or demand on or before ___________________

The Surety Bond can be confirmed from our following E- confirmation cell Mail IDs and Address:

Email ID:

Address:

WITNESS Signed for and on behalf of the

(C) BID FORM

Date.  .......

TO: (Name and Address of Purchaser)

Gentlemen and/or Ladies:

Having examined the Bidding documents, the receipt of which is hereby duly acknowledged, we, the undersigned, offer to execute   ......................... (Description of Work) in conformity with the said bidding documents for the sum quoted by us or such other sums as may be ascertained in accordance with the schedule of prices attached herewith and made part of this Bid.

We undertake, if our Bid is accepted, to complete the work in accordance with the completion period specified in the Schedule-D.

If our Bid is accepted, we will submit the Performance Bank Guarantee as per specification for the due performance of the Contract, in the form prescribed by the Purchaser.

We agree to abide by this Bid upto ……………. (for the Bid Validity Period) specified in          Clause       (         ) and it will remain binding upon us and may be accepted at any time before the expiration of that period.

Until a formal contract is prepared and executed, this Bid, together with your written acceptance thereof and your notification of award, will constitute a binding Contract between us.

We understand that you are not bound to accept the lowest or any bid you may receive.

We certify / confirm that we comply with the eligibility requirements as per clause (     )  of the bidding documents.

Dated this.  ...........day of.  .............2026

____________________________

____________________________

[Signature]

[in the capacity of]

Duly authorized to sign Bid for and on behalf of ………….

(D) FORMAT FOR BANK’S CERTIFICATE TOWARDS

AVAILABILITY OF CREDIT FACILITIES

# BANK CERTIFICATE

This is to certify that M/s. ______________________________ (Full Name & Address) _______________________ who are submitting their bid to TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED against their Bid specification vide ref. No.___________________________ & dated ______________________.

M/s. _______________  is our Customer for the past___________________years. Their financial transactions with our Bank have been satisfactory.  They enjoy the following fund based and non fund based limits including for guarantees, L/C and other credit facilities with us against which the extent of utilization as on date is also indicated below:

| Sl.No. | Type of Facility | Sanctioned Limit as on Date__________ | Utilization as on Date____________ |
| --- | --- | --- | --- |

This letter is issued at the request of M/s. __________________________________.

Sd/-

Name of Bank		__________________

Name of Authorized

Signatory		__________________

Designation		__________________

Phone No.		__________________

Fax No.		 __________________

Address		__________________

SEAL OF THE BANK

(E) FORMAT FOR JOINT VENTURE AGREEMENT

(ON NON-JUDICIAL STAMP PAPER OF APPROPRIATE VALUE TO BE PURCHASED IN THE NAME OF JOINT VENTURE)

PROFORMA OF JOINT VENTURE AGREEMENT AMONG …………………; …………..........

FOR BID SPECIFICATION NO …. ……………….. OF APTRANSCO.

This joint venture agreement executed on this ……………………day of ………………    two thousand and ………………………..among M/s ………………………a company incorporated under the laws of ………………………. and having its registered office at ……………. (hereinafter called the “lead Partner” which expression shall include its successors, executors and permitted assigns) ;                           M/s ………………………… a company incorporated under the laws of …………………………..and having its registered office at …………………………… (hereinafter called the “Partner” which expression shall include its successors, executors and permitted assigns) for the purpose of making a bid and entering into a contract (in case of award) against the specification No…………………………for construction of 220/132KV transmission project on turnkey basis with Transmission Corporation of Andhra Pradesh Limited (APTRANSCO).  (hereinafter called the “Purchaser”), Vidyut Soudha, Vijayawada -04

WHEREAS the purchaser invited bids as per the above mentioned specification for Supply, Transport, Construction, Erection, Testing & Commissioning stipulated in the bidding documents under subject package for 220/132KV Transmission project on turnkey basis.

AND WHEREAS clause...…………………,(Qualifying requirements for bidders as Joint Ventures) and ………….. forming part of the bidding documents, inter-alia stipulates that a Joint venture of two qualified firms/companies as partners, meeting the qualifying requirements, as applicable may bid, provided the Joint venture fulfills all other requirements and in such a case, the Bid Proposal Form shall be signed by all the partners so as to legally bind all the partners of the joint venture, who will be jointly and severally liable to perform the contract and all obligations hereunder.

The above clause further states that the Joint Venture agreement shall be attached to the bid and the contract Performance Guarantee will be as per the format enclosed with the bidding document without any restrictions or liability for either party.

AND WHEREAS the bid has been submitted to the Purchaser vide proposal No…………………. dated……………….. by Lead partner based on the Joint Venture agreement among all the partners under these presents and the bid in accordance with the requirements of clause ………, (Qualifying requirements for bidders as Joint Ventures) and (Qualifying requirements of bidder for 220/132.KVtransmission project), has been signed by all the partners.

NOW THIS INDENTURE WITNESSETH AS UNDER:

In consideration of the above premises and agreements all the partners to this Joint Venture do hereby now agree as follows:

1.	In consideration of the award of the contract by the purchaser to the Joint Venture, we, the partners to the Joint Venture agreement do hereby agree that M/s ……………. shall act as Lead Partner and further declare and confirm that we shall jointly and severally be bound to the purchaser for the successful performance of the contract and shall be fully, responsible for the design, manufacture, supply and successful performance of the material/equipment in accordance with the contract.

2.	In case of any breach of the said contract by the Lead Partner or other partner(s) of the Joint Venture agreement, the partner(s) do hereby agree to be fully responsible for the successful performance of the contract and to carry out all the obligations and responsibilities under the contract in accordance with the requirement of the contract.

3.	Further, if the purchaser suffers any loss or damage on account of any breach in the contract or any shortfall in the performance of the Equipment/material in meeting the performances guaranteed as per the specification in terms of the Contract, the partner(s) of these presents undertake to promptly make good such loss or damages caused to the Purchaser, on its demand without any demur.  It shall not be necessary or obligatory for the Purchaser to proceed against Lead partner to these presents before proceeding against or dealing with other Partner(s).

4.	The financial liability of the Partners of this Joint Venture agreement to the Purchaser, with respect to any of the claims arising out of the performance or non-performance of the obligations set forth in the said Joint Venture agreement, read in conjunction with the relevant conditions of the contract shall, however, not be limited in any way so as to restrict or limit the liabilities of any of the partners of the joint venture agreement.

5.	It is expressly understood and agreed to by the partners to this joint venture agreement that the responsibilities and obligations of each of the partners shall be as delineated in separate Appendix (“To be incorporated suitably by the Partners) to this agreement.  It is further agreed by the Partners that the above sharing of responsibilities and obligations shall not in any way be a limitation of joint and several responsibilities of the partners under this contract.

6.	This Joint Venture agreement shall be construed and interpreted in accordance with the Laws of India and the courts of Hyderabad shall have the exclusive Jurisdiction in all matters arising there under.

7.	In case of an award of a contract, we the partners to the Joint Venture agreement do hereby agree that we shall be jointly and severally responsible for furnishing a Performance Security from a bank (Performance Bank Guarantee) in favour of the purchaser in the currency of the contract for the performance of the said contract.

8.	It is further agreed to that this Joint Venture agreement shall be irrevocable and shall form an integral part of the contract, and shall continue to be enforceable till the purchaser discharges the same.  It shall be effective from the date first mentioned above for all purposes and intents.

IN WITNESS THERE OF, the partners to this Joint Venture agreement have through their authorized representatives executed these presents and affixed common seals of their companies, on the day, month and year first mentioned above.

| 1. Common seal of…………. has been affixed in my/our presence pursuant to the Board of Director’s Resolution dated……………….. | For Lead Partner (Signature of authorized representative) |
| --- | --- |
|  | Name………………….. Designation…………………… Common Seal of the Company |
| Signature………………… Name……………………. Designation……………… |  |
| 2. Common seal of……………… has been affixed in my/our presence pursuant to the Board of Director’s Resolution dated………. | For Lead Partner (Signature of authorized representative) |
|  | Name………………….. Designation…………………… Common Seal of the Company |
| Signature…………….. Name……………… Designation…………….. |  |

WITNESSES

1.	………………………			2.	……………………….

(Signature)						(Signature)

Name…………………				Name………………….

………………………				…………………………

(Official address)					(Official address)

Note:  JOINTVENTURE NOT APPLICABLE AS TENDER ECV VALUE IS BELLOW 10CRORES 
(F) FORMAT FOR POWER OF ATTORNEY FOR JOINT VENTURE

(On Non-Judicial Stamp Paper of Appropriate value to be Purchased in the Name of Bidder)

KNOW ALL MEN BY THESE PRESENTS THAT WE, the Partners whose details are given hereunder………………………………….have formed a Joint Venture under the laws of ……………………………and having our Registered Office/Head Office at ……………… (thereinafter called the ‘Joint Venture’ which expression shall unless repugnant to the context or meaning there of include its successors, administrators and assigns acting through M/s……… … ………………being the partner in-charge do hereby constitute, nominate and appoint M/s…….. …………………….a Company incorporated under the laws of ………………………………and having its Registered / Head Office at …………………………………..as our duly constituted lawful Attorney (hereinafter called “Attorney” or “Authorized Representative” or “Partner Incharge”) to exercise all or any of the powers for and on behalf of the Joint Venture in regard to specification No………………………… Package…………………………..the bids for which have been invited by Transmission Corporation of Andhra Pradesh Limited (APTRANSCO) (hereinafter called the “Purchaser”)to undertake the following acts.

- To submit proposal and participate in the aforesaid Bid Specification of the Purchaser on   behalf of the “Joint Venture”.

- To negotiate with the Purchaser regarding the terms and conditions for award of the Contract pursuant to the aforesaid Bid and to sign the Contract with the Purchaser for and on behalf of the “Joint Venture”.

- To do any other act or submit any document related to the above.

- To receive, accept and execute the Contract for and on behalf of the “Joint Venture”.

It is clearly understood that the Partner in-charge shall ensure performance of the Contract’s and if one or more partner(s) fails to perform their respective portions of the Contract(s), the same shall be deemed to be a default by all the partners.

It is expressly understood that this Power of Attorney shall remain valid, binding and irrevocable till completion of the Warranty Period in terms of the contract.

The Joint Venture hereby agrees and undertakes to ratify and confirm all the acts whatsoever the said Attorney/Authorized Representative quotes in the bid, negotiates and signs the contract with the Purchaser and / or proposes to act on behalf of the Joint Venture by virtue of this Power of Attorney and the same shall bind the Joint Venture as if done by itself.

IN WITNESS THEREOF the Partners Constituting the Joint Venture as aforesaid have executed these presents on this……………….day of………………under the Common Seal(s) of their Companies.

For and on behalf of the

Partners of Joint Venture

…………………………..

………………………..

The Common Seal of the above Partners of the joint Venture:

The Common Seal has been affixed there upto in the presence of:

WITNESS

1.	Signature	……………………		2.	Signature	………………………

Name		……………………			Name		………………………

Designation	……………………			Designation	………………………

Occupation	……………………			Occupation	………………………

LIST OF APPROVED MANUFACTURERS

| Sl. No | Material / Equipment |  | Name of the Manufacturer |
| --- | --- | --- | --- |
| 1) | Conductor |  | M/s Anam Electrical Manufacturing Co., Kadiyam |
|  |  |  | M/s Arrow Cables Ltd, Hyderabad |
|  |  |  | M/s Sterlite Industries India Ltd, Pune |
|  |  |  | M/s Oswal Cables Pvt. Ltd, Hyderabad |
|  |  |  | M/s J.S.K.Industries Ltd, Mumbai |
|  |  |  | M/s Deepak Cables (I) Ltd, Bangalore |
|  |  |  | M/s Smitha Conductors Ltd, Mumbai |
|  |  |  | M/s Hindustan Vidyut Products Ltd., Faridabad |
|  |  |  | M/s APAR Industries Ltd., Vadodara |
|  |  |  | M/s KJV Alloy Conductors Pvt. Ltd, Hyderabad |
|  |  |  | M/s. Hind Aluminium Industries Ltd., Silvasa |
|  |  |  | M/s. Achuyuta Electricals Pvt. Ltd., Hyderabad |
|  |  |  | M/s. Hindustan Vidyut Products, Faridabad. |
|  |  |  | M/s. APAR Conductors, Vadhodara |
|  |  |  | M/s .Cabcon India Pvt Ltd. Kolkota |
|  |  |  | M/s R.E. Cables and Conductors Pvt Ltd. approved by CE/Cont-2 on 01.02.2012 |
|  |  |  | M/s Lumino Industries Ltd,Kolkatta Panther and Moose approved by CE/Cons-1 on 15.03.2013 |
|  |  |  | M/s Diamond Power Infrastructure Ltd,Vadodara, Approved by CE/Const-1 on 18.04.2013 |
| 2) | TransmissionLineTowers and Sub Station Structures fabricators | i) | M/s. Bajaj Electricals Ltd., Mumbai |
|  |  | ii) | M/s. RPG Transmission Ltd., New Delhi |
|  |  | iii) | M/s. Jyothi Structures Ltd., Mumbai |
|  |  | iv) | M/s. BS Transcom, Hyderabad. |
|  |  | v) | M/s. KEC International Ltd., Mumbai |
|  |  | vi) | M/s. Kalpataru Power Transmission Ltd., Gandhinagar |
|  |  | vii) | M/s. Hyundai Electrical Transmission Ltd., Gurgaon |
|  |  | viii) | M/s. Sujana Towers Ltd., Hyderabad |
|  |  | ix) | M/s. Deepak Galvanising&Engg. Indus. Pvt. Ltd., Hyderabad |
|  |  | x) | M/s. Sangam Structures Ltd., Allahabad |
|  |  | xi) | M/s. ICOMM Tele Ltd., Hyderabad |
|  |  | xii) | M/s. Aster Teleservices Pvt. Ltd., Hyderabad |
|  |  | xiii) | M/s. Hyderabad Steels Ltd., Hyderabad |
|  |  | xiv) | M/s. R.S Engineering Co.., Hyderabad |
|  |  | xv) | M/s. Venkateswara Electrical Industries., Hyderabad |
|  |  | xvi) | M/s. Vertex Engineers., Hyderabad |
|  |  | xvii) | M/s. Kusuma Enterprises, Hyderabad |
|  |  | xviii | M/s. K.Ramachandra Rao Transmission & Projects Pvt.Ltd., Hyd. |
|  |  | xix) | M/s Annapurna Constructions and Transmissions Hyderabad |
|  |  | xx) | M/s Iris Infra Services Pvt Ltd Hyderabad |
|  |  | xxi) | M/s Sai Tirumala Fabricators |
|  |  | xxii) | M/s ECI Infra |
|  |  | xxiii) | M/s MPower Infratech. Ltd.Hyd. |
|  |  | xxiv) | M/s AK Power Industries ;Kolkata |

| Sl. No | Material / Equipment |  | Name of the Manufacturer |
| --- | --- | --- | --- |
| 3) a | Porcelain Disc Insulators |  | M/s. Birla NGK Industries Private Limited, Kolkata |
|  |  |  | M/s Insulators & Electricals Company, Bhopal |
|  |  |  | M/s W.S. Industries (I) Ltd., Chennai |
|  |  |  | M/s BHEL, Secunderabad |
|  |  |  | M/s. Saravana Insulators, Chennai |
|  |  |  | M/s General Power Company Ltd, New Delhi. |
|  |  |  | M/s Bikaner Ceramics Pvt Ltd,Rajastan |
| 3)b | Long Rod Porcelain Inulators | i) | M/s Modern Insulators Ltd. Rajasthan |
| 4) | 7/3.15mm HTGS wire |  | M/s UIC Wires Limited, Kolkata |
|  |  |  | M/s Geekay Wires Private Ltd., Hyderabad |
|  |  |  | M/s. Ramsarup Industries, Kolkata |
| 5) | Galvanised Bolts and Nuts and Washers |  | M/s Nexo Industries, Ludhiana |
|  |  |  | M/s HR Steel Industries, Howrah |
|  |  |  | M/s NL Engineers Pvt. Ltd., Mohali |
|  |  |  | M/s HimalayaEngg. Works Pvt. Ltd., Hyderabad |
|  |  |  | M/s Naveen Metal Industries, Kolkata (Washers) |
|  |  |  | M/s Spring Lock Industries, Vadodara (Washers) |
|  |  |  | M/s. Remax (India), Ludhiana |
|  |  |  | M/s. BRK Industries, Ludhiana |
|  |  | - ix) | M/s. Maheshwari Bright and Fasteners Pvrt Ltd. Hyderabad |
|  |  | - x) | M/s KRSNA Transmission Hardware Mfg.Pvt Ltd. Gujrat |
| 6) | Hardware & Accessories and Clamps and Connectors |  | M/s. IAC Electricals Pvt. Ltd., Kolkata |
|  |  |  | M/s. Tyco Electronics Systems India Pvt. Ltd., Bangalore |
|  |  |  | M/s. Godavari Mechanical Industries, Hyderabad |
|  |  |  | M/s. Durga Line Materials, Hyderabad |
|  |  |  | M/s. Kailash Enterprises, Hyderabad |
|  |  |  | M/s. Uday Clamps Mfg. Co., Hyderabad |
|  |  |  | M/s. Modern Malleable Ltd., Kolkata |
|  |  |  | M/s. Star Iron Works Ltd., Kolkata |
|  |  |  | M/s. Asbesco (I) Pvt. Ltd., Kolkata |
| 7) | Solid Core Insulators |  | M/s. Birla NGK Industries Private Limited, Kolkata |
|  |  |  | M/s Insulators & Electricals Company, Bhopal |
|  |  |  | M/s W.S. Industries (I) Ltd., Chennai |
|  |  |  | M/s BHEL, Secunderabad |
|  |  |  | M/s Modern Insulators Ltd., Rajastan |
|  |  |  | M/s. Saravana Insulators, Chennai. |

| Sl. No | Material / Equipment |  | Name of the Manufacturer |
| --- | --- | --- | --- |
| 8) | Circuit Breakers |  | M/s ABB Ltd, Baroda |
|  |  |  | M/s Siemens Ltd., Aurangabad |
|  |  |  | M/s Crompton Greaves Ltd., Nasik |
|  |  |  | M/s. Areva T & D India Ltd., Chennai |
|  |  |  | M/s. Megawin Switchgear P Ltd, Secunderabad (up to 33 kV only) |
| 9) | Current Transformers & Potential Transformers | i) | M/s ABB Ltd., Baroda |
|  |  | ii) | M/s. Areva T & D India Ltd, Banglore |
|  |  | iii) | M/s BHEL, Secunderabad |
|  |  | iv) | M/s Crompton Greaves Ltd., Nasik |
|  |  | v) | M/s. Vidyut Controls Systems (P)Ltd, Hyderabad (up to 132kV) |
|  |  | vi) | M/s. Vijai Electricals Ltd, Hyderabad(PTs up to 132 kV only) |
|  |  | vii) | M/s. LAMCO, Hyderabad (up to 132 kV only) |
| 10) | Capacitor Voltage Transformers |  | M/s ABB Ltd., Baroda |
|  |  |  | M/s. Areva T & D India Ltd, Banglore |
|  |  |  | M/s BHEL, Secunderabad |
|  |  |  | M/s Crompton Greaves Ltd., Nasik |
| 11) | Lightning Arrestors |  | M/s. Areva T & D India Ltd, Bangalore |
|  |  |  | M/s Crompton Greaves Ltd., Nasik |
|  |  |  | Ms/. Lamco Lightning Arrestors Pvt., Ltd., Hyderabad |
|  |  |  | M/s. Oblum Electricals Industries P Ltd., Hyderabad |
|  |  | v) | M/s Elektrolites power ltd.;Jaipur |
| 12) | Isolators |  | M/s G.R.Power Switchgear Ltd., Hyderabad |
|  |  |  | M/s Versatek Switchgears Pvt. Ltd., Secunderabad |
|  |  |  | M/s Southern Switchgear Industries, 145/B, Hyderabad |
|  |  |  | M/s Switchgears &Structurals (I) Private Ltd, Hyderabad |
|  |  |  | M/s Universal Isolators, Indore, MP |
|  |  |  | M/s Siemens Ltd.,Hyderabad |
|  |  |  | M/s Crompton Greaves Ltd., Nasik |
|  |  |  | M/s Switches and Switchgears Hyderabad |
|  |  | ix) | M/s Elekrolites (Power ) Pvt Ltd,Jaipur |
|  |  | x) | M/s S.L.Electricals |
| 13) | Control and Relay Panels |  | M/s G.E. Power Controls, Banglore |
|  |  |  | M/s EasunReyrolle ltd., Hossur |
|  |  |  | M/s. Areva T & D India Ltd, Chennai |
|  |  |  | M/s ABB Ltd., Baroda |
|  |  |  | M/s. Siemens Ltd. |
|  |  | vi) | M/s Schneider Electricals |
| 14) | LTAC Panels & Marshalling Kiosks |  | M/s G.E.Power Controls, Banglore |
|  |  |  | M/s EasunReyrolle ltd., Hossur |
|  |  |  | M/s. Areva T & D India Ltd, Chennai |
|  |  |  | M/s ABB Ltd., Baroda |
|  |  |  | M/s Popular Switchgears Pvt Ltd., Nasik |
|  |  |  | M/s. Jain Enterprises, Rajahmundry |
|  |  |  | M/s Bose Corpration, Kolkata |
|  |  |  | M/s Bodapati Controls |

| Sl. No | Material / Equipment |  | Name of the Manufacturer |
| --- | --- | --- | --- |
| 16) | Chargers & DCDB |  | M/s Dubas Engineering Pvt. Ltd., Bangalore |
|  |  |  | M/s Amara Raja Batteries Ltd., Renigunta |
|  |  |  | M/s Kejriwal Auto Electric & Engineering Works, Kolkata |
|  |  |  | M/s. Automatic Pvt., Ltd., Kolkata |
|  |  |  | M/s. Sabnife, Hyderabad |
|  |  |  | M/s. Statcon Power Controls, Noida |
|  |  |  | M/s. Agarwal Salt Co., Bikaner |
|  |  |  | M/s Chhabi Electricals Pvt. Ltd., Jalgoan , Maharastra |
|  |  |  | M/s Servilink Engineers Pvt Ltd, Vadodara |
|  |  |  | M/s Caldyne Automatics Ltd., Kolkata |
|  |  |  | M/s Swati Electronics Pvt Ltd. |
| 17) | Batteries (Sealed Maintenance free Batteries) |  | M/s Amara Raja Batteries Ltd., Renigunta |
|  |  |  | M/s. HBL Nife, Hyderabad |
|  |  |  | M/s. Exide, Hyderabad |
|  |  |  | M/s AAJ Accumulators Pvt Ltd., Kolhapur |
| 18) | Control Cables & LT power Cables |  | M/s. Arrow Cables Ltd, Hyderabad |
|  |  |  | M/s. Arun manufacturing Company, Delhi |
|  |  |  | M/s. Vikas Cable Company, New Delhi |
|  |  |  | M/s. Polycab Wires Pvt., Ltd., Daman |
|  |  |  | M/s. Finecab Ltd., Hyderabad |
|  |  |  | M/s. GoyoleneFibres ( India) Private Limited, Mumbai |
|  |  |  | M/s. Deco Industries ( India) Pvt., Ltd., Delhi |
|  |  |  | M/s. Grid India Power Cables Pvt., Ltd Gurgao |
|  |  |  | M/s. Pavan Power Cables, Hyderabad |
|  |  |  | M/s. SPM Power and Telecom Pvt Ltd Hyderabad |
|  |  |  | M/s .Thermo Cables Limited , Hyderabad |
|  |  |  | M/s. KEI Industries Limited, Hyderabad |
|  |  |  | M/s. GEMSCAB Industries Ltd,Rajastan |
|  |  |  | M/s. Diamond Power Infrastructure Ltd,Vadodara |
| 19) | XLPE U/G Power Cables |  | M/s. Universal Cables Ltd., Satna |
|  |  |  | M/s. RPG Cables Ltd, Hyderabad |
|  |  |  | M/s. Hindustan Vidyut Products Ltd., New Delhi-110001 |
|  |  |  | M/s. Cable Corporation of India Ltd, Mumbai |
|  |  |  | M/s. Torrent Cables Gujrat. |
| 20) | Sub-Station Lighting |  | M/s. Bajaj Electricals |
|  |  |  | M/s. Philips |
|  |  |  | M/s. Crompton Greaves Ltd |
| 21) | Wave Traps |  | M/s. Areva T & D India Ltd, Bangalore |
|  |  |  | M/s. BPL, Palakkad, Kerala |
| 22) | PLCC and Telecom Equipment |  | M/s. ABB, Mumbai |
|  |  |  | M/s. BPL, Palakkad, Kerala |
|  |  |  | M/s. Puncom, Mohali |

| Sl. No | Material / Equipment |  | Name of the Manufacturer |
| --- | --- | --- | --- |
| 23) | Energy Meters |  | M/s. Secure meters Ltd., Udaipur |
|  |  |  | M/s. L & G, |
|  |  |  | M/s. L & T, Mysore |
| 24) | a) 33kV Station Transformers |  | M/s. Vijay Elec. Ltd, Hyderabad |
|  |  |  | M/s. Crompton Greaves Ltd, Nasik |
|  |  |  | M/s. EsennarTrasformers (P) Ltd., Hyderabad |
|  |  |  | M/s. EMCO Ltd., Jalgoan |
|  |  |  | M/s. Inra Vidyut Ltd., Banglore |
|  |  |  | M/s. ECE, Hyderabad |
|  |  |  | M/s. HIT, Hyderabad |
|  |  |  | M/s. PETE, Hyderabad. |
|  |  |  | M/s HINT |
|  | b) 11kV Station Transformer |  | As per DISCOMs approved list of Companies. |
| 25) | Diesel Generator Set |  | M/s. Powerica |
|  |  |  | M/s. Jakson Ltd., Noida |
|  |  |  | M/s. Escorts Ltd., |
|  |  |  | M/s. Genset India (P) Ltd., Kolkata |
|  |  |  | M/s. Greaves Cotton Ltd. |
| 26)a) | Steel Brands for use in Reinforcement |  | 1) VSP 2) SAIL 3) TISCO |
| 26)b) | Steel Brands for use for Structures & Towers |  | 1) VSP 2) SAIL 3) TISCO and 4) ISCO |
| 27) | Cement Brands |  | 1) ACC Limited 2) Kesoram Cements 3) Orient Cements 4) Zuari Cements 5) CCI Limited 6) Andhra Cements 7) Coramandel Cement 8) Raasi Cement 9) Sri Vishnu Cements 10) Madras Cements 11) Ultra Tech Cement Limited – APCW 12) KCP Limited 13) Penna Cements 14) Panayam Cement 15) Grasim 16) Rajashree Cement 17) Mysore Cement 18) Century Cement 19) Ambhuja Cement and 20) Priya Cement21) Deccan Cement 22) Dalmia Cement 23) Maha Cement 24) Prajashakti Cement 25) JSW Cements 26) M/s Bharati Cements 27)M/s Sagar Cements 28) Nagarjuna Cement |
| 28) | Furniture |  | Godrej |
| 29) | T & P |  | Taparia, Indore. |
| 30) | EOT Crane |  | RANK, ACCESS, TRANS RAIL, SIVPRA, ATLAS CRANES |
| 31) | AIR CONDITIONING SYSTEM |  | Voltas, Bluestar, Carrier |
| 32) | PLCC Terminal & Coupling units |  | M/s. ABB Limited., Andheri (west) Mumbai |
| 33) | PLCC Terminals, wave traps & Exchanges |  | M/s. BPL Telecom PVt.LTd., Kasturba Road, Banglore. |

| 34) | Exchanges | 1 | M/s. IntelliconPvt.Ltd., Karkhana, Secunderabad |
| --- | --- | --- | --- |
|  |  | 2 | M/s. IntelliconPvt.Ltd., Gandhinagar. |
|  |  | 3 | M/s. Siemens Ltd., Banglore |
| 35) | Wave Traps | 1 | M/s. Areva T&D PVt Ltd., Hosur, Tamilnadu |
|  |  | 2 | M/s. Techno Labs, Hyderabad |
| 36) | Telephone Cables |  | M/s. Maharaja Cables, New Delhi |
| 37) | Batteries & Chargers |  | M/s. Amar Raja Power Systems Ltd., Karakamb, Tirupathi. |
| 38) | Chargers | 1 | M/s. Swati Electronics & Automation, Balanagar, Hyderabad |
|  |  | 2 | M/s. Exide Batteries Ltd., Hosur, Banglore. |
|  |  | 3 | M/s. SPM Cables, Secunderabad |
| 39) | OLT equipment |  | M/s. Comtel Networks Pvt Ltd., Trombay Road, Chember, Mumbai. |
| 40) | Chargers |  | M/s. S. Creative Electronics, Gurgaon, Haryana |
| 41) | A/C units |  | M/s. Varun Techno Services, Ameerpet, Hyderabad |
| 42) | Cables |  | M/s. Kothari Brothers, Hyderbasti, Secunderabad |
| 43) | A/C Units |  | M/s. Globo Tech Services, Vijayanagar Colony, Hyderbad |
| 44) | Electric Testing Instrument |  | M/s. World Traders & Company, Veernariman road, Mumbai |
| 45) | PLCC terminals |  | M/s. Punjab communications Ltd., S.A.S.Nagar, Chandigarh. |
| 46) | Batteries |  | M/s. Exide Industries LTd., Chowranghee road, Kolkata. |
| 47) | Chargers | 1 | M/s. DubasEngineering Pvt.Ltd., BTM Layout, Bangalore. |
|  |  | 2 | M/s. SM Creative Electronics Ltd., Gurgaon, Haryana |
|  |  | 3 | M/s. Exide Industries Ltd., KrishnagiriDist, Tamilnadu |

The following Power Grid approved steel manufacturers are also approved by APTRANSCO for procuring steel and angles which are not manufactured/rerolled by SAIL, VSP. TISCO & ISCO subject to stage inspection as per clause 24.1 section- I General.

        - M/s Southern iron & steel company Ltd, Pattaneri, Salem (Tamil Nadu)

        - M/s Lloyds Steel (only for steel plates)

        - M/s Jindal Steel & Power Ltd, Raigarh (only slabs, booms & billets).

        - M/s Jindal Vijaya Nagar Steel Limited, Bellary, Karnataka, (only for plates 3mm to 10mm thick)

        - M/s Jindal Iron & Steel Company Ltd, Thane.

        - M/s. Hazira works  (for MS & HT plates upto 20mm thick)

The following re-rollers are approved by APTRANSCO subject to procurement of the input Ingots from  SAIL, VSP. TISCO & ISCO

  - M/s Sanvijay Rolling & Engineering Limited, Nagpur.

  - M/s Shri Bhajarang Alloys Ltd, Nagpur.

  - M/s Vandana Ispat Ltd, Raipur.

  - M/s Shilpa Re-Rollers Ltd, Butibori, Nagpur.

  - M/s Bhuwalka Steel Industries Limited, Thane.

  - M/s P.R. Rolling Pvt Ltd, Jaipur.

  - M/s VinarIspat Ltd, Chandrapur.

  - M/s Eagle Steels, Taloja.

  - M/s Shilpa Re-Rollers Ltd, Kamptee Road, Nagpur.

  - M/s Mahavir Steel Industries Ltd, Pune.

  - M/s Unique Structures & Tower Ltd, Raipur.

  - M/s Rita Steel Industries, Nagpur.

  - M/s United Metal Industries, Chennai.

  - M/s Hamma Steel Industries, Chennai.

  - M/s Sharda Ispat, Nagpur.

  - M/s Maharashtra Steel Rolling & Engineering works, Mumbai.

  - M/s SRMB Udyog Limited Paharpur, Kolkata.

  - M/s Shyam Steel Industries Limited, Kolkata.

  - M/s Prakash Ispat Udyog, Nagpur.

  - M/s Swastika Steel & Allied products, Kolkata.

  - M/s Sujana Metal products, Hyderabad.

  - M/s Kadevi Engineering Co. Pvt Ltd, Hyderabad.

  - M/s Sawaria Pipes Pvt Ltd, Hyderabad.

  - M/s Abhishek Steels Pvt. Ltd, Hyderabad.

The above re-rollers are approved with the following guide lines into consideration.

i) The steel angles re-rolled shall be as per the approved manufacturing quality assurance plan.

ii)The steel supplied to APTRANSCO shall be embossed with company name ending with APT

Note: The list of approved vendors will be varying from time to time depending on the validity extension and the details of the approved vendors list will be available in APTRANSCO website. Hence, the same may be verifiedfrom APTRANSCO website.
LIST OF THE APPROVED BANKS FOR ISSUING BG /DD

| S.No. | NAME OF THE BANK |
| --- | --- |
| 1 | Allahabad Bank |
| 2 | Andhra Bank |
| 3 | APCO. Bank, Main Branch, Hyderabad. |
| 4 | Bank of Baroda |
| 5 | Bank of India |
| 6 | Bank of Maharashtra |
| 7 | Bank of Punjab Ltd |
| 8 | Central Bank of India |
| 9 | Centurion Bank Ltd |
| 10 | City Bank |
| 11 | Corporation Bank |
| 12 | Federal Bank |
| 13 | HDFC Bank, |
| 14 | HSBC BANK |
| 15 | I.C.I.C.I Bank |
| 16 | I.D.B.I. Bank |
| 17 | Indian Bank |
| 18 | Indian Overseas Bank |
| 19 | ING Vysya Bank Ltd |
| 20 | Karnataka Bank |
| 21 | Karur Vysya Bank |
| 22 | Kotak Mahindra Bank |
| 23 | Lakshmi Vilas Bank |
| 24 | Oriental Bank of Commerce |
| 25 | Punjab National Bank |
| 26 | Standard Chartered Bank |
| 27 | State Bank of India and other State Bank Group Banks / Associate Banks. |
| 28 | Syndicate Bank |
| 29 | U.T.I. Bank Ltd |
| 30 | Union Bank Of India |
| 31 | Vijaya Bank |
| 32 | YES Bank Ltd |
| 33 | Development Credit Bank Ltd., |
| 34 | UCO Bank |

COMPLETION PERIOD - SCHEDULE – D

Program of execution:

The successful bidder shall execute the works as per the program given in bar charts for each work.

The overall completion period of the project is as per the Project Data Sheet. The commencement date of the Project will be reckoned from the date of issue of detailed Contract award letter or from the date of issue of 10% profiles for the line or from the date of issue of the approved layout /Formation levels for Sub-Station/Bay whichever is later.  If the tender involves multiple works like transmission lines and substation works, the single completion period mentioned in the following table shall be considered as per TOO  Ms no 492 DT 28.02.2011 and T.O.O.(CE-Projects) Ms.No.4040 Date: 17.03.2026.

| Sl.No. | Description of work | Completion Period |
| --- | --- | --- |
| 1 | Replacement of existing ACSR Lynx conductor (16.37KM) with AAAC Panther conductor for 132KV Chittoor – Pakala SC line in Chittoor District under RMI 2024-25 on turn key basis. | 9 (Nine months) |

I/We agree to the above mentioned completion period.

Signature of the Bidder/

Lead Partner

(Along the seal)

CHIEF ENGINEER/ZONE

APTRANSCO/KADAPA

## SCHEDULE – E

LIST OF MAKES OF THE MATERIALS PROPOSED TO SUPPLY IF THE CONTRACT IS AWARDED

| Sl. No | Material / Equipment |  | Name of the Manufacturer |
| --- | --- | --- | --- |
| 1) |  | a) |  |
|  |  | b) |  |
|  |  | c) |  |
| 2) |  | a) |  |
|  |  | b) |  |
|  |  | c) |  |
| 3) |  | a) |  |
|  |  | b) |  |
|  |  | c) |  |

While quoting the bid we have considered the above makes of the materials. I/We agree to supply the materials invariably from the above makes if the order is placed on us.

Signature of the Bidder/

Lead Partner

(Along the seal)

Note: The bidder shall furnish a maximum of three manufacturers per each material from the list of approved manufacturers from whom they are going to purchase the materials if order is placed. This manufacturers has to be furnished for all the materials mentioned under schedule-A.

# NOTICE INVITING BIDS

| 1. | Department Name | : | APTRANSCO-Chief Engineer/KadapaZone/KADAPA |
| --- | --- | --- | --- |
| 2. | Tender notice number | : | e- 28 /2026-27 of CE/KADAPA Zone |
| 3. | Bid Number | : | e- 42 /2026-27 of CE/KADAPA Zone |
| 4.1 | Bid Subject | : | Replacement of existing ACSR Lynx conductor (16.37KM) with AAAC Panther conductor for 132KV Chittoor – Pakala SC line in Chittoor District under RMI 2024-25 on turn key basis. |
| 4.2 | Name of the Project. | : | Replacement of existing ACSR Lynx conductor (16.37KM) with AAAC Panther conductor for 132KV Chittoor – Pakala SC line in Chittoor District under RMI 2024-25 on turn key basis. |
| 5. | Package No. | : | APT-e- 42 (CE/Zone/KDP)/2026-27 |
| 6. | Estimated Contract Value | : | Rs. 2,20,13,114.00 |
| 7. | Period of Contract | : | 9 (Nine) months |
| 8. | Form of Contract | : | LS |
| 9. | Bid Type | : | Open Competitive Bidding |
| 10. | Bid Category | : | Works |
| 11. | Bid Validity | : | 90 days from Scheduled Bid submission closing date |
| 12. | EMD / Bid Security | : | 2% of Estimated Contract Value i.e., Rs. 4,40,262/- |
| 13. | EMD/Bid Security Payable to | : | In the form of Demand Draft in favour of Superintending Engineer/O&M Circle/APTRANSCO/Tirupati ,payable at Tirupati (or) Bank Guarantee issued by a Nationalized Bank/ Scheduled Bank (as per the list enclosed)/ Insurance Surety Bond issued by Insurance Companies as per IRDAI Guide lines in favour of Superintending Engineer/O&M Circle/APTRANSCO/ Tirupati, and shall cover a period of 60 days over and above the period of bid validity |
| 14. | Transaction Fee | : | Rs.7,793/- (i.e., 0.03% on ECV + GST @ 18%) |
| 15. | Transaction Fee Payable to | : | Payable on line to Managing Director, APTS., Vijayawada. |
| 16. | Schedule Sale opening Date | : | .2026 at 01.00 PM (IST) |
| 17. | Schedule sale Closing Date | : | .2026 at 05.00 PM (IST) |
| 18. | Pre-Bid meeting date | : | - |
| 19 | Bid Submission Closing Date | : | .2026 at 04.00 PM (IST) |
| 20. | Bid Submission | : | Online |
| 21. | Pre-qualification/Technical Bid Opening Date | : | .2026 at 04.30 PM (IST) |
| 22. | Place of Bid Opening | : | O/o. Chief Engineer Engineer/Zone APTRANSCO, Sankarapuram/KADAPA. |
| 23. | Officer Inviting Bids | : | CHIEF ENGINEER / Zone/KADAPA |
| 24. | Address | : | APTRANSCO, Transco Nilayam, Sankarapuram, KADAPA -516002. |
| 25. | Contact Details/ Telephone/Fax | : | Phone No. 9440877700,9490154205 |
| 26. | Eligibility Criteria | : | Refer Clause No. 3 ‘Qualification Requirements’ of General Terms and conditions of contract of specification Volume-1 |
| 27. | Procedure for Bid Submission | : | Refer Instructions to the bidder of specification Volume-1. |
| 28. | General Terms & Conditions | : | Refer General Terms and conditions of contract of specification Volume-1 Note: Bidders are requested to go through all the clauses and contents of specification thoroughly and quote the bid. Ignorance of clauses will not be entertained by the purchaser at a later date. |

CHIEF ENGINEER/ZONE

APTRANSCO::KADAPA

PROJECT DATA

|  | Name of the Project / work | : | Replacement of existing ACSR Lynx conductor (16.37KM) with AAAC Panther conductor for 132KV Chittoor – Pakala SC line in Chittoor District under RMI 2024-25 on turn key basis. |
| --- | --- | --- | --- |
|  | Location | : | Chittoor |
|  | District, Mandal | : | Chittoor District |
|  | Circle and Division | : | SE /O&M circle /Tirupati, EE / O&M/ Chittoor |
|  | Medical Aid |  | Chittoor |
|  | Bid Inviting Authority | : | Chief Engineer / Zone / APTRANSCO/KADAPA, Transco Nilayam, Kadapa Zone/KADAPA-516002. |
|  | Master Copy of the Bid Specifications available | : | Chief Engineer /Kadapa Zone/KADAPA |
|  | Rates of Taxes adopted | : | Schedule A: GST = 18%, on works contract. Schedule B: GST =18% on total. |
|  | Present Rates of Tax Deductions in the Bills |  | Income Tax = 2.0%, GST and Seignorage charges as per Govt. rules in vogue. |
|  | Basic Data for Price Variation |  | The Basic rate of Transmission Line Tower Parts, Substation Structures and Earth Flat as taken in the estimate was exclusive of all taxes and transportation charges for the month May 2026 Sl. No.; Material; May 2026. 1; Galvanized Line structures per MT; Rs.107967/-. Galvanized SS structures per MT; Rs.99130/-. 2; M.S. Flat per MT; Rs. 57,000/-. 3; GI Flat per MT; Rs. 83741/-. |
|  | Completion Period of the Project. |  | Refer Schedule D |
|  | Financial Tie up / Funding | : | PFC/REC/Banks/any other Financial Agency. |
|  | Any amendments / deviations given to the Standard Bid Documents. |  | Will be furnished in Special Conditions of the Contract. |

CHIEF ENGINEER/ZONE

APTRANSCO::KADAPA

3.0 QUALIFICATION REQUIREMENTS:

A.	Physical Experience Requirements: For awarding of notified work/ project the bidder should meet the following qualifying criteria.

3.1     The bidder is a sole bidder having experience in supply, erection, testing & commissioning of 132KV or Higher Voltage overhead line and must have qualification requirement as per T.O.O (CE-Construction-1) MS No. 492, Dated : 28-02-2011 and MS.No.146, Dt. 08-08-2012

Note: The Joint Venture clause shall be applicable for the works with ECV greater thanRs.10.00 Crores only. As this ECV is below Rs.10.00 Crores, Joint Venture is not applicable for this project.

3.2	The bidder should have valid ‘A” Class electrical license issued / recognized by Government of AP for executing the electrical works related to Extra High voltages.

  - The bidder in his name should have executed the following quantity of works mentioned below against each type of notified work.

| Sl. No | Notified Work | Technical Qualification Criteria |  |
| --- | --- | --- | --- |
|  |  | The bidder should have executed at least the following works in the last 10 years as a prime contractor / as a lead partner for qualifying the notified work. | The following works done by the bidder should be in successful operation for at least one year. The bidder shall enclose the proof of successful operation of 1 year. |
| 1 | Replacement of existing ACSR Lynx conductor (16.37KM) with AAAC Panther conductor for 132KV Chittoor – Pakala SC line in Chittoor District under RMI 2024-25 on turn key basis. | Supply, Erection / Stringing of 50% of 132KV or higher voltage line of notified KM (or) 100% of 66KV or higher voltage line of notified KM as Prime Contractor certified by not below the rank of Executive Engineer | Supply, Erection / Stringing of 50% of 132KV or higher voltage line of notified KM (or) 100% of 66KV or higher voltage line of notified KM as Prime Contractor certified by not below the rank of Executive Engineer |

Note: The Joint Venture clause shall be applicable for the works with ECV greater than Rs.10.00 Crores only. As this ECV is below Rs.10.00 Crores, Joint Venture is not applicable for this project. The lead Partner of the Joint Venture shall meet at least either one of the Q.R mentioned against Sl.No. 1 or Sl.No. 2 otherwise the bid will be disqualified.

If the notified work is a combination of the above items, the bidder shall meet the qualification requirements mentioned against each notified item separately. “The bidder should invariably furnish the Performance certificates in support of their Qualifying requirements and the Performance certificates shall be issued by an officer not below the rank of Executive Engineer or equivalent cadre of state power utility / Government organizations / PSU only otherwise the bid will become non-responsive”.

CHIEF ENGINEER

ZONE::KADAPA