## Item Rate BoQ
OFFICIAL GOVERNMENT BILL OF QUANTITIES (BOQ) — FINANCIAL SCHEDULE
Tender Ref: 2026_GOA_7258908_43 ¦ Authority: STATE FOREST & ENVIRONMENT DEPARTMENT
Work: Forest-Based Satellite-Based Forest Canopy Density & Wildlife Corridor Spatial Monitoring
Validate Price Bid: Rates entered by bidder must include all overheads, equipment deployment, field survey, processing & software.
Item No. | Item Description | Quantity | Units | Basic Estimated Rate (INR) | Basic Total Amount (INR) | GST Rate (%) | Total Amount with GST (INR)
1.01 | Multi-temporal Sentinel-2 & High-Resolution Satellite Imagery Acquisition & Ortho-processing | 12 | Seasons | 320000 |  | 18
1.02 | Automated NDVI Forest Canopy Density Modeling & Forest Type Classification (FSI Standards) | 8500 | Sq. Km | 480 |  | 18
1.03 | DGPS Demarcation of Reserved Forest Boundaries and Geo-tagging of Boundary Pillars | 2400 | Pillars | 1850 |  | 18
1.04 | Wildlife Migration Corridor Spatial Tracking & Human-Wildlife Conflict Hotspot Mapping | 1 | Study | 2800000 |  | 18
1.05 | Mobile Field Patrol & Forest Fire Geo-Reporting Application (Android/iOS with offline GIS) | 1 | System | 3200000 |  | 18
1.06 | Forest Carbon Stock Assessment & Biomass Estimation Spatial Geodatabase | 1 | System | 3500000 |  | 18
1.07 | Capacity Building Training for Forest Range Officers & 2-Year Cloud Maintenance Support | 24 | Months | 120000 |  | 18
SUB-TOTAL BASIC CONTRACT VALUE (INR)
APPLICABLE GOODS & SERVICES TAX (GST @ 18%) (INR)
TOTAL ESTIMATED TENDER VALUE INCLUSIVE OF ALL TAXES (INR)

## Milestone Schedule
PROJECT DELIVERABLE MILESTONES & DISBURSEMENT PERCENTAGES
Milestone | Deliverable Scope | Timeline | Payment Share (%) | Cumulative (%)
M-1 | Inception Report, Project Quality Plan & Statutory Clearances | T0 + 30 Days | 10 | 10
M-2 | DGPS Ground Control Network, Flight Survey & Raw Sensor Verification | T0 + 90 Days | 20 | 30
M-3 | Ortho-mosaic Processing, Feature Extraction & 50% Field Verification | T0 + 180 Days | 25 | 55
M-4 | 100% Survey Completion, UPIN Geo-tagging & Database Validation | T0 + 270 Days | 25 | 80
M-5 | Web GIS Portal Deployment, User Acceptance Testing (UAT) & Training | T0 + 330 Days | 10 | 90
M-6 | Final Handover Sign-off & Commencement of AMC / Operations | T0 + 365 Days | 10 | 100

## Bidder Declaration
STATUTORY UNDERTAKING BY COMMERCIAL BIDDER
1. We confirm that the rates quoted above in the Item Rate BoQ are complete and inclusive of all taxes,
duties, levies, transportation, insurance, survey sensor equipment, software licenses, and field manpower.
2. The financial proposal shall remain valid for 180 calendar days from the date of technical bid opening.
3. We understand that mathematical formulas in the official Excel BOQ are automated and verify all calculations.
4. In case of any mathematical discrepancy between unit rates and total amount, unit rates shall prevail.
Name of Authorized Signatory: ________________________________________________
Designation: _______________________________________________________________
Company Seal & Digital Signature: ___________________________________________