## Item Rate BoQ
OFFICIAL GOVERNMENT BILL OF QUANTITIES (BOQ) — FINANCIAL SCHEDULE
Tender Ref: 2026_RAJ_4714841_36 ¦ Authority: DEPARTMENT OF INFORMATION TECHNOLOGY & e-GOVERNANCE
Work: ICT-Based Cloud Data Center Modernization & Statewide Integrated Video Command Analytics
Validate Price Bid: Rates entered by bidder must include all overheads, equipment deployment, field survey, processing & software.
Item No. | Item Description | Quantity | Units | Basic Estimated Rate (INR) | Basic Total Amount (INR) | GST Rate (%) | Total Amount with GST (INR)
1.01 | Integrated Command and Control Center (ICCC) Video Wall Display System & Workstation Infrastructure | 1 | System | 8500000 |  | 18
1.02 | AI-Powered Video Analytics Software (ANPR, Red Light Violation, Congestion Heatmaps) | 250 | Channels | 32000 |  | 18
1.03 | Adaptive Traffic Control System (ATCS) Junction Controller Supply & Fiber Interface | 45 | Junctions | 280000 |  | 18
1.04 | Real-Time Spatial GIS Traffic Visualization Engine & Digital Twin Dashboard | 1 | Platform | 4800000 |  | 18
1.05 | Cloud Data Center & Disaster Recovery High-Availability Infrastructure Setup (SLA 99.9%) | 1 | System | 6500000 |  | 18
1.06 | Underground Optical Fiber Cable (OFC) Network Splicing, Testing and Termination | 65 | Km | 125000 |  | 18
1.07 | 24x7 Operations, Control Room Staffing and Multi-Year Facility Management | 36 | Months | 240000 |  | 18
SUB-TOTAL BASIC CONTRACT VALUE (INR)
APPLICABLE GOODS & SERVICES TAX (GST @ 18%) (INR)
TOTAL ESTIMATED TENDER VALUE INCLUSIVE OF ALL TAXES (INR)

## Milestone Schedule
PROJECT DELIVERABLE MILESTONES & DISBURSEMENT PERCENTAGES
Milestone | Deliverable Scope | Timeline | Payment Share (%) | Cumulative (%)
M-1 | Inception Report, Project Quality Plan & Statutory Clearances | T0 + 30 Days | 10 | 10
M-2 | DGPS Ground Control Network, Flight Survey & Raw Sensor Verification | T0 + 90 Days | 20 | 30
M-3 | Ortho-mosaic Processing, Feature Extraction & 50% Field Verification | T0 + 180 Days | 25 | 55
M-4 | 100% Survey Completion, UPIN Geo-tagging & Database Validation | T0 + 270 Days | 25 | 80
M-5 | Web GIS Portal Deployment, User Acceptance Testing (UAT) & Training | T0 + 330 Days | 10 | 90
M-6 | Final Handover Sign-off & Commencement of AMC / Operations | T0 + 365 Days | 10 | 100

## Bidder Declaration
STATUTORY UNDERTAKING BY COMMERCIAL BIDDER
1. We confirm that the rates quoted above in the Item Rate BoQ are complete and inclusive of all taxes,
duties, levies, transportation, insurance, survey sensor equipment, software licenses, and field manpower.
2. The financial proposal shall remain valid for 180 calendar days from the date of technical bid opening.
3. We understand that mathematical formulas in the official Excel BOQ are automated and verify all calculations.
4. In case of any mathematical discrepancy between unit rates and total amount, unit rates shall prevail.
Name of Authorized Signatory: ________________________________________________
Designation: _______________________________________________________________
Company Seal & Digital Signature: ___________________________________________