## Item Rate BoQ
OFFICIAL GOVERNMENT BILL OF QUANTITIES (BOQ) — FINANCIAL SCHEDULE
Tender Ref: 2026_ELCOT_541902_1 ¦ Authority: ELECTRONICS CORPORATION OF TAMIL NADU LIMITED (ELCOT)
Work: Implementation, Expansion and Multi-Year Facility Management of Tamil Nadu State Spatial Data Infrastructure (TN-SSDI)
Validate Price Bid: Rates entered by bidder must include all overheads, equipment deployment, field survey, processing & software.
Item No. | Item Description | Quantity | Units | Basic Estimated Rate (INR) | Basic Total Amount (INR) | GST Rate (%) | Total Amount with GST (INR)
1.01 | State Spatial Data Infrastructure (SSDI) Core Portal Architecture & Metadata Catalog (OGC CSW) | 1 | Platform | 7500000 |  | 18
1.02 | High-Resolution Multi-Spectral Satellite Imagery Hosting & OGC Compliant WMS/WFS/WCS Services | 1 | System | 5500000 |  | 18
1.03 | Cross-Departmental Spatial Data Standardization, ETL Pipelines & Schema Harmonic Alignment | 28 | Departments | 185000 |  | 18
1.04 | Cloud-Native Distributed Spatial Database (PostGIS Cluster) with Geo-Replication | 1 | Cluster | 4200000 |  | 18
1.05 | Decision Support GIS Application Modules (Disaster Management, Industrial Land Bank, Utilities) | 4 | Modules | 1800000 |  | 18
1.06 | API Gateway, Mobile SDK and Open Data Developer Portal | 1 | System | 2600000 |  | 18
1.07 | 3-Year Enterprise SLA Technical Support, Cybersecurity Audits (CERT-In) and Maintenance | 36 | Months | 195000 |  | 18
SUB-TOTAL BASIC CONTRACT VALUE (INR)
APPLICABLE GOODS & SERVICES TAX (GST @ 18%) (INR)
TOTAL ESTIMATED TENDER VALUE INCLUSIVE OF ALL TAXES (INR)

## Milestone Schedule
PROJECT DELIVERABLE MILESTONES & DISBURSEMENT PERCENTAGES
Milestone | Deliverable Scope | Timeline | Payment Share (%) | Cumulative (%)
M-1 | Inception Report, Project Quality Plan & Statutory Clearances | T0 + 30 Days | 10 | 10
M-2 | DGPS Ground Control Network, Flight Survey & Raw Sensor Verification | T0 + 90 Days | 20 | 30
M-3 | Ortho-mosaic Processing, Feature Extraction & 50% Field Verification | T0 + 180 Days | 25 | 55
M-4 | 100% Survey Completion, UPIN Geo-tagging & Database Validation | T0 + 270 Days | 25 | 80
M-5 | Web GIS Portal Deployment, User Acceptance Testing (UAT) & Training | T0 + 330 Days | 10 | 90
M-6 | Final Handover Sign-off & Commencement of AMC / Operations | T0 + 365 Days | 10 | 100

## Bidder Declaration
STATUTORY UNDERTAKING BY COMMERCIAL BIDDER
1. We confirm that the rates quoted above in the Item Rate BoQ are complete and inclusive of all taxes,
duties, levies, transportation, insurance, survey sensor equipment, software licenses, and field manpower.
2. The financial proposal shall remain valid for 180 calendar days from the date of technical bid opening.
3. We understand that mathematical formulas in the official Excel BOQ are automated and verify all calculations.
4. In case of any mathematical discrepancy between unit rates and total amount, unit rates shall prevail.
Name of Authorized Signatory: ________________________________________________
Designation: _______________________________________________________________
Company Seal & Digital Signature: ___________________________________________